## Proj. por Eng. (hidden)
PROJETOS POR ENGENHEIROS
CATEGORIA | Responsavel | LCP | Projetos | 2020 | 2021 | Prev. Termino
CAPITAL | BARBAN | LCP-180117 | SAO - NEW ORBITREAD MACHINE | 378.7 | 5.5679 | 2021-03-01
CAPITAL | BARBAN | LCP-180150 | SAO - SHEROGRAPHY UPGRADE (OBSEOLESCENCE AND SOFTWARE) | 10.7 | 0 | 2020-11-01
CAPITAL | BARBAN | LCP-190186 | CORSAIR Project | 964.9 | 50.6 | 2021-03-01
DIRECT CHARGE | BARBAN | EEX-200001-00-09 | ESTUDO ADEQ. CARGA/POTENCIA CM EPIACABA | 2.4 | 0 | 2020-12-01
CAPITAL | BARBAN | LCP-200116 | UPG PLC AUTOMAX EXTRUDER SBO | 0 | 492 | 2021-09-01
|  |  | TOTAL | 1356.7 | 56.1679 | -
CAPITAL | CASTANHARO | LCP-190011 | QCO - MOTHER ROLL CALEMARD | 4.9 | 0 | 2020-12-01
CAPITAL | CASTANHARO | LCP-190078 | REPLACEMENT OF ROLLS CAL3R | 662.2 | 608.9 | 2021-04-01
CAPITAL | CASTANHARO | LCP-200009 | AME-REPL & UPG OF ROLLS IN CAL4R2 | 0 | 804.6275 | 2021-06-01
CAPITAL | CASTANHARO | LCP-190231 | HOTFORMER UPGRADE LINNER AND SCREW | 61.56 | 0 | 2020-11-01
CAPITAL | CASTANHARO | LCP-200037 | REPLACE OF ROLLS IN HOTFORMER | 32.5 | 237.9 | 2021-03-01
CAPITAL | CASTANHARO | LCP-200030 | REPL OF ACCELERATOR TUBE - EBP SYSTEM FOR CAL3R | 81.9 | 0 | 2020-09-01
CAPITAL | CASTANHARO | LCP-190144 | WIRE CALENDER EDGE TRIMMING DEVICE | 0 | 88.932 | 2021-03-01
CAPITAL | CASTANHARO | LCP-190184 | WIRE CALENDER WIGWAG FEED CONVEYOR | 0 | 132.4 | 2021-04-01
CAPITAL | CASTANHARO | LCP-200001 | AME-REPL & UPG OF ROLLS IN CAL3R | 0 | 1207.3428 | 2021-06-01
CAPITAL | CASTANHARO | LCP-200008 | AME-REPL & UPG OF ROLLS IN CAL4R1 | 0 | 918.7207 | 2021-08-01
CAPITAL | CASTANHARO | LCP-200076 | HOTFORMER UPG LINNER AND SCREW STATIONS #04 | 0 | 144.029 | 2021-03-01
QUARTELY | CASTANHARO | LCP-200026-18 | CTI-006-04-00028 - CALENDER ROLL CRASH PROTECTION | 49 | 0 | 2020-12-01
DIRECT CHARGE | CASTANHARO | EEX-200001-00-19 | RELOCAÇÃO CONJ. FACA MOINHO 84 BB#04 | 3.463 | 0 | 2020-12-01
DIRECT CHARGE | CASTANHARO | EEX-200001-00-11 | READEQUAÇÃO CECOM CALANDRA Z | 2.5 | 0 | 2020-12-01
DIRECT CHARGE | CASTANHARO | EEX-200001-00-12 | RELOCAR RACK DA FISCHER PARA AREA DE FITINHA | 14 | 0 | 2020-12-01
|  |  | TOTAL | 895.523 | 4142.852 | -
CAPITAL | FABIO | LCP-180080 | COMMERCIAL TIRE BUILDING MACHINE | 300 | 0 | 2020-12-01
CAPITAL | FABIO | LCP-190089 | AME - X-ray B upgrade | 90.7 | 0 | 2020-11-01
CAPITAL | FABIO | LCP-190150 | B1 - UPGRADE PC-ETMS BALANCE AND FVM MACHINE | 32 | 30 | 2021-02-01
CAPITAL | FABIO | LCP-190159 | (02) TRANSFER ORING NGTTS & MONO CUTTER IN ANGLE | 60 | 0 | 2020-12-01
CAPITAL | FABIO | LCP-200092 | AME-METAL DETECTOR IN CAL 4R2 | 100 | 145 | 2021-03-01
CAPITAL | FABIO | LCP-200028 | REPLACEMENT OF RING IN KOKUSAI | 299.67 | 0 | 2020-12-01
CAPITAL | FABIO | LCP-200023 | UPGRADE KOKUSAI #01 | 300 | 86.005 | 2021-02-01
CAPITAL | FABIO | LCP-190061 | SECURITY IMPROVEMENT IN (8) APEX APPLIER - NGTTS | 0 | 372.8005 | 2021-06-01
DIRECT CHARGE | FABIO | EEX-200001-00-17 | IDLE ASSETS FAM | 94 | 0 | 2020-12-01
|  |  | TOTAL | 1276.37 | 633.8055 | -
CAPITAL | HENRIQUE | LCP-180115 | AME - CLOSED WATER SYSTEM - MIXERS SUBSTATIONS | 4 | 0 | 2020-09-01
CAPITAL | HENRIQUE | LCP-180139 | POWER HOUSE STEAM TURBINE | 62.7 | 0 | 2020-11-01
CAPITAL | HENRIQUE | LCP-180137 | (10) VDF PANEL INSTALLATION | 0 | 50.7 | 2021-03-01
CAPITAL | HENRIQUE | LCP-190203 | SAFETY SYSTEM RIVER PUMP AREA | 0 | 23.3 | 2021-04-01
QUARTELY | HENRIQUE | LCP-200026-20 | RETROFIT IHM COMPRESSOR CENTAC #14 | 25 | 0 | 2020-12-01
DIRECT CHARGE | HENRIQUE | EEX-200001-00-06 | EST. VIAB. EFICIENCIA ENERGETICA RED. CONSUMO VAPOR | 5 | 0 | 2020-12-01
DIRECT CHARGE | HENRIQUE | EEX-200001-00-07 | EST. VIAB. OTIM. TERMICA DOS PAINEIS ELETRICOS FF B1 E TBM | 15 | 0 | 2020-12-01
DIRECT CHARGE | HENRIQUE | EEX-200001-00-08 | EST. VIAB. SIST. PRESSUR. HID. 2400 LBS PRENSAS OTR | 1.6 | 0 | 2020-12-01
DIRECT CHARGE | HENRIQUE | EEX-200001-00-13 | RELOCAR SECADOR AR SALA PÓ MIXER #07 PARA AREA EXTERNA | 8 | 0 | 2020-12-01
DIRECT CHARGE | HENRIQUE | EEX-200001-00-14 | ESTUDO SEL. CARGA/POT SEF#901 - CUB#05 | 1.6 | 0 | 2020-12-01
DIRECT CHARGE | HENRIQUE | EEX-200001-00-20 | Relocação de Alimentação de potência do Chiller do BB#07 | 9.5 | 0 | 2020-12-01
DIRECT CHARGE | HENRIQUE | EEX-200001-00-20 | RELOCAÇÃO DA ALIMENTAÇÃO POTENCIA CHILLER BB#07 | 9.5 | 0 | 2020-12-01
|  |  | TOTAL | 141.9 | 74 | -
CAPITAL | MAGNANI | LCP-190213 | ALPHA SHEAR LETOFF TREATMENT | 17.2 | 100 | 2021-03-01
CAPITAL | MAGNANI | LCP-190117 | CAP-X-RAY GREEN POINT MARKER | 0 | 39 | 2020-02-01
CAPITAL | MAGNANI | LCP-190229 | UPGRADE TYLOR SYSTEM IN MRT CURING PRESSES | 60 | 60 | 2021-04-01
QUARTELY | MAGNANI | LCP-200026-03 | ADEQ. PROT. ESTEIRA INFERIOR FF B2 | 50 | 0 | 2020-12-01
QUARTELY | MAGNANI | LCP-200026-06 | UPG MÁQ. GIRAR TAMBOR OTR | 43 | 0 | 2020-12-01
QUARTELY | MAGNANI | LCP-200026-08 | AME-CAMERAS INSTALLATION | 48 | 0 | 2020-12-01
QUARTELY | MAGNANI | LCP-200026-04 | AME-BATHROOM ADEQUATION FAM NR24 | 50 | 0 | 2020-12-01
QUARTELY | MAGNANI | LCP-200026-13 | ADEQ. SIST. ATERRAMENTO PIT STOPS | 18 | 0 | 2020-12-01
QUARTELY | MAGNANI | LCP-200026-23 | NEW TRUCK FOR CLEANING | 30 | 0 | 2020-12-01
QUARTELY | MAGNANI | LCP-200026-07 | PROLONGAR PLATAFORMA RETIRADA ENRROSCO NGTTS | 38 | 0 | 2020-12-01
QUARTELY | MAGNANI | LCP-200026-09 | UPG TROCADOR CALOR PORÃO OTR | 47 | 0 | 2020-12-01
DIRECT CHARGE | MAGNANI | EEX-200001-00-02 | APRECIAÇÃO DE RISCO NR12 | 28 | 0 | 2020-12-01
DIRECT CHARGE | MAGNANI | EEX-200001-00-10 | EST. VIAB. MAQUINA TAMBOR OTR | 6 | 0 | 2020-12-01
CAPITAL | MAGNANI | LCP-200115 | BT DRUM WYKO UPGRADE | 0 | 100 | 2021-03-01
CAPITAL | MAGNANI | LCP-200117 | PROJETO PRODITIVIDADE B2 | 96 | 0 | 2020-12-01
|  |  | TOTAL | 531.2 | 299 | -
CAPITAL | PARRAS | LCP-180014 | SEMI AUTOMATIC BEAD STAPLER | 9.6403 | 0 | 2020-11-01
CAPITAL | PARRAS | LCP-180095 | AME - METAL DETECTOR IN CALANDERS (FORD PROJECT) | 15 | 0 | 2020-10-01
CAPITAL | PARRAS | LCP-180114 | LAMINATOR PROFILE AUTOMATION | 0 | 129 | 2021-08-01
CAPITAL | PARRAS | LCP-180174 | METAL DETECTOR IN EXTRUDERS | 317.4 | 0 | 2020-12-01
CAPITAL | PARRAS | LCP-180179 | UPG DRIVES & CONTROLS – CAL3R | 5 | 112.6353 | 2021-06-01
CAPITAL | PARRAS | LCP-190020 | AME - ROBOT FOR BEAD WINDER | 123.4 | 72 | 2021-04-01
CAPITAL | PARRAS | LCP-190057 | AME - UP GRADE EXTRUSORA Q5 ( AUTOMAX ) PHASE 2 | 4 | 211.7 | 2021-03-01
CAPITAL | PARRAS | LCP-190142 | NEW OIL LINE SYDININI | 120 | 240.2 | 2021-04-01
CAPITAL | PARRAS | LCP-190149 | B1 - UPGRADE HMI HF PLT2 | 19.3 | 0 | 2020-11-01
CAPITAL | PARRAS | LCP-190202 | MIXER#6 BODY REPLACEMENT | 1200 | 231.3 | 2021-04-01
CAPITAL | PARRAS | LCP-190208 | AME- (1) BALANCE MACHINE MARKER (DOWN SIDE) | 440.3 | 120.2 | 2021-03-01
CAPITAL | PARRAS | LCP-200077 | AME - Bijinic Tank | 120 | 73.9 | 2021-03-01
CAPITAL | PARRAS | LCP-200053 | MIXER#7 BODY REPLACEMENT | 0 | 1340 | 2021-12-01
CAPITAL | PARRAS | LCP-XXXXXX | AME - STERLINE - SOYBEAN OIL | 50 | 107.17 | 2021-03-01
CAPITAL | PARRAS | LCP-XXXXXX | AME - UPGRADE DRIVE + MOTOR AC MILL MIXER#3 | 30 | 0 | 2021-03-01
DIRECT CHARGE | PARRAS | EEX-200001-00-16 | PROJETO AS-BUILT ZIG ZAG CAL-Z | 3.7 | 0 | 2020-12-01
|  |  | TOTAL | 2454.0403 | 2638.1053 | -
CAPITAL | QUINTAL/REGINALDO | LCP-170154 | BRZ - AVCB NEW WAREHOUSE-BUILDING COMMERCIAL | 42.1 | 0 | 2020-09-01
CAPITAL | QUINTAL/REGINALDO | LCP-180002 | FAM AVCB PHASE II EMERGENCY LIGHTINING AND ALARMS | 4 | 179 | 2021-06-01
CAPITAL | QUINTAL/REGINALDO | LCP-180180 | ANCHOR SYSTEM & SAFETY LINE - PHASE II | 35.1 | 0 | 2020-09-01
CAPITAL | QUINTAL/REGINALDO | LCP-180010 | (3) NEW 52 HYDRAULIC CONSUMER PRESSES | 20 | 0 | 2020-08-01
CAPITAL | QUINTAL/REGINALDO | LCP-190215 | CONTOUR CORRECTION MACHINE | 0 | 1244 | 2021-12-01
CAPITAL | QUINTAL/REGINALDO | LCP-190199 | MOBILE DOCK LEVELER FOR NEW WAREHOUSE | 16.1 | 0 | 2020-11-01
CAPITAL | QUINTAL/REGINALDO | LCP-200011 | PCI IN (6) ROGERS MECHANICAL PRESSES | 0 | 774.099 | 2021-04-01
OUTROS | QUINTAL/REGINALDO | LCP-XXXXXX | INSTALACAO DE LONADO RESTAURANTE | 10 | 0 | 2020-08-01
OUTROS | QUINTAL/REGINALDO | LCP-XXXXXX | INSTALACAO DE LONADO GOODPLACE | 10 | 0 | 2020-08-01
OUTROS | QUINTAL/REGINALDO | LCP-XXXXXX | INSTALACAO ENFARDADEIRA DEPTO 85 | 10 | 0 | 2020-10-01
DIRECT CHARGE | QUINTAL/REGINALDO | EEX-200001-00-05 | LICENÇA DE OPERAÇÃO CETESB (2) VMI & NAKATA | 5 | 0 | 2020-12-01
DIRECT CHARGE | QUINTAL/REGINALDO | EEX-200001-00-18 | ESTUDO ANALISE MUNICIO & PREFEITURA | 2.7778 | 0 | 2020-12-01
|  |  | TOTAL | 155.0778 | 2197.099 | -
CAPITAL | RAGONHA/SIA | LCP-180003 | GEM PROJECT EMC GRAVATAÍ | 74.1 | 0 | 2020-12-01
CAPITAL | RAGONHA/SIA | LCP-180081 | GEM PROJECT SÃO CAETANO DO SUL | 117.5 | 0 | 2020-12-01
CAPITAL | RAGONHA/SIA | LCP-190132 | VEHICLE DYNAMICS AREA (VDA) REPAVING | 88.5 | 0 | 2020-10-01
CAPITAL | RAGONHA/SIA | LCP-190140 | UPGRADE RING 18" CUV IN MC ANCHIETA | 213.5 | 0 | 2020-11-01
CAPITAL | RAGONHA/SIA | LCP-XXXXXX | UPGRADE TPMS SYSTEM MC GRAVATAI | 40 | 0 | 2021-03-01
|  |  | TOTAL | 533.6 | 0 | -
CAPITAL | RICARDO | LCP-180149 | EXHAUST SYSTEM - LINES A/B & G/H CONSUMER PRESSES | 35.5 | 100.2 | 2021-05-01
CAPITAL | RICARDO | LCP-190092 | SHIPMENT SAFETY IMPROVEMENT | 1.3 | 0 | 2020-09-01
CAPITAL | RICARDO | LCP-190204 | INFLATION TESTING MACHINE | 85.5 | 46.1 | 2021-03-01
CAPITAL | MAGNANI | LCP-180178 | WIND UP LET OFF NGTTS#5 & #8 | 33.4 | 81.8139 | 2021-04-01
DIRECT CHARGE | RICARDO | EEX-200001-00-15 | RELOCAR BANCADA MANUT. VULC.B1 PARA FRENTE AS PRENSAS | 1.2 | 0 | 2020-12-01
DIRECT CHARGE | RICARDO | EEX-200001-00-03 | ESTUDO VIABILIDADE SISTEMA FIO SOLTO | 1 | 0 | 2020-12-01
DIRECT CHARGE | RICARDO | EEX-200001-00-04 | ESTUDO VIABILIDADE SISTEMA DAMI K7 | 4.3 | 0 | 2020-12-01
QUARTELY | RICARDO | LCP-200026-10 | AME-GATE HOUSE IMPROVEMENT | 48 | 0 | 2020-12-01
|  |  | TOTAL | 162.2 | 228.1139 | -

## Comparativo 7+5 e 8+4 (hidden)
| 1 st Quarter |  |  | 2 st Quarter |  |  | 3 st Quarter |  |  | 4 st Quarter |  |  | ANUAL
| Jan | Fev | Mar | Abr | Mai | Jun | Jul | Ago | Set | Out | Nov | Dez
6+6 | 1 st Quarter Jan: 2296.2831; 2 st Quarter Abr: 1831.8923; 3 st Quarter Jul: 2780.2244; 4 st Quarter Out: 4545.6947 | 11454.0945
7+5 | 1 st Quarter Jan: 2296.2831; 2 st Quarter Abr: 1836.4852; 3 st Quarter Jul: 2711.6014; 4 st Quarter Out: 6607.5947 | 13451.9644
8+4 | 1 st Quarter Jan: 2296.2831; 2 st Quarter Abr: 1836.4852; 3 st Quarter Jul: 2319.0696; 4 st Quarter Out: 6594.8413 | 13046.6791
[9 empty] | -392.5318 |  |  | -12.7534
RISCOS | 3 st Quarter Jul: Á GASTAR
100 | 1 st Quarter Jan: AKRON MESNAC; 3 st Quarter Jul: SET-DEZ; 3 st Quarter Ago: 7.2
10 | 1 st Quarter Jan: SHEROGRAFIA; 3 st Quarter Jul: P.O; 3 st Quarter Ago: -3.7
50 | 1 st Quarter Jan: RAIO X (VISTO); 3 st Quarter Jul: S.C; 3 st Quarter Ago: -2.4
160 | 1 st Quarter Jan: TOTAL; 3 st Quarter Jul: NEW PROJ.; 3 st Quarter Ago: -1.8
OFFSET
60 | 1 st Quarter Jan: CAL3R
27 | 1 st Quarter Jan: CAL4R1
45 | 1 st Quarter Jan: CAL4R2
159 | 1 st Quarter Jan: GEARBOX 10"
291 | 1 st Quarter Jan: TOTAL

## CONTINGENCIA 8+4 (hidden)
CAPEX - PLANO DE CONTINGÊNCIA
| PROJETO | DESCRIÇÃO | ENGENHEIRO | VALOR | DEADLINE PARA AGIR
| LCP-200119 | REPL MAIN GEARBOX 6” & 10” MRT EXTRUDER | GUSTAVO PARRAS | 159
| LCP-200023 | UPGRADE KOKUSAI #01 | FABIO MORAES | 300
| LCP-200008 | AME-REPL & UPG OF ROLLS IN CAL4R1 | DIEGO CASTANHARO | 13 | Imediato - Estoque | REQUISITAR - PUXAR | OFFSETAR COM LCP-200125
| LCP-200009 | AME-REPL & UPG OF ROLLS IN CAL4R2 | DIEGO CASTANHARO | 43 | Imediato - Estoque | REQUISITAR - PUXAR | OFFSETAR COM LCP-200125
| LCP-200001 | AME-REPL & UPG OF ROLLS IN CAL3R | DIEGO CASTANHARO | 55 | Imediato - Estoque | REQUISITAR - PUXAR | OFFSETAR COM LCP-200125
| LCP-180117 | SAO - NEW ORBITREAD MACHINE | CHARLES BARBAN | 378
|  | QUARTELY - NOVOS PROJETOS | BASSO | 300
|  | PROJETO DAS CAMERAS | HUELITON | 170
|  | MOTOR DO BBY#03 | GUSTAVO PARRAS
| LCP-200125 | UPGRADE MICROPOISE BALANCE MACHINE ANCHIETA | DIEGO RAGONHA | 152
| TOTAL |  |  | 1459
ANALISE DE RATE

## WORST (hidden)
[33 empty] | 10.04% |  |  | #REF! | 0 |  | 0 |  |  |  | 23280.1848 | 18424.3883 | 12796.5224 | 18357.7136 | 608403.877 | 10697.1582 | 619101.0351 | 17473.9394 | 483.8 | 374.3421 | 222.5733 | 624.0802 | 422.4005 | 425.8098 | 277.91 | 498.8311 | 603.789 | 1582.62 | 568.9361 | 975.8485 | 1604.4886 | 1869.9287 | 875.9814 | 950.3759 | 1383.8806 | 1495.1307 | 1904.0396 | 2338.366 | 1819.7948 | 1948.0765 | 4559.8308 | 3882.8028 | 4390.5299 | 48577.2295 | 515.1112 | 1911.6337 | 1300.3176 | 2324.0944 | 3386.813 | 8649.0841 | 1834.7802 | 11080.2028 | 2236.6438 | 3583.5118 | 1546.6686 | 10208.3686 | 20289.036 | 1745.666 | 2207.546 | 1807.546 | 1686.8793 | 1624.9993 | 1624.9993 | 1629.0333 | 1629.0333 | 1583.3333 | 1583.3333 | 1583.3333 | 1583.3333 | 169.3009 | -507.7271 | 13083.4095 | 4390.5299 | 65058.9639 | 55379.1463 | 9440.8176 | #REF! |  | 1424.2321 | 3057.2995 | 4315.4353 | #REF! | 144563.3144 | 86993.8887 | 18566.0599 | 1926.555 | 107486.5035 | 37076.8108 | #N/A | #N/A
| GESTÃO DE PROJETOS CAPEX 2021 ($000) | [25 empty] | 1701.3099 | [22 empty] | 2021 | [25 empty] | 2022 | [12 empty] | 2023
[50 empty] | 17473.9394 | 1424.2321 | [5 empty] | 3057.2995 | [5 empty] | 4315.4353 | [5 empty] | 8676.9725 | [6 empty] | 48577.2295 | 3727.0624 |  |  | 14359.9915 |  |  | 15151.6267 |  |  | 15338.5489 |  |  | 20289.036 | 5760.758 |  |  | 4936.878 |  |  | 4841.4 |  |  | 4750 |  |  | 169.3009 |  |  | 4390.5299 |  |  |  | #REF! | [5 empty] | 144563.3144 | 86993.8887 | 18566.0599 | 1926.555 | 107486.5035 | 37076.8108
| N. | NUM. PROJETO (WBS) | NUM. HOPPER | OSEP | Ano | Data Abertura | Data de Aprovação (GBS) | Data Encerramento (TECO - SAP) | Data Encerramento (politica 18 meses ~ 547 dias) | Data TECO (politica 18 meses ~ 547 dias) | Data CLOSE (politica 24 meses ~ 730 dias) | LISTADO NO E.S Q3 | E.S NO Q1 | E.S ATÉ DEZ | DEVE DEIXAR A LISTA NO: | AOP 2022 | PLANTA | DIVISÃO | TNC | New C/O | NUM. DOC APPROVAL | AJUSTE REG / ICP / PROJETO | RESPONSÁVEL | NOME PROJETO | PROJECT TYPE | SYSTEM STATUS SAP | COMENTÁRIO STATUS DO PROJETO | TECO DATA PREVISTA | CAPITALIZAÇÃO DATA PREVISTA | FATURAR PO + ENTREGAS DE NF | SCOPE CHANGE ou OVERRUN | DATA E MOTIVO | % OVERRUN | ICP vs LCP Horas de Akron | Área do Projeto | Valor alocado OUT a DEZ | MATERIAL OUT/DEZ | NÚMERO DO PO (RISCOS) | MÃO DE OBRA OUT / DEZ | VALOR IMPORTADO | DATA DE PRONTIDÃO | FRETE (AEREO/MARITIMO) | TOTAL 2019 | AOP 2020 | TOTAL 2020 | AOP 2021 | Capital | Expenses | TOTAL INVEST. | TOTAL 2021 | JAN OBJ | Jan Real | FEV OBJ | Fev Real | MAR OBJ | Mar Real | ABR OBJ | Abr Real | MAI OBJ | Mai Real | JUN OBJ | Jun Real | Jul OBJ | Jul Real | AGO OBJ | Ago Real | SET OBJ | Set Real | OUT OBJ | Out Real | Nov Obj. | Nov Real | Dez OBJ | Dez Real SAP | Dez ENG | TOTAL 2022 Carryover | Jan | Fev | Mar | Abr | Mai | Jun | Jul | Ago | Set | Out | Nov | Dez | 2023 | Jan | Fev | Mar | Abr | Mai | Jun | Jul | Ago | Set | Out | Nov | Dez | Comparativo OBJ vs ESTIMADO ENG | Comparativo REAL vs ESTIMADO ENG | Janeiro a Novembro | Dezembro | Soma 2021 e 2022 | Soma 2021+2022 do 10+2 | Diferença | Comprometido vs base Nov e Dez | Comentários sobre o que falta comprometer | Q1 | Q2 | Q3 | Q4 | BUDGET | ACTUAL | PO | SC | ASSIGNED | AVAILABLE | Procv | Diferença
| 25 | ICP-200043 | [14 empty] | AME |  |  | Carryover |  | ICP | FABIO MORAES | AMERICANA CONSUMER HMC TIRE BUILDING | Capability | REL | SET:ICP não cumpriu o objetivo de U$111,1, então foi passado a diferença de 72,8 para Novembro DEZ: Prensa #1 e #2: 379K Prensa #3 e #4: 379K Tooling TBM: 110K Apexer: 872K (vai ficar pronta dia dia 17/12 para coleta). Precisa ter um armazem para guardar o material. Pagamento parcial esteira vulca 43K Horas de Engenharia 4k Estimativa Inicial: $2,800MM Colocado na Base $333k pela Região, referente a: (+3) 52” HMC Presses-in (VMI Projec) = Total ICP 3,133M Em agosto/21 ficou definido um total de 2,402MM em ICP, Em Outubro/21, reduziu a base para 1,965MM | [6 empty] | LCP-200185 |  | #REF! | [7 empty] | 0 | 2184.4436 | 6.3029 | 14300 |  | 14300 | 1920.926 | 0 | 6.3029 | 0 | 8.8713 | 0 | 9.7776 | 0 | 16.6597 | 0 | 18.0637 | 0 | 44.8694 |  | 59.022 |  | 47.9417 | 111.0783 | 38.3047 | 340 | 160.7295 | 612.7 | 520.1197 | 1632.7 | 135.7487 | 990.264 | -4977.5 |  | -949 | -949 | -949 | -949 | -1178.7 | -2.8 | [5 empty] | 0 | [12 empty] | 642.436 | -854.5153 | 930.662 | 990.264 | 6898.426 | -2097.7577 | 8996.1837 | #REF! |  | 24.9518 | 79.5927 | 145.2683 | #REF! |  |  | 10421.6691 | 0 |  |  | -4587 | 390.5
| 203 | LCP-210078 | Informar |  | 2021 | 2021-04-08 | 2021-06-21 |  | -933.336 | 2022-12-20 | 2023-06-21 | [5 empty] | AME | B2 | CONSTRUÇÃO | New | 3981729 | PROJETO | CARLOS SERAFIM | PNC - PNEUMATIC CORE CONSTRUCTION | Quality | REL | DEZ: Sera Embalado até dia 17 (embarque aéreo) Pagamento em Transito dos Tambores (carta na manga de mais 60) Total será de 330K. AGUARDANDO BOOKING Novos Tambores para PLT2 4 TAMBORES: 2 ARO 17" / 2 ARO 18" Tem 1 Pedido para Peças Tem 1 Pedido dos 4 tambores Tambores: AGO: 150K de Downpayment em Previsão de embarque: 23/12 | 2022-11-30 | 2022-06-30 | 2023-04-30 |  |  |  | ICP-210032 |  | #REF! | PREVISÃO DE ENTREGA PARA DEZEMBRO/21, SERÁ PAGO EM TRANSITO | AGUARDANDO PEDIDO DE COMPRAS PARA O RC 1001669935 E 1001677591 (TAMBORES E SUB COMPONENTES) | NÃO POSSUI RISCOS | 684,000.00 USD | PREVISTO PARA DEZ/21 | MARITIMO |  |  |  | 999.7 | 1357.7249 | 25 | 1382.7249 | 483.926 | [6 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0.2 | 0.30803 | 0 | 0.61799 | 269.1 |  | 483 | 873.7944 |  | 413.9344 | 30 | 30 | 104.2 | 164.2305 | 18 | 41.1432 | 41.1432 | 31.1432 |  |  | 0 | [12 empty] | -213.9 | -483 | 0.92602 | 483 | 1357.7205 | 1357.7025 | 0.01799 | #REF! |  | 0 | 0 | 0 | #REF! | 1369.7249 | 0.92602 | 529.887 | 7.1988 | 538.0118 | 831.7131 | 1207.7249 | -333.9305
|  | ICP-210069 | [14 empty] | AME |  |  | New |  | ICP | CARLOS SERAFIM | AME Micropoise AIT Balance | Facilities Sustaining | REL | [7 empty] | LCP-210212 | [15 empty] | 100 | [24 empty] | 100 | -100 |  |  |  |  | -100 | [21 empty] | -100 | [13 empty] | 463.554 | 463.554
| 188 | LCP-210007 | N/A |  | 2021 | 2020-12-16 | 2021-02-12 |  | -1064.336 | 2021-12-31 | 2022-03-31 |  | SIM | SIM | AQ4/21 | AQ1/22 | AME | STAFF | ENGENHARIA | New | 3635316 | PROJETO | RICARDO ALNIEZI | AME - 2021 MISCELLANEOUS ANNUAL BUDGET | Facilities Sustaining | REL | 20k Vulcaweld vai para 2022 | 2021-12-31 | 2021-12-31 | 2021-12-31 | Overrun |  | 9.87% |  |  | #REF! | [9 empty] | 800.0455 | 878.96 |  | 878.96 | 845.8915 |  |  | 0 |  | 0 | 0 | 0 | 9.2803 | 0 | 38.7385 | 0 | 79.836 | 71.3616 | 57.965 | 82.8544 | 46.2651 | 203.967 | 154.5838 | 103.2709 | 92.2797 | 213.4004 | 145.141 | 255.1532 | 197.0749 | 221.802 | 33.106 | 33.106 | [11 empty] | 0 | [12 empty] | 33.3512 | -24.7271 | 624.0895 | 221.802 | 878.9975 | 878.8652 | 0.13229 | #REF! |  | 0 | 127.8549 | 258.8139 | #REF! | 878.96 | 821.2056 | 53.9173 | 7.3433 | 882.4662 | -3.5062 | 0 | 33.106
| 1 | ICP-150042 | [14 empty] | AME |  |  | Carryover |  | ICP | REGIÃO | TWIN SCREW MIXER#6 | Facilities Sustaining | CLSD |  |  |  | OK | [5 empty] | #REF! | [7 empty] | 0 | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 | 0 | 0 | #REF! | [7 empty] | 0
| 2 | ICP-160008 | [14 empty] | AME |  |  | Carryover |  | ICP | REGIÃO | UPGRADE OF MRT YXLON | Facilities Sustaining | CLSD | [9 empty] | #REF! | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 | 0 | 0 | #REF! | [7 empty] | 0
| 3 | ICP-160011 | [14 empty] | AME |  |  | Carryover |  | ICP | REGIÃO | Americana 2016 MISCELLANEOUS PROJECT | Facilities Sustaining | CLSD | [9 empty] | #REF! | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 | 0 | 0 | #REF! | [7 empty] | 0
| 4 | ICP-160022 | [14 empty] | AME |  |  | Carryover |  | ICP | REGIÃO | Americana REPLACEMENT OF WIRE CORD DETEC | Facilities Sustaining | CLSD | [9 empty] | #REF! | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 | 0 | 0 | #REF! | [7 empty] | 0
| 5 | ICP-180007 | [14 empty] | BRZ |  |  | Carryover |  | ICP | REGIÃO | Americana AVCB New Warehouse-Bldg Comm | SAG | CLSD | [9 empty] | #REF! | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 | 0 | 0 | #REF! | [7 empty] | 0
| 6 | ICP-180009 | [14 empty] | AME |  |  | Carryover |  | ICP | REGIÃO | Americana (3) 52" Hydraulic Cons Presses | Capability | CLSD | [7 empty] | LCP-180010 |  | #REF! | [7 empty] | 0 | 115.6419 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 | 0 | 0 | #REF! | [7 empty] | 0
| 7 | ICP-180013 | [14 empty] | AME |  |  | Carryover |  | ICP | REGIÃO | AMERICANA 2ND MRT MESNAC | Capability | CLSD |  |  |  | OK |  |  |  | LCP-180080 |  | #REF! | [7 empty] | 0 | 214.9754 | -418.0342 |  |  | 0 | -418.0342 | 0 | -418.0342 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | -418.0342 | 0 | -418.0342 | -418.0342 | 0 | #REF! |  | -418.0342 | 0 | 0 | #REF! | [7 empty] | 0
| 8 | ICP-180015 | [14 empty] | AME |  |  | Carryover |  | ICP | REGIÃO | REPLACE PLC/CCM OF BATCH OFF MIXER#3 | Facilities Sustaining | CLSD |  |  |  | OK | [5 empty] | #REF! | [7 empty] | 0 | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 | 0 | 0 | #REF! | [7 empty] | 0
| 9 | ICP-180020 | [14 empty] | MC |  |  | Carryover |  | ICP | REGIÃO | Brazil GE Mounting Project | SAG | CLSD | [9 empty] | #REF! | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 | 0 | 0 | #REF! | [7 empty] | 0
| 10 | ICP-180031 | [14 empty] | AME |  |  | Carryover |  | ICP | REGIÃO | Americana FVM Grinder Automation | Energy Conservation | CLSD |  |  |  | OK | [5 empty] | #REF! | [7 empty] | 0 | -5.5511e-17 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 | 0 | 0 | #REF! | [7 empty] | 0
| 11 | ICP-180041 | [14 empty] | MC |  |  | Carryover |  | ICP | REGIÃO | BRS GEM Project | SAG | CLSD | [9 empty] | #REF! | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 | 0 | 0 | #REF! | [7 empty] | 0
| 12 | ICP-180044 | [14 empty] | AME |  |  | Carryover |  | ICP | REGIÃO | Americana Mixer #2 Body Replacement | Facilities Sustaining | CLSD |  |  |  | OK | [5 empty] | #REF! | [7 empty] | 0 | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 | 0 | 0 | #REF! | [7 empty] | 0
| 13 | ICP-180053 | [14 empty] | AME |  |  | Carryover |  | ICP | REGIÃO | Americana Replace PLC/CCM BO Mixer#3 | Facilities Sustaining | CLSD |  |  |  | OK | [5 empty] | #REF! | [7 empty] | 0 | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 | 0 | 0 | #REF! | [7 empty] | 0
| 14 | ICP-190002 | [14 empty] | AME |  |  | Carryover |  | ICP | REGIÃO | CAPITAL Equipment To Molds Consumer Tire | Molds | CLSD |  |  |  | OK | [5 empty] | #REF! | [7 empty] | 0 | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 | 0 | 0 | #REF! | [7 empty] | 0
| 15 | ICP-190027 | [14 empty] | AME |  |  | Carryover |  | ICP | REGIÃO | Americana Upgrade MRT Xylon X-Ray | Facilities Sustaining | REL | Projeto Local já finalizado. Verificar com John Bucey se vai carcelar este PO | [6 empty] | LCP-190089 |  | #REF! | [7 empty] | 0 | 174.2051 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 | 0 | 0 | #REF! |  |  | 30.805 | 0 |  |  |  | 0
| 16 | ICP-190041 | [14 empty] | SAO |  |  | Carryover |  | ICP | REGIÃO | CORSAIR | SAG | CLSD | [7 empty] | LCP-190186 |  | #REF! | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 | 0 | 0 | #REF! | [7 empty] | 0
| 17 | ICP-190047 | [14 empty] | AME |  |  | Carryover |  | ICP | REGIÃO | AMERICANA TRANSFER O-RING, MONO CUTTER | Quality | CLSD | [7 empty] | LCP-190159 |  | #REF! | [7 empty] | 0 | -0.04652 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 | 0 | 0 | #REF! | [7 empty] | 0
| 18 | ICP-190053 | [14 empty] | AME |  |  | Carryover |  | ICP | GUSTAVO PARRAS | AMERICANA AKROMARKER FOR FVM-AAA | Quality | CLSD | [7 empty] | LCP-190208 |  | #REF! | [7 empty] | 0 | 33.1842 | -31.679 |  |  | 0 | -33.1842 | 0 | -31.679 | 0 | 186.8852 | 0 | -216.9941 | 0 | -2.2812 | 0 | 31.944 | 0 | 12.495 |  | -0.14103 | -14.5 | -13.413 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | -33.1842 | 0 | -33.1842 | -33.1842 | 0 | #REF! |  | -61.7879 | 42.1578 | -13.554 | #REF! | [7 empty] | 0
| 19 | ICP-200001 | [14 empty] | AME |  |  | Carryover |  | ICP | RICARDO TEIXEIRA | AMERICANA INFLATION TESTING MACHINE ICP-200001 | Quality | CLSD | [7 empty] | LCP-190204 |  | #REF! | [7 empty] | 0 | 12.0116 | -12.0116 |  |  | 0 | -12.0116 | 0 | -12.0116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | -12.0116 | 0 | -12.0116 | -12.0116 | 0 | #REF! |  | -12.0116 | 0 | 0 | #REF! | [7 empty] | 0
| 20 | ICP-200008 | [14 empty] | AME |  |  | Carryover |  | ICP | FABIO MORAES | AMERICANA UPGRADE KOKUSAI #1 | Facilities Sustaining | REL | NOV: Caiu valor do Eixo Spindle. Avisado Philipinas sobre o caso. Precisa ser feito o credito para zerar a linha | [6 empty] | LCP-200023 |  | #REF! | [7 empty] | 0 | 155.0155 | -154.0748 |  |  | 0 | -155.0155 | 0 | -154.0748 | 0 | 3.7699 | 0 | -0.42057 | 0 | 0.10481 | 0 | -3.2854 | 0 | 36.5626 |  | -37.1377 |  | -0.29814 |  | -0.04329 |  | 0.87101 |  | -0.79898 |  | -0.26491 | -0.26491 | 0 | [12 empty] | 0 | [12 empty] | 0.26491 | 0 | -154.7506 | -0.26491 | -155.0155 | -153.9517 | -1.0639 | #REF! |  | -150.7255 | 33.382 | -37.4792 | #REF! |  |  | 17.545 | 0 |  |  |  | 0
| 21 | ICP-200023 | [14 empty] | AME |  |  | Carryover |  | ICP | REGIÃO | AME - BT DRUM WYKO | Facilities Sustaining | CLSD | [7 empty] | LCP-200115 |  | #REF! | [7 empty] | 0 | 1.3934 | -1.3934 |  |  | 0 | -1.3934 | 0 | -1.3934 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | -1.3934 | 0 | -1.3934 | -1.3934 | 0 | #REF! |  | -1.3934 | 0 | 0 | #REF! | [7 empty] | 0
| 22 | ICP-200024 | [14 empty] | AME |  |  | Carryover |  | ICP | FABIO MORAES | AME REWIND STAT COM TBM | Facilities Sustaining | REL | Pode ser fechado pelo Bob Horn. Verificar com Bob Projeto Local já finalizado | [6 empty] | LCP-200117 |  | #REF! | [7 empty] | 0 | 0 | 0 |  |  | 0 | 1.1102e-16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.17405 | 0 | 0.22938 | 0 | 1.759 |  | -1.735 |  | -0.42745 | 73.2 | 0 |  | 0 |  | 0 |  |  |  | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 1.1102e-16 | 0 | 1.1102e-16 | 1.1102e-16 | 0 | #REF! |  | 0 | 2.1624 | -2.1624 | #REF! | [7 empty] | 0
| 23 | ICP-200033 | [14 empty] | AME |  |  | Carryover |  | ICP | GUSTAVO PARRAS | Americana Mixer #6 Body Replacement | Facilities Sustaining | TECO | Pode ser fechado pelo Bob Horn. Verificar com Bob Projeto Local já finalizado | [6 empty] | LCP-190202 |  | #REF! | [7 empty] | 0 | 1.0731 | -1.2541 |  |  | 0 | -1.2541 | 0 | -1.2541 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | -1.2541 | 0 | -1.2541 | -1.2541 | 0 | #REF! |  | -1.2541 | 0 | 0 | #REF! | [7 empty] | 0
| 24 | ICP-200037 | [14 empty] | AME |  |  | Carryover |  | ICP | CARLOS SERAFIM | AME PCI (6) ROGERS 47" PRESSES | Capability | REL | [7 empty] | LCP-200011 |  | #REF! | [7 empty] | 0 | 132.954 | 0 |  |  | 0 | 307.6388 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 292.4988 |  | 0.21372 |  | -0.11925 |  | -0.09447 |  | 0 |  | 0.37088 | -425.8 | 14.7691 | 14.7691 | -440.6 | -440.6 | [11 empty] | 0 | [12 empty] | -440.5691 | 0 | 292.8697 | 14.7691 | 748.2388 | -133.0012 | 881.24 | #REF! |  | 0 | 292.4988 | 0 | #REF! |  |  | 106.3632 | 0 |  |  |  | 440.6
| 26 | ICP-210002 | [14 empty] | AME |  |  | Carryover |  | ICP | GUSTAVO PARRAS | Americana Mixer BB#07 | Facilities Sustaining | REL | Projeto Local ainda em andamento | [6 empty] | LCP-200053 |  | #REF! | [9 empty] | 0 |  |  |  | 14.1625 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 2.1684 | 0 | 757.7502 | -772.7837 | -750.5721 | -772.8 | -4.4005 | -772.8 | -1.0651 | -770.093 | 25.5653 |  | -28.2857 |  | 13.0019 | 13.0019 | -14.2 | -14.2 | [11 empty] | 0 | [12 empty] | -13.0019 | 0 | 1.1606 | 13.0019 | 28.3625 | 29.4463 | -1.0838 | #REF! |  | 0 | 759.9187 | -756.0376 | #REF! | [6 empty] | 0 | 14.2
| 27 | ICP-210004 | [14 empty] | AME |  |  | Carryover |  | ICP | GUSTAVO PARRAS | AME MATTEUZZI RRM45 SMART GRINDER (CONTOUR CORRECTION) | Quality | REL | DOWNPAYMENT JUNHO = 180K a confirmar com John Bucey | [6 empty] | LCP-190215 |  | #REF! | [9 empty] | 0 |  |  |  | 234.4671 |  | 0 |  | 0 | 0 | 0.98029 | 0 | 3.2568 | 0 | 0.46366 | 0 | -0.14721 | 180 | 4.1022 |  | -9.7273 | 180 | 178.4925 |  | -3.3104 |  | 30.0186 |  | 30.338 | 30.338 | -234.5 |  |  | -234.5 |  | 417 |  | -417 | [5 empty] | 0 | [12 empty] | -30.338 | 0 | 204.1291 | 30.338 | 468.9671 | -7.1895 | 476.1566 | #REF! |  | 0.98029 | 3.5732 | 172.8674 | #REF! |  |  | 417.5055 | 0 |  |  | -186.3 | 48.2
| 28 | ICP-210011 | [14 empty] | AME |  |  | New |  | ICP | GUSTAVO PARRAS | AME Mill Drive #3 Upgrade | Facilities Sustaining | REL | Projeto Local ainda em andamento | [6 empty] | LCP-200170 |  | #REF! | [9 empty] | 0 |  |  |  | -0.16338 |  | 0 |  | 0 |  | 0 | 0 | 0.18473 | 0 | 1.2656 | 0 | -1.6137 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | -0.16338 | 0 | -0.16338 | -0.16338 | 0 | #REF! |  | 0 | -0.16338 | 0 | #REF! | [6 empty] | 0 | 0
| 29 | ICP-210016 | [14 empty] | AME |  |  | New |  | ICP | CARLOS SERAFIM | AME FVM TGIS UPGRADE (CAMERAS PRETAS) | Facilities Sustaining | REL | Projeto Local já finalizado. | [6 empty] | LCP-210025 |  | #REF! | [9 empty] | 0 |  |  |  | 98.6825 |  | 0 |  | 0 |  | 0 | 0 | 0.39162 | 0 | 0.66803 | 0 | -0.58955 |  | -0.01593 |  | 41.9634 | 113.3867 | -140.0321 |  | 113.7686 |  | -15.8891 |  | 98.4176 | 98.4176 | -98.4176 | -98.4176 | [11 empty] | 0 | [12 empty] | -98.4176 | 0 | 0.26492 | 98.4176 | 197.1001 | 16.154 | 180.9461 | #REF! |  | 0 | 0.4701 | -98.0846 | #REF! |  |  | 27.995 | 0 |  |  | 0 | 98.4176
|  | ICP-210031 | [14 empty] | AME |  |  | New |  | ICP | CARLOS SERAFIM | AME Creel Room Transfer Gadsden |  | REL | [7 empty] | LCP-210045 |  | #REF! | [13 empty] | 3.9968e-18 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 3.9968e-18 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 3.9968e-18 | 0 | 3.9968e-18 | 3.9968e-18 | 0 | #REF! |  | 0 | 3.9968e-18 | 0 | #REF! | [6 empty] | 0 | 0
|  | ICP-210032 | [14 empty] | AME |  |  | New |  | ICP | CARLOS SERAFIM | AME PNC Pneumatic Core Construction | Quality | REL | $ 243,688.55 Running Balance $ 77,293.76 PO 8240657189 Data de envio atual esperada é 1º de dezembro de 2021. $ 166,300.32 PO 8240634175 Nicholas Bracken confirmed these are not scheduled to ship until 10/12/2021. | [6 empty] | LCP-210078 |  | #REF! | [13 empty] | 243.5941 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0.21372 |  | 243.4748 |  | -0.04625 |  | 0.43536 |  | -0.16568 |  | -0.3179 | -0.3179 | -243.5941 | -243.5941 |  |  |  | 568.4842 | -568.4842 | [6 empty] | 0 | [12 empty] | 0.3179 | 0 | 243.912 | -0.3179 | 487.1882 | 0.57766 | 486.6105 | #REF! |  | 0 | 0 | 243.6423 | #REF! |  |  | 583.5013 | 0 |  |  | -243 | 0.59408
|  | ICP-210036 | [14 empty] | AME |  |  | New |  | ICP | CARLOS SERAFIM | AME - NEW MRT KOKUSAI MACHINE | Quality | REL | DOWNPAYMENT - Matt Wallace está cuidando | [6 empty] | LCP-210086 |  | #REF! | [9 empty] | 0 |  |  |  | 368.415 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0.96441 |  | 1.7437 | 360 | 368.4936 |  | -2.7867 | -2.7867 | -368.415 | [5 empty] | -368.415 | [6 empty] | 0 | [12 empty] | 2.7867 | 0 | 371.2017 | -2.7867 | 736.83 | 2.7081 | 734.1219 | #REF! |  | 0 | 0 | 0.96441 | #REF! |  |  | 842.142 | 0 |  |  | -360 | 8.415
|  | ICP-210037 | [14 empty] | AME |  |  | New |  | ICP | HUELITON MAGNANI | AME - Vulcaweld Creel Room Press |  | REL | [7 empty] | LCP-210007-29 |  | #REF! | [13 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 | 0 | 0 | #REF! |  |  | 14.7 | 0 |  |  | 0 | 0
|  | ICP-210053 | [14 empty] | AME |  |  | New |  | ICP | CARLOS SERAFIM | ICP - AME - (8) PCI Cavities |  | REL | Josh Réckman, comprador GY. Ricardo Alniezi está em contato com ele Conforme alinhado com a região, downpayment retirado, será desenvolvido novo fornecedor (Sinoarp) | [6 empty] | LCP-210196 |  | #REF! | [13 empty] | 0 | [21 empty] | 0 |  |  |  | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 | 0 | 0 | #REF! | [6 empty] | #N/A | #N/A
|  | ICP-XXXXX | [14 empty] | AME |  |  | New |  | ICP | HEDSLEY QUINTAL | AME - Pigment Room (AKRON) | EHS | CRTD | [9 empty] | #REF! | [9 empty] | 0 |  |  |  | 0 | [25 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 | 0 | 0 | #REF! | [6 empty] | -2000 | -2000
|  | ICP-XXXXX3 | [14 empty] | AME |  |  | New |  | ICP | GUSTAVO PARRAS | AME - MIXER#3 BODY REPLACEMENT (AKRON) |  | CRTD | [7 empty] | LCP-210200 |  | #REF! | [13 empty] | 0 | [25 empty] | 0 | [6 empty] | 280 | -280 |  |  |  |  | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 | 0 | 0 | #REF! | [6 empty] | -280 | -280
|  | ICP-210051 | [14 empty] | AME |  |  | New |  | ICP | GUSTAVO PARRAS | AME Upgrade Windup Extr 8x8 SW | Capability | REL | [7 empty] | LCP-210098 | [15 empty] | 0 | [21 empty] | 0.42386 |  | -0.42386 | -0.42386 | 0 | [26 empty] | 0
|  | ICP-210070 | [14 empty] | AME |  |  | New |  | ICP | GUSTAVO PARRAS | AME 2500HP MAIN MOTOR SPARE |  | REL | [23 empty] | 38.1898 | [23 empty] | 38.1898 | 38.1898 | -38.1898 | -38.1898 | [25 empty] | 0 | [13 empty] | 152.759 | 0
| 155 | LCP-200011 |  | 20/0108 | 2019 | 2019-10-24 | 2020-02-24 | 2021-11-29 | 644 | 2021-08-24 | 2022-02-23 | SIM | SIM | SIM | XQ2/22 | CQ2/22 | AME | B1 | VULCANIZAÇÃO | Carryover | 2729616 | PROJETO | CARLOS SERAFIM | PCI IN (6) ROGERS MECHANICAL PRESSES | Capability | TECO | PRONTIDÃO: 13/12 - Embalado e disponivel Booking OK - BL será 27-12 4 PCI em Transito 2 PCI ano que vem DEZEMBRO: Entrega dos PCIs FRETE: Marítimo ICOTERM: FCA (Da pra pagar em transito) Feito a provisão para os serviços referente ao mês de dezembro | OK | 2022-06-30 | 2022-04-30 | Scope Change | 11/06/21 - PCI para 6 prensas mecânicas 47' Taxa de importação |  | ICP-200037 |  | #REF! | ENTREGA DOS PCI'S, A ROGERS SINALIZOU A ENTREGA DE TRÊS PARA 2021, TRABALHANDO PARA ENTREGAR OS SEIS | 4500413489 - PCI'S | NÃO POSSUI RISCOS | 531,816.00 USD | PREVISTO PARA DEZ/21 | MARITIMO | 0 | 500 | 0 | 773 | 774.099 | 12.4 | 786.499 | 117.3704 | 0 | 0 | 0 |  | 0 | 28.1054 | 7 |  | 0 | 0.16829 | 0 |  |  | 1.0245 | 17 | 19.5681 |  | 12.8548 | 9 | 20.1148 |  | 15.5534 | 470.1 | 19.9811 | 19.9811 | 850.1 |  | 372 | 224.4 | 253.7 | [8 empty] | 0 | [12 empty] | 450.1189 | 0 | 97.3893 | 19.9811 | 967.4704 | 1003.9359 | -36.4655 | #REF! |  | 28.1054 | 0.16829 | 33.4474 | #REF! | 1006.05 | 117.3704 | 634.5943 | 0 | 751.9647 | 254.0853 | 364.8 | 485.3
| 204 | LCP-210083 | N/A | 20/0015 | 2021 | 2021-04-15 | 2021-06-10 |  | -944.336 | 2022-12-09 | 2023-06-10 |  |  |  |  | ? | RET |  |  | New | 4060127 | PROJETO | CHARLES BARBAN | RET - FLAT PRECURED EXPANSION | Growth | REL | DEZ: 3 Downpayments OK - Só falta 1 de 90K Cope + Buffer + Trimmer + Cabeça PRENSA - COPE (Nacional) Finalizando parte comercial BUFFER - MANUTEC (Nacional) (Empresa na qual já trabalhou: BANDAC) = 600K contra 1,2M da MATEEUZI, incluindo taxas - Finalizando parte comercial CABEÇA EXTRUSORA - BEARSTORF (Importado) - Revisando orçamento Máquinas serão entregues em 2022. Cabeça da Extrusora fica pronta só em Setembro (informação fabricante), depois será importada e pode ser que até Dez/22 não seja possivel dar o TECO. | 2022-10-30 | 2022-12-31 | 2023-04-30 | [5 empty] | #REF! | [9 empty] | 0 | 5312.05 | 508 | 5820.05 | 2007.9309 | [6 empty] | 0 |  | 0 |  | 0 |  |  |  | 40 | 23.7694 | 43 | 81.0535 | 1088 | 1170.2438 | 27.2 | 32.04 | 765 | 700.8243 | 700.8243 | 3306.2 | 128.2 | 105 | 100 | 245 | 875 | 121 | 571 | 872 | 85 | 100 | 104 |  | 0 | [12 empty] | 64.1757 | 0 | 1307.1066 | 700.8243 | 5314.1309 | 5312.2667 | 1.8643 | #REF! |  | 0 | 0 | 104.8228 | #REF! | 5312.05 | 2007.9309 | 3903.2098 | 3.0809 | 5914.2216 | -602.1716 | 3314 | -7.8
| 223 | LCP-210132 | 2590 |  | 2021 | 2021-06-10 | 2021-08-12 |  | -880.336 | 2023-02-10 | 2023-08-12 | [5 empty] | AME | B2 | CONSTRUÇÃO | New | 4441744 | PROJETO | RICARDO TEIXEIRA | AME - STEEL TRANSFERS BAND NGTTS | Productivity | REL | DEZ: 55K Anel Transferband Peças irão chegar até dia 22/12 | 2022-12-31 | 2022-07-31 | 2023-06-30 | [5 empty] | #REF! | OS MATERIAIS IRÃO CHEGAR ATÉ DEZEMBRO, NÃO FORAM SINALIZADOS RISCOS ATÉ O MOMENTO PREVISÃO DE CHEGADA DAS PRIMEIRAS PEÇAS: ATÉ O FINAL DE NOVEMBRO | NÃO POSSUI RISCOS | EM NEGOCIAÇÃO COM O DEPARTAMENTO DE COMPRAS, REALIZADA A EQUALIZAÇÃO TÉCNICA E AGUARDANDO SAIR O PEDIDO | N/A | N/A | N/A |  |  |  | 0 | 168 |  | 168 | 68.9099 | [10 empty] | 0 | [6 empty] | 2.2258 | 13.6 | 11.5713 | 55.5 | 2.0913 | 81.4 | 53.0214 | 53.0214 | 99.9 | 14.9 | 15 | 15 | 15 | 13 | 27 | [6 empty] | 0 | [12 empty] | 28.3786 | 0 | 15.8884 | 53.0214 | 168.8099 | 168.7971 | 0.01274 | #REF! | SC Será aberta até 15/10 | 0 | 0 | 2.2258 | #REF! | 168 | 69.2018 | 36.7008 | 49.6336 | 155.5361 | 12.4639 | 53 | 46.9
| 138 | LCP-190215 |  | 20/0085 | 2019 | 2019-10-03 | 2019-12-19 |  | -1483.336 | 2021-06-18 | 2021-12-18 | SIM | SIM | SIM | ZQ4/22 | DQ4/22 | AME | B1 | FINAL FINISH | Carryover | 2357324 | PROJETO | GUSTAVO PARRAS | CONTOUR CORRECTION MACHINE | Quality | REL | DEZ: 55K Painel Intereng dia 23 de dezembro 15K Gtel Instlação 10K CF DOWNPAYMENT SET = 180K em ICP FRETE: MARÍTIMO PRONTIDÃO: ABRIL/22 INCOTERM: FOB - Da para pagar em Transito | 2022-10-30 | 2022-10-30 | 2022-10-30 |  |  |  | ICP-210004 |  | #REF! | RISCO DE 70K PARA ESTEIRAS | PO DE AKRON (ESTEIRAS) | NÃO POSSUI RISCOS | 70K (ESTEIRAS) | 2021-12-10 | MARITIMO | 0 | 300 | 0 | 1244 | 1244 | 0 | 1244 | 110.0561 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 25 | 0.98018 | 10 | 8.9378 | 5 |  | 5 |  | 18 | 17.3131 | 5.7 | 5.1972 | 84.4 | 77.6278 | 77.6278 | 926.8 | 21.8 | 70 | 10 | 10 | 750 | 50 | 5 | 5 | 5 |  |  |  | 0 | [12 empty] | 6.7722 | 0 | 32.4283 | 77.6278 | 1036.8561 | 1238.731 | -201.875 | #REF! | 5K transferencia de ICP | 0 | 0.98018 | 8.9378 | #REF! | 1244.5036 | 110.2603 | 91.4539 | 1.4219 | 203.1361 | 1041.3675 | 1087.8 | -161
|  | LCP-210204 | 16119 |  | 2021 | 2021-09-20 | 2021-10-18 |  | -815.336 | 2023-04-18 | 2023-10-18 | [5 empty] | AME | A | BANBURY | New | 4771285 | PROJETO | GUSTAVO PARRAS | AME - NEW MIXER SLURRY - PLITVIC | Quality | REL | Dez: Medição PISO X 50% de chagada de materiais até dia 22 | 2023-03-31 | 2023-05-31 | 2023-08-31 | [5 empty] | #REF! | BUDGET NECESSITA SER APROVADO EM OUTUBRO/21 PARA NÃO CORRER O RISCO DE NÃO CUMPRIR O CAPITAL | BUDGET EM APROVAÇÃO | BUDGET EM APROVAÇÃO | N/A | N/A | N/A |  |  |  |  | 158.535 |  | 158.535 | 71.9141 | [21 empty] | 35.7887 | 34.1682 | 36.1254 | 36.1254 | 65.1 | 13.1 | 25 | 12 | 15 | [8 empty] | 0 | [12 empty] | -1.9572 | 0 | 35.7887 | 36.1254 | 137.0141 | 158.535 | -21.5209 | #REF! |  | 0 | 0 | 0 | #REF! | 158.535 | 74.6785 | 48.334 | 0 | 123.0125 | 35.5225 | 73.535 | -8.435
| 226 | LCP-210135 | N/A |  | 2021 | 2021-06-11 | 2021-07-09 |  | -914.336 | 2023-01-07 | 2023-07-09 | [5 empty] | MC |  |  | New | 4267113 | PROJETO | RICARDO TEIXEIRA | MC - FALSE TRUCK TIRES SYSTEM RETROFIT | Productivity | REL | OUT: 103k Projeto Eletrico/Mec + M.O e implementação NOV: 98k Continuação da implementeção DEZ: 20k Testes JAN: 42,6 Teste e start up | 2022-03-31 | 2022-03-31 | 2023-05-31 | [5 empty] | #REF! | APROXIMADAMENTE 20K DE MATERIAIS NÃO SERÃO GASTOS DEVIDO A NEGOCIAÇÃO COMERCIAL (VALOR MENOR) | NÃO POSSUI RISCOS | APROXIMADAMENTE 20K DE MATERIAIS NÃO SERÃO GASTOS DEVIDO A NEGOCIAÇÃO COMERCIAL (VALOR MENOR) | N/A | N/A | N/A |  |  |  | 0 | 249.5 | 15 | 264.5 | 219.655 | [10 empty] | 0 | [5 empty] | 10 | 4.2147 | 102.9 | 105.1298 | 76.3 | 65.3599 | 34.6 | 44.9506 | 44.9506 | 29 | 5.25 | 5.65 | 5.65 | 10.65 | 1.8 | [7 empty] | 0 | [12 empty] | -10.3506 | 0 | 174.7044 | 44.9506 | 248.655 | 248.6445 | 0.01053 | #REF! | SC Será aberta até 15/10 | 0 | 0 | 4.2147 | #REF! | 249.5 | 219.655 | 13.1881 | 0 | 232.8431 | 16.6569 | 0 | 29
| 228 | LCP-210138 | 2523 |  | 2021 | 2021-06-15 | 2021-07-09 |  | -914.336 | 2023-01-07 | 2023-07-09 | [5 empty] | AME | UTIL | ETE | New | 4305993 | PROJETO | HUELITON MAGNANI | AME - NEW RAINWATER CONTAINMENT SYSTEM | EHS | REL | DEZ: Falta faturar Laudo Prefeitura Projeto e Entrega de Materiais. | 2022-12-31 | 2022-12-31 | 2023-05-31 |  |  |  |  | Utilidades/Facilidades | #REF! | NÃO POSSUI RISCOS (TURN KEY) | AGUARDANDO GERAR O PEDIDO DE COMPRAS | NÃO POSSUI RISCOS (TURN KEY) | N/A | N/A | N/A |  |  |  | 0 | 175.1714 | 34.2727 | 209.444 | 70.332 | [10 empty] | 0 | [9 empty] | 30 | 5.436 | 70 | 64.896 | 64.896 | 104.5889 | 2.7 | 0 | 7.4 | 8.8889 | 10.7 | 10.7 | 10.7 | 10.7 | 10.7 | 10.7 | 10.7 | 10.7 | 0 | [12 empty] | 5.104 | 0 | 5.436 | 64.896 | 174.9209 | 175 | -0.079121 | #REF! |  | 0 | 0 | 0 | #REF! | 175.1714 | 70.332 | 84.8536 | 0.54105 | 155.7266 | 19.4448 | 85 | 19.5889
| 197 | LCP-210038 | 1599 |  | 2021 | 2021-02-10 | 2021-03-31 |  | -1015.336 | 2022-09-29 | 2023-03-31 | [5 empty] | AME | B1 | VULCANIZAÇÃO | New | 3781472 | PROJETO | HUELITON MAGNANI | UPPER CONVEYORS UPGRADE – CURING B1 | EHS | REL | DEZ: Instalações Elet. E entrega de materiais | 2022-03-31 | 2022-03-31 | 2023-01-31 | Overrun | Aumentos no valor de cabos e componentes eletronicos | 9.8% |  |  | #REF! | RISCOS DOS MATERIAIS NÃO SEREM ENTREGUES - 50K (US$) | AGUARDANDO GERAR O PEDIDO DE COMPRAS | POSSUI RISCOS CASO OS MATERIAIS NÃO FOREM ENTREGUES EM 2021, APROXIMADAMENTE 50K (US$) | N/A | N/A | N/A |  |  |  | 0 | 197.8596 | 15 | 212.8596 | 128.9177 |  |  | 0 |  | 0 | 0 | 0 |  | 0 | 3.2243 | 3 | 3.2831 | 3 | 34.6385 | 3 | 13.4981 | 2.4 | 10.0247 | 25.7 | 1.256 | 45.3 | 26.2203 | 64.9 | 36.7728 | 36.7728 | 51.3 | 2.6 | 2 | 2.05 | 7.05 | 11.05 | 10.05 | 7 | 7 | 2.5 |  |  |  | 0 | [12 empty] | 28.1273 | 0 | 92.1449 | 36.7728 | 180.2177 | 180.4246 | -0.20694 | #REF! | SC Será aberta até 15/10 | 0 | 6.5073 | 58.1612 | #REF! | 197.8596 | 130.7278 | 42.0706 | 0 | 172.7984 | 25.0612 | 0 | 51.3
| 232 | LCP-210147 | Informar |  | 2021 | 2021-06-21 | 2021-07-06 |  | -917.336 | 2023-01-04 | 2023-07-06 | [5 empty] | AME | B1 | CONST. TRADIC. | New | 4320565 | PROJETO | CARLOS SERAFIM | AME - NR12 - NT CONSUMMER BUILDING ENHANCEMENT | EHS | REL | Chega até dia 23 Todos os NTs (menos NT 22 e 20) - Total de 22 NTs Em processo de abertura de SCs Possivel instalação para este ano tambe'm Pode existir um risco devido a entrega de materiais pela Intereng | 2022-12-31 | 2022-12-31 | 2023-04-30 | [5 empty] | #REF! | NÃO POSSUI RISCOS | NÃO POSSUI PEDIDOS COM RISCOS | NÃO POSSUI PEDIDOS COM RISCOS OBS.: AGUARDANDO CONTRATO COM A LGS | N/A | N/A | N/A |  |  |  | 0 | 879.7 | 80 | 959.7 | 157.8172 | [10 empty] | 0 |  |  |  |  | 27.3194 | 29.7596 | 70.2491 | 20.1 | 12.9869 | 72.5 | 33.3221 | 79.5 | 13.9399 | 13.9399 | 705.18 | 21.9 | 83.6 | 50 | 50 | 71.465 | 86.465 | 50.125 | 56.625 | 67.5 | 67.5 | 50 | 50 | 0 | [12 empty] | 65.5601 | 0 | 143.8774 | 13.9399 | 862.9972 | 874.0553 | -11.0581 | #REF! |  | 0 | 0 | 97.5684 | #REF! | 879.7 | 159.7406 | 168.1002 | 57.954 | 385.7948 | 493.9052 | 639.7 | 65.48
| 222 | LCP-210131 | 11944 |  | 2021 | 2021-06-09 | 2021-07-20 |  | -903.336 | 2023-01-18 | 2023-07-20 | [5 empty] | AME | FACIL | EHS | New | 4280564 | PROJETO | HUELITON MAGNANI | AME - WOMEN'S RESTROOM | EHS | REL | DEZ:Mat já chegou, falta faturar SERV Banheiros: TBM: Final Finish: Div. A | 2022-12-31 | 2022-12-31 | 2023-05-31 |  |  |  |  | Utilidades/Facilidades | #REF! | PROJETO TURN KEY, HÁ RISCOS PARA O INÍCIO DA EXECUÇÃO POIS COMPRAS AINDA NÃO FECHOU O PEDIDO | AGUARDANDO GERAR O PEDIDO DE COMPRAS | PROJETO TURN KEY, HÁ RISCOS PARA O INÍCIO DA EXECUÇÃO POIS COMPRAS AINDA NÃO FECHOU O PEDIDO | N/A | N/A | N/A |  |  |  | 0 | 255.455 | 12.5 | 267.955 | 118.9952 | [10 empty] | 0 | [11 empty] | 100 | 118.9952 | 118.9952 | 136 | 1.9 | 6.1 | 15 | 10 | 18 | 16.4286 | 16.4286 | 16.4286 | 16.4286 | 6.4286 | 6.4286 | 6.4286 | 0 | [12 empty] | -18.9952 | 0 | 0 | 118.9952 | 254.9952 | 255 | -0.00478 | #REF! |  | 0 | 0 | 0 | #REF! | 255.455 | 120.8752 | 125.6904 | 0 | 246.5656 | 8.8894 | 105 | 31
|  | LCP-210189 | N/A |  | 2021 | 2021-08-27 | 2021-09-22 |  | -842.336 | 2023-03-23 | 2023-09-22 | [5 empty] | BRZ |  |  | New | 4723158 | PROJETO | JOAO ZAINA | CTVM - VBOX EQUIPMENT | Facilities Sustaining | REL | Projeto aprovado em 22/09/2021. Em processo de abertura de SC | 2023-02-28 | 2021-11-30 | 2023-07-31 | [5 empty] | #REF! | [10 empty] | 32.864 | 2.144 | 35.008 | 30.2473 | [21 empty] | 30.0973 | 2 | 0.15 | 0.15 | 1.9 | 1.9 | [11 empty] | 0 | [12 empty] | 1.85 | 0 | 30.0973 | 0.15 | 32.1473 | 32 | 0.14731 | #REF! | Impostos de importação | 0 | 0 | 0 | #REF! | 32.864 | 30.2473 | 0 | 0 | 30.2473 | 2.6167 | 0 | 1.9
| 194 | LCP-210020 | 567 |  | 2021 | 2021-04-07 | 2021-05-04 |  | -980.336 | 2022-11-02 | 2023-05-04 | [5 empty] | AME | UTIL | CASA FORÇA | New | 3918460 | PROJETO | CARLOS SERAFIM | NEW AIR COMPRESSOR - 100 PSI | Facilities Sustaining | REL | DEZ: 200 Pagamento em Transito do compressor (China) AGUARDANDO BOOKING Instalação de Potencia na Parada de Fábrica para alimentação do compressor + Paineis + cabos + Painel da WEG Perdemos 40K dos Filtros Quimicos Compressor: Entrega apenas em Janeiro | 2022-09-30 | 2022-04-30 | 2023-03-31 |  |  |  |  | Utilidades/Facilidades | #REF! | ENTREGA DO COMPRESSOR E PAINEL, ENTREGA PREVISTA PARA DEZEMBRO | 8240641477 - COMPRESSOR 122447490 - PAINEL (FALTA GERAR PO) | ESTÁ EM COTAÇÃO | N/A | N/A | N/A |  |  |  | 0 | 699.8 | 64.5 | 764.3 | 213.6049 |  |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 3 | 1.3944 | 5 | 4.4272 | 10.5 | 2.0828 | 28.5 | 75.8294 | 289.7 | 129.871 | 129.871 | 484.6 | 31.8 | 258 | 75 | 70 | 20 | 29.8 | [6 empty] | 0 | [12 empty] | 159.829 | 0 | 83.7338 | 129.871 | 698.2049 | 698.2044 | 0.00047 | #REF! |  | 0 | 0 | 5.8216 | #REF! | 699.8 | 166.2263 | 355.8997 | 1.791 | 523.9171 | 175.8829 | 369.8 | 114.8
| 229 | LCP-210149 | 12955 |  | 2021 | 2021-06-23 | 2021-07-15 |  | -908.336 | 2023-01-13 | 2023-07-15 | [5 empty] | AME | B2 | VULCANIZAÇÃO | New | 4340683 | PROJETO | RICARDO TEIXEIRA | AME - CURING VACUUM SYSTEM UPGRADE | Capability | REL | 2021: Compra de materiais, alguns importados. 2022: Intalação 58 Maquinas MRT (precisa de 8 horas de máquina parada/máquina) Previsão de uma máquina por dia com suporte da manutenção | 2022-12-31 | 2022-12-31 | 2023-05-31 | [5 empty] | #REF! | O MATERIAL IRÁ CHEGAR EM OUTUBRO, NÃO FORAM SINALIZADOS RISCOS | NÃO POSSUI RISCOS | OK | N/A | N/A | N/A |  |  |  | 0 | 105.04 |  | 105.04 | 94.7637 | [10 empty] | 0 |  |  |  |  | 2.1045 | 17.9607 | 15.0234 | 17.9 | 42.8844 | 4.5 | 25.519 | 1 | 9.2326 | 9.2326 | 10 | 1.6 | 1.4 |  | 2 | 2 | 2 | 1 | [5 empty] | 0 | [12 empty] | -8.2326 | 0 | 85.5311 | 9.2326 | 104.7637 | 105.0122 | -0.24848 | #REF! |  | 0 | 0 | 17.1278 | #REF! | 105.04 | 94.7637 | 3.9345 | 0 | 98.6982 | 6.3418 | 40 | -30
|  | LCP-210219 | N/A |  | 2021 | 2021-10-11 | 2021-11-22 |  | -781.336 | 2023-05-23 | 2023-11-22 | [5 empty] | AME | A | CALANDRA | New | 4879190 | PROJETO | ROGÉRIO SIA | AME - RETROFIT SYSTEM OF THE CREEL ROOM | Facilities Sustaining | REL | Aprovado em 22/11 Previsão de entrega dos materiais: 23/12 | 2023-05-30 | 2023-09-30 | 2023-09-30 | [5 empty] | #REF! | [10 empty] | 56.2419 |  | 56.2419 | 44.1598 | [23 empty] | 44.1598 | 44.1598 | 12.0473 | 1.3 |  |  | 10.7473 | [21 empty] | -44.1598 | 0 | 0 | 44.1598 | [9 empty] | 56.2419 | 44.1598 | 3.3438 | 1.4172 | 48.9207 | 7.3212
| 193 | LCP-210018 | 879 |  | 2021 | 2020-12-29 | 2021-04-09 |  | -1006.336 | 2022-10-08 | 2023-04-09 | [5 empty] | AME | A | ENTUBADORA | New | 3722351 | PROJETO | GUSTAVO PARRAS | REPLACEMENT OF BOTTOM COOLING TANK D#4 | Facilities Sustaining | REL | Dez: 283K Chegada dos Tanques prevista para o dia 23 de dezembro 2022: Instalação | 2022-08-30 | 2022-05-31 | 2023-02-28 | Overrun | 30/08/21 Aumento do preço do ferro | 9.9% |  |  | #REF! | (ADZ ATÉ O MOMENTO NÃO ACENOU RISCO) | AG. CONTRATO DE COMPRAS | N/A | N/A | N/A | N/A |  |  |  | 0 | 465116.58 | 13.2075 | 465129.7876 | 312.5539 |  |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | [5 empty] | 16 |  | 21 | 28.2652 | 4.7 |  | 283 | 284.2887 | 284.2887 | 150.618 | 3.7 | 5 | 5 | 65.1 | 71.818 | [7 empty] | 0 | [12 empty] | -1.2887 | 0 | 28.2652 | 284.2887 | 463.1719 | 423.1832 | 39.9887 | #REF! |  | 0 | 0 | 0 | #REF! | 465.1166 | 313.8428 | 39.4828 | 4.0094 | 357.3349 | 107.7816 | 223.218 | -72.6
| 216 | LCP-210110 | N/A |  | 2021 | 2021-05-18 | 2021-05-28 |  | -956.336 | 2021-12-31 | 2022-03-31 |  | SIM |  | AQ4/21 | AQ1/22 | MC |  |  | New | 4175016 | PROJETO | RICARDO TEIXEIRA | MC - 2021 ANNUAL MISCELLANEOUS <50K ALL PLANTS | SAG | REL | Nov: Falta Balanceadora em Gravatai e Material up Micropoise São Bernardo (Intereng) Epiacaba + Material e M.O Upgrade Balanceadores São Bernardo Dez: Material e M.O Upgrade Balanceadores São Bernardo + Balanceadora de Epiacaba 5,6K de Epiacaba em Risco | 2021-12-31 | 2021-12-31 | 2022-01-31 | Overrun | 10/12/2021 avaliação do sistema por intranet remota teve divergência de material necessário par das estabilidade e qualidade entre a comunicação do PLC com as remotas e o processamento e comando da Micro Poise | 9.33% |  |  | #REF! | OS MATERIAIS IRÃO CHEGAR ATÉ DEZEMBRO, ESTÁ SENDO CADASTRADO OS MATERIAIS NA PLANTA PARA SEREM COMPRADOS PREVISÃO DE EXECUÇÃO UPG SBC - 2021 | NÃO POSSUI RISCOS (SC DE COMPRAS DE MATERIAIS E M.O PARA SBC) | NÃO POSSUI RISCOS (SC DE COMPRAS DE MATERIAIS E M.O PARA SBC) | N/A | N/A | N/A |  |  |  | 67 | 75 |  | 75 | 67.1721 | [8 empty] | 0 |  | 0 |  |  |  | 10 |  | 16 | 10.6834 | 23.6 | 11.5081 | 32.1 | 22.9006 | 18.1 | 22.0799 | 22.0799 | 1 | 1 | [11 empty] | 0 | [12 empty] | -3.9799 | 0 | 45.0922 | 22.0799 | 68.1721 | 62.9915 | 5.1806 | #REF! | SC Será aberta até 15/10 | 0 | 0 | 10.6834 | #REF! | 82 | 67.1721 | 12.6399 | 0 | 79.812 | 2.188 | 0 | 1
| 200 | LCP-210052 | Informar |  | 2021 | 2021-03-01 | 2021-03-31 |  | -1015.336 | 2022-09-29 | 2023-03-31 | [5 empty] | AME | UTIL | SUBESTAÇÃO | New | 3815429 | PROJETO | HUELITON MAGNANI | FIRE PROTECTION SYSTEM MAIN SUBSTATION | EHS | REL | DEZ: Instalacão | 2022-02-28 | 2022-02-28 | 2023-01-31 |  |  |  |  | Utilidades/Facilidades | #REF! | MATERIAL SENDO COMPRADO, AGUARDANDO GERAR O PEDIDO DE COMPRAS | AGUARDANDO GERAR O PEDIDO DE COMPRAS | NÃO POSSUI RISCOS | N/A | N/A | N/A |  |  |  | 0 | 75 | 23.8 | 98.8 | 67.0953 |  |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | [9 empty] | 50 | 42.5852 | 32 | 24.51 | 24.51 | 7.5 | 0.4 |  | 3 | 3 | 1.1 | [7 empty] | 0 | [12 empty] | 7.49 | 0 | 42.5852 | 24.51 | 74.5953 | 75 | -0.40474 | #REF! | SC de 7,6K irá fechar em torno de 25K | 0 | 0 | 0 | #REF! | 75 | 67.0953 | 5.0205 | 0 | 72.1158 | 2.8842 | 0 | 7.5
| 175 | LCP-200130 |  | 21/0006 | 2020 | 2020-08-01 | 2020-09-02 |  | -1227.336 | 2022-03-03 | 2022-09-02 |  | SIM |  | ZQ4/22 | DQ4/22 | AME | B2 | VULCANIZAÇÃO | Carryover | 3114541 | PROJETO | HUELITON MAGNANI | AME - UPGRADE PLC PRESSES MRT (12 PRESSES) | Facilities Sustaining | REL | 12 PRENSAS: Projeção para execução Maior que 24 meses (previsto finalizar em junho 22) A instalação iniciou dia 05/04 (3 meses pro prensa) PRENSAS 1) PQ21/22 - OK 2) PQ15/16 - OK 3) PR17/18 - Em andamento 4) PR01/02 - Outubro Primeira Parte: Pneumática / Hidráulica e Elétrica: 45 dias Teste de Qualidade: 15 dias Terceira Parte: Aguarda retorno de Akron: De uma semana a 1 mês ESTIMADO 3 PRENSAS PARA 2021 E AS DEMAIS PARA 2022 Entrega dos painéis Intereng previsto para o dia 23 de dezembro | 2022-10-30 | 2022-12-31 | 2022-07-31 | Overrun |  | 9.77% |  |  | #REF! | NÃO POSSUI RISCOS | NÃO POSSUI RISCOS | RISCO CASO AS MÁQUINAS NÃO PAREM, CONFORME PLANEJADO VALOR TOTAL | N/A | N/A | N/A |  | 0 | 561.9153 | 416.0081 | 1074.8106 | 12 | 1086.8106 | 289.7048 | 10 | 19.0081 | 21 | 6.678 | 0 | 5.802 | 0 | 12.0371 | 3 | 33.8246 | 5 | 10.1786 | 4.9 | 16.2102 | 4.9 | 24.7475 | 2 | 30.6402 | 9 | 34.1471 | 20.9 | 28.9229 | 33.4 | 67.5085 | 67.5085 | 259.9 | 0.4 | 19 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24.5 | 0 | [12 empty] | -34.1085 | 0 | 222.1963 | 67.5085 | 549.6048 | 549.6735 | -0.06868 | #REF! |  | 31.4881 | 56.0403 | 71.598 | #REF! | 1074.8106 | 852.0063 | 209.0156 | 0 | 1061.0219 | 13.7887 | 314 | -54.1
| 211 | LCP-210101 | N/A |  | 2021 | 2021-05-13 | 2021-05-28 |  | -956.336 | 2022-11-26 | 2023-05-28 | [5 empty] | RET |  |  | New | 4162039 | PROJETO | CHARLES BARBAN | RET - BATHROOM ADEQUANCY NR24 | EHS | REL | Previsão de Término Fev/22 | 2022-02-28 | 2022-01-30 | 2023-03-31 | [5 empty] | #REF! | [9 empty] | 0 | 70 |  | 70 | 57.4663 | [8 empty] | 0 |  | 0 | [5 empty] | 2 |  | 2 | 1.5726 | 52.5 | 29.297 | 22.1 | 26.5967 | 26.5967 | 5.3 | 5.3 | [11 empty] | 0 | [12 empty] | -4.4967 | 0 | 30.8696 | 26.5967 | 62.7662 | 70.0726 | -7.3064 | #REF! |  | 0 | 0 | 0 | #REF! | 70 | 57.4663 | 4.963 | 0.00705 | 62.4363 | 7.5637 | 0 | 5.3
| 224 | LCP-210133 | 3605 |  | 2021 | 2021-06-10 | 2021-07-09 |  | -914.336 | 2023-01-07 | 2023-07-09 | [5 empty] | AME | A | ENTUBADORA | New | 4280835 | PROJETO | DIEGO CASTANHARO | AME - MILLS ADEQUACY PROJECT FAM | EHS | REL | Aguardando entrega de materiais - Paineis dos moinhos Dez: Risco de 41K de Instalação - Possivel Carryover | 2022-02-28 | 2022-02-28 | 2023-05-31 | [5 empty] | #REF! | NÃO POSSUI RISCOS | NÃO POSSUI RISCOS | NÃO POSSUI RISCOS | N/A | N/A | N/A |  |  |  | 0 | 73.2085 | 22.974 | 96.1825 | 2.856 | [10 empty] | 0 | [9 empty] | 36.6 |  | 41.2 | 2.856 | 2.856 | 70.3 |  | 12.1 | 26.2 | 32 | [8 empty] | 0 | [12 empty] | 38.344 | 0 | 0 | 2.856 | 73.156 | 73.2 | -0.04399 | #REF! | SC Será aberta até 15/10 - M.O - Risco de não executar a MO este ano (23K) | 0 | 0 | 0 | #REF! | 73.2085 | 2.856 | 47.9916 | 20.9162 | 71.7638 | 1.4447 | 0 | 70.3
| 97 | LCP-190020 |  | 19/0042 | 2019 | 2019-03-27 | 2019-03-27 |  | -1748.336 | 2020-09-24 | 2021-03-26 | SIM | SIM | SIM | ZQ4/22 | DQ4/22 | AME | A | CALANDRA | Carryover | 992289 | PROJETO | GUSTAVO PARRAS | AME - ROBOT FOR BEAD WINDER | Productivity | REL | DEZ: 45K Carrosel - Chegou 7K Intereng - 23/12 PRIMEIRO ROBO LIBERADO PARA CAPITALIZAÇÃO EM ABRIL/21 PARA 2021: ROBO NÃO IRÁ CHEGAR, SERÁ MITIGADO RISCO COM CHEGADA DO CARROSEL. PEDIDO 8240657178 2022: CHEGADO DO ROBO E IMPLEMENTAÇÃO Valor de 6k de novembro transferido para dezembro/21 | 2022-10-30 | 2022-10-30 | 2022-10-30 | Scope Change |  |  |  |  | #REF! | RISCO DE 50K ROBÔ FANUC | 8240607168 (ROBÔ FANUC) | NÃO POSSUI RISCOS | 50K (ROBÔ FANUC) | Dez/21 (chegada prevista) | N/A (POR CONTA DA EMPRESA) | 49.0856 | 354.5802 | 44.2791 | 138.627 | 371.996 | 81.05 | 453.046 | 118.3965 | 5 | 3.627 | 5 | 1.8801 | 3 | 3.6562 | 3 | 6.5335 | 4 | 17.708 | 6 | 8.8656 | 6 | 7.6409 |  | 0.58243 |  | 10.9958 | 4.6 | 2.4468 | 6 | 4.4879 | 52.5 | 49.9722 | 49.9722 | 78.1 | 43.1 | 10 | 10 | 15 | [8 empty] | 0 | [12 empty] | 2.5278 | 0 | 68.4243 | 49.9722 | 196.4965 | 220.8364 | -24.3399 | #REF! |  | 9.1634 | 33.1071 | 19.2191 | #REF! | 371.996 | 211.7508 | 107.1124 | 0.00027 | 318.8635 | 53.1325 | 100 | -21.9
| 227 | LCP-210137 | 16888 |  | 2021 | 2021-06-14 | 2021-07-09 |  | -914.336 | 2023-01-07 | 2023-07-09 | [5 empty] | AME | FACIL | EHS | New | 4321792 | PROJETO | HUELITON MAGNANI | AME -SIDEWALK BUILDING IN FRONT OF PLANT | EHS | REL | Dez: Pintura guia, faixa de pedestre e rampa de acessibilidade | 2022-12-31 | 2021-12-31 | 2023-05-31 | Overrun | Negociação comercial ficar acima do valor estimado para abertura do Budget. | 9.9% |  | Utilidades/Facilidades | #REF! | NÃO POSSUI RISCOS (TURN KEY) | NÃO POSSUI RISCOS | NÃO POSSUI RISCOS (TURN KEY) | N/A | N/A | N/A |  |  |  | 0 | 124.1669 |  | 124.1669 | 118.1833 | [10 empty] | 0 | [5 empty] | 40 | 57.5603 | 12.5 | 29.6371 | 48.9 | 20.2761 | 16 | 10.7098 | 10.7098 | 0.3 | 0.3 | [11 empty] | 0 | [12 empty] | 5.2902 | 0 | 107.4735 | 10.7098 | 118.4833 | 136.0974 | -17.6141 | #REF! |  | 0 | 0 | 57.5603 | #REF! | 124.1669 | 118.1833 | 0 | 0 | 118.1833 | 5.9836 | 23 | -22.7
| 235 | LCP-210148 | 16273 |  | 2021 | 2021-06-21 | 2021-07-06 |  | -917.336 | 2023-01-04 | 2023-07-06 | [5 empty] | AME | A | CALANDRA | New | 4320452 | PROJETO | CARLOS SERAFIM | AME - NR12 - TEXTIL CALENDER 3R | EHS | REL | Em processo de compras de materiais Proteção mecânica e M.O - Ok Materiais irão chegar até o dia 23/12 | 2022-12-31 | 2022-07-31 | 2023-04-30 | [5 empty] | #REF! | NÃO POSSUI RISCOS | NÃO POSSUI PEDIDOS COM RISCOS | EM PROCESSO DE COTAÇÃO | N/A | N/A | N/A |  |  |  | 0 | 350.1 |  | 350.1 | 107.5066 | [10 empty] | 0 |  |  |  |  | 7.3094 | 6.7 | 5.1611 | 21.0332 | 11.8458 | 54.2 | 52.469 | 21.7 | 30.7214 | 30.7214 | 241 | 11 | 20 | 40 | 50 | 50 | 40 | 10 | 10 | 10 |  |  |  | 0 | [12 empty] | -9.0214 | 0 | 76.7852 | 30.7214 | 348.5066 | 348.5162 | -0.00963 | #REF! |  | 0 | 0 | 12.4704 | #REF! | 350.1 | 107.7654 | 33.7802 | 13.188 | 154.7335 | 195.3665 | 250 | -9
|  | LCP-210190 | Informar |  | 2021 | 2021-09-06 | 2021-10-14 |  | -819.336 | 2023-04-14 | 2023-10-14 | [5 empty] | AME | UTIL | CASA FORÇA | New | 4723426 | PROJETO | RICARDO TEIXEIRA | AME - (2) NEW AIR DRYER POWER HOUSE | Facilities Sustaining | REL | Aguardando aprovação do downpayment | 2023-03-31 | 2023-08-30 | 2023-08-31 |  |  |  |  | Utilidades/Facilidades | #REF! | APROXIMADAMENTE 30K DE MATERIAIS NÃO IRÃO CHEGAR, DEVIDO A APROVAÇÃO DE BUDGET E PRAZOS DE ENTREGA DOS SECADORES DE AR | NÃO POSSUI POR AINDA ESTAR APROVANDO O BUDGET | APROXIMADAMENTE 10K DEVIDO A NÃO APROVAÇÃO DO BUDGET EM TEMPO HÁBIL | N/A | N/A | N/A |  |  |  |  | 289.7324 |  | 289.7324 | 54.271 | [21 empty] | 1.4384 | 28.6 | 52.8326 | 52.8326 | 234.2 | 1.2 | 1 | 5 | 174 | 20 | 15 | 18 | [5 empty] | 0 | [12 empty] | -24.2326 | 0 | 1.4384 | 52.8326 | 288.471 | 289 | -0.52902 | #REF! | Projeto aprovado dia 14/10 Será aberta SC até 15/10 | 0 | 0 | 0 | #REF! | 289.7324 | 54.4319 | 161.1539 | 54.564 | 270.1497 | 19.5827 | 244 | -9.8
| 168 | LCP-200119 |  | 21/0003 | 2020 | 2020-07-01 | 2020-09-02 |  | -1227.336 | 2022-03-03 | 2022-09-02 |  | SIM |  | BQ1/22 |  | AME | A | ENTUBADORA | Carryover | 3112704 | PROJETO | GUSTAVO PARRAS | REPL MAIN GEARBOX 6” & 10” MRT EXTRUDER | Facilities Sustaining | REL | Ainda tem um PO em aberto 8240776240 SEW - Pericicias e Laudos Tecnicos | 2022-01-31 | 2021-10-31 | 2022-07-31 | Scope Change | 18/03/21 Replacement main gearbox 6' e 10' MRT. Extruder. |  |  |  | #REF! | NÃO POSSUI RISCOS | NÃO POSSUI RISCOS | NÃO POSSUI RISCOS | N/A | N/A | N/A |  | 0 | 240.9694 | 45.1788 | 309.296 | 40 | 349.296 | 46.5045 | 0 | 5.5935 | 0 | 1.4873 | 0 | 1.912 | 6 | 11.0647 | 9 | 7.5035 | 5 | 6.9891 | 5 |  | 5 |  | 5 | 3.8634 | 2.4 | 1.0342 | 1.3 | 4.6825 |  | 2.3742 | 2.3742 | 0 | [12 empty] | 0 | [12 empty] | -2.3742 | 0 | 44.1303 | 2.3742 | 46.5045 | 40.7478 | 5.7567 | #REF! |  | 8.9928 | 25.5573 | 3.8634 | #REF! | 309.296 | 287.541 | 0.82892 | 0 | 288.3699 | 20.9261 | 0 | 0
| 220 | LCP-210121 | 2270 |  | 2021 | 2021-05-31 | 2021-06-22 |  | -932.336 | 2022-12-21 | 2023-06-22 | [5 empty] | AME | B1 | CONST. TRADIC. | New | 4249298 | PROJETO | CARLOS SERAFIM | AME – WULO – CONSUMMER BUILDING - STEP 2 - NT22 | EHS | REL | 2021: Projetos Eletrico 2022: 80K de materiais/Instalação (falar pra Região que o prazo de entrega não atende este ano, mais estamos trabalhando para antecipar) | 2022-11-30 | 2022-04-30 | 2023-04-30 | [5 empty] | #REF! | NÃO POSSUI RISCOS | NÃO POSSUI PEDIDOS COM RISCOS | NÃO POSSUI RISCOS, SERVIÇO SERÁ FEITO PELA ADZ | N/A | N/A | N/A |  |  |  | 0 | 103.2 | 10 | 113.2 | 55.5964 | [8 empty] | 0 |  | 0 |  |  | 1.7216 | 1.5 | 13.0196 | 4.3 | 5.3676 | 2.2 | 5.8556 |  | 17.4647 | 7.9 | 12.1674 | 12.1674 | 49.3065 | 1.3065 | 8.2 | 19.8 | 20 | [8 empty] | 0 | [12 empty] | -4.2674 | 0 | 43.429 | 12.1674 | 104.903 | 105.7644 | -0.86143 | #REF! |  | 0 | 0 | 20.1088 | #REF! | 103.2 | 55.6287 | 22.261 | 0 | 77.8898 | 25.3102 | 80 | -30.6935
| 161 | LCP-200053 |  | 21/0002 | 2020 | 2020-02-07 | 2020-09-17 |  | -1212.336 | 2022-03-18 | 2022-09-17 |  | SIM |  | BQ1/22 |  | AME | A | BANBURY | Carryover | 2780598 | PROJETO | GUSTAVO PARRAS | MIXER#7 BODY REPLACEMENT | Facilities Sustaining | REL | 2022: 4 talhas no Mixer 5 | 2022-02-28 | 2021-10-31 | 2022-07-31 | Scope Change | Aprovado em 06/10/2021 Aquisição de 4 talhas. Suplemento de U$ 306,570K (capital) e U$17K (despesa) |  | ICP-210002 |  | #REF! | NÃO POSSUI RISCOS | NÃO POSSUI RISCOS | NÃO POSSUI RISCOS | N/A | N/A | N/A | 0 | 0 | 0 | 1340 | 1647.355 | 42 | 1689.355 | 1325.7427 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 900 | 904.9998 | 20 | 33.7279 | 80.22 | 101.0314 | 113.2 | 126.4778 | 36.7 | 98.7425 |  | 60.7633 | 60.7633 | 149.2 |  |  |  |  | 119.2 | 30 | [6 empty] | 0 | [12 empty] | -60.7633 | 0 | 1264.9794 | 60.7633 | 1474.9427 | 1488.9369 | -13.9942 | #REF! |  | 0 | 0 | 1039.7591 | #REF! | 1647.355 | 1325.7506 | 187.9283 | 0 | 1513.679 | 133.676 | 286 | -136.8
| 30 | LCP-160092 |  |  | 2016 | 2016-04-13 | 2016-05-12 | 2019-07-25 | 1169 | 2017-11-10 | 2018-05-12 | [5 empty] | AME | STAFF |  | Carryover |  | PROJETO | HENRIQUE CARDOSO | STEAM COGEN | Energy Conservation | CLSD | OK, FINALIZADO | OK | OK | OK | [5 empty] | #REF! | [6 empty] | 40.57 |  | 0 |  | 13168.052 | 28.95 | 13197.002 | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 | 0 | 0 | #REF! | 13168.052 | 13053.7617 | 0 | 0 | 13053.7617 | 114.2903 |  | 0
| 31 | LCP-160138 |  |  | 2016 | 2016-07-01 | 2016-07-01 | 2019-09-19 | 1175 | 2017-12-30 | 2018-07-01 | [5 empty] | AME | B1 |  | Carryover |  | PROJETO | REGINALDO MARESCHI | PCI IN (8) ROGERS MECHANICAL PRESSES | Capability | CLSD | OK, FINALIZADO | OK | OK | OK | [5 empty] | #REF! | [6 empty] | 122.0355 |  | 0 |  | 1296.2 | 96 | 1392.2 | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 | 0 | 0 | #REF! | 1296.2 | 1267.7092 | 0 | 0 | 1267.7092 | 28.4908 |  | 0
| 32 | LCP-160208 |  |  | 2016 | 2016-11-29 | 2016-11-29 | 2019-06-18 | 931 | 2018-05-30 | 2018-11-29 | [5 empty] | AME | B2 |  | Carryover |  | PROJETO | HUELITON MAGNANI | FLEXCORD SENSOR DETECTOR UPGRADE | Productivity | CLSD | OK, FINALIZADO | OK | OK | OK | [5 empty] | #REF! | [6 empty] | -6.8326 |  | 0 |  | 63.1 | 0 | 63.1 | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 | 0 | 0 | #REF! | 63.1 | 0 | 0 | 0 | 0 | 63.1 |  | 0
| 33 | LCP-170013 |  | 18/0138 | 2017 | 2017-02-28 | 2017-02-08 | 2019-03-14 | 764 | 2018-08-09 | 2019-02-08 | [5 empty] | AME | STAFF |  | Carryover |  | PROJETO | RICARDO TEIXEIRA | ADEQUATION OF NR#12 COMPLIANCE PHASE III | EHS | CLSD | OK, FINALIZADO | OK | OK | OK | [5 empty] | #REF! | [6 empty] | 2.2 |  | 0 |  | 350 | 5 | 355 | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 | 0 | 0 | #REF! | 350 | 347.0724 | 0 | 0 | 347.0724 | 2.9276 |  | 0
| 34 | LCP-170039 |  |  | 2017 | 2017-07-20 | 2017-07-20 | 2019-07-25 | 735 | 2019-01-18 | 2019-07-20 | [5 empty] | AME | B2 |  | Carryover |  | PROJETO | HENRIQUE CARDOSO | GREEN TIRE DEBOOKER FOR MRT PRESSES | EHS | CLSD | OK, FINALIZADO | OK | OK | OK | [5 empty] | #REF! | [6 empty] | 102.8213 |  | 0 |  | 770.1 | 70 | 840.1 | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 | 0 | 0 | #REF! | 770.1 | 744.723 | 0 | 0.00018 | 744.7232 | 25.3768 |  | 0
| 35 | LCP-170065 |  |  | 2016 | 2016-12-01 | 2017-03-24 | 2019-02-26 | 704 | 2018-09-22 | 2019-03-24 | [5 empty] | AME | B2 |  | Carryover |  | PROJETO | HUELITON MAGNANI | AME - ARTICULATED DRUM TIRE 20,5" GREADER LRF AND OTR LAMINATOR | Productivity | CLSD | OK, FINALIZADO | OK | OK | OK | [5 empty] | #REF! | [6 empty] | 1.046 |  | 0 |  | 352 | 0 | 352 | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 | 0 | 0 | #REF! | 352 | 347.3165 | 0 | 0 | 347.3165 | 4.6835 |  | 0
| 36 | LCP-170069 |  |  | 2017 | 2017-04-19 | 2017-04-19 | 2019-09-11 | 875 | 2018-10-18 | 2019-04-19 | [5 empty] | AME | A |  | Carryover |  | PROJETO | FABIO MORAES | REPLACE AND UPGRADE OF ROLLS IN WIRE CALANDER | Facilities Sustaining | CLSD | OK, FINALIZADO | OK | OK | OK | [5 empty] | #REF! | [6 empty] | 147.1062 |  | 0 |  | 1338.9 | 85 | 1423.9 | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 | 0 | 0 | #REF! | 1338.9 | 1335.9524 | 0 | 0 | 1335.9524 | 2.9476 |  | 0
| 37 | LCP-170077 |  |  | 2016 | 2016-12-01 | 2017-03-24 | 2019-03-23 | 729 | 2018-09-22 | 2019-03-24 | [5 empty] | AME | B2 |  | Carryover |  | PROJETO | FABIO MORAES | AMERICANA WIND UP LET OFF PHASE III | EHS | CLSD | OK, FINALIZADO | OK | OK | OK | [5 empty] | #REF! | [6 empty] | 4.64 |  | 0 |  | 513 | 53 | 566 | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 | 0 | 0 | #REF! | 513 | 486.746 | 0 | 0 | 486.746 | 26.254 |  | 0
| 38 | LCP-170099 |  |  | 2017 | 2017-06-16 | 2017-06-16 | 2019-06-25 | 739 | 2018-12-15 | 2019-06-16 | [5 empty] | AME | STAFF |  | Carryover |  | PROJETO | FABIO MORAES | FAM PRODUCTIVITY PROJECTS | Productivity | CLSD | OK, FINALIZADO | OK | OK | OK | [5 empty] | #REF! | [6 empty] | 0 |  | 0 |  | 987.73 | 38 | 1025.73 | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 | 0 | 0 | #REF! | 987.731 | 801.6134 | 0 | 0 | 801.6134 | 186.1176 |  | 0
| 39 | LCP-170107 |  |  | 2017 | 2017-06-23 | 2017-06-23 | 2019-07-30 | 767 | 2018-12-22 | 2019-06-23 | [5 empty] | AME | A |  | Carryover |  | PROJETO | FABIO MORAES | WIRE CAL AUTOMATIC WIND UP & CUTE IN ANGLE | Quality | CLSD | OK, FINALIZADO | OK | OK | OK | [5 empty] | #REF! | [6 empty] | 117.9438 |  | 0 |  | 713.3 | 23 | 736.3 | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 | 0 | 0 | #REF! | 713.3 | 659.1775 | 0 | 0 | 659.1775 | 54.1225 |  | 0
| 40 | LCP-170118 |  | 19/0101 | 2017 | 2017-05-05 | 2017-05-05 | 2019-10-14 | 892 | 2018-11-03 | 2019-05-05 | [5 empty] | RET | STAFF |  | Carryover |  | PROJETO | CHARLES BARBAN | RET - THERMAL OIL BOILER | Facilities Sustaining | CLSD | OK, FINALIZADO | OK | OK | OK | [5 empty] | #REF! | [6 empty] | 37.5297 | 0 | 1.1069 |  | 248 | 95 | 343 | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 | 0 | 0 | #REF! | 248 | 203.2111 | 0 | 0 | 203.2111 | 44.7889 |  | 0
| 41 | LCP-170154 |  |  | 2017 | 2017-06-07 | 2017-12-18 | 2020-08-25 | 981 | 2019-06-18 | 2019-12-18 | [5 empty] | BRZ | B2 |  | Carryover |  | PROJETO | DIEGO RAGONHA | BRZ - AVCB NEW WAREHOUSE-BUILDING COMMERCIAL | SAG | CLSD | OK, FINALIZADO | OK | OK | OK | Scope Change |  |  |  |  | #REF! | [6 empty] | 1070.1851 | 211.9552 | 134.1426 | 0.7 | 2866.6 | 119 | 2985.6 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 | 0 | 0 | #REF! | 2866.6 | 2781.012 | 0 | 0 | 2781.012 | 85.588 | 0 | 0
| 42 | LCP-170159 |  |  | 2017 | 2017-08-17 | 2017-08-17 | 2019-04-05 | 596 | 2019-02-15 | 2019-08-17 | [5 empty] | AME | B1 |  | Carryover |  | PROJETO | RICARDO TEIXEIRA | AME - SEPARATED INNERLINER NEST#18 & #20 | Productivity | CLSD | OK, FINALIZADO | OK | OK | OK | [5 empty] | #REF! | [6 empty] | 35.3332 | 0 | 0 |  | 355.02 | 45 | 400.02 | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 | 0 | 0 | #REF! | 355.017 | 341.418 | 0 | 0 | 341.418 | 13.599 |  | 0
| 43 | LCP-170161 |  |  | 2017 | 2017-06-29 | 2017-07-27 | 2019-03-01 | 582 | 2019-01-25 | 2019-07-27 | [5 empty] | BRZ | STAFF |  | Carryover |  | PROJETO | RICARDO TEIXEIRA | AME WAREHOUSE MANAGEMENT SYSTEM UPGRADE | SAG | CLSD | OK, FINALIZADO | OK | OK | OK | [5 empty] | #REF! | [6 empty] | 32.2269 | 0 | 0 |  | 464.6 | 3.2 | 467.8 | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 | 0 | 0 | #REF! | 464.6 | 450.6737 | 0 | 0 | 450.6737 | 13.9263 |  | 0
| 44 | LCP-170170 |  |  | 2017 | 2017-07-27 | 2017-07-27 | 2019-02-04 | 557 | 2019-01-25 | 2019-07-27 | [5 empty] | AME | B1 |  | Carryover |  | PROJETO | RICARDO TEIXEIRA | AME - R1 MACHINE STITCHER UPGRADE | Productivity | CLSD | OK, FINALIZADO | OK | OK | OK | [5 empty] | #REF! | [6 empty] | 0.167 |  | 0 |  | 198 | 0 | 198 | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 | 0 | 0 | #REF! | 198 | 196.4219 | 0 | 0 | 196.4219 | 1.5781 |  | 0
| 45 | LCP-170194 |  |  | 2017 | 2017-09-01 | 2017-09-01 | 2019-02-21 | 538 | 2019-03-02 | 2019-09-01 | [5 empty] | MC |  |  | Carryover |  | PROJETO | CHARLES BARBAN | UPG MOUNTING LINE FOR MQB - ANCHIETA | Facilities Sustaining | CLSD | OK, FINALIZADO | OK | OK | OK | [5 empty] | #REF! | [6 empty] | -2.6 |  | 0 |  | 234 | 0 | 234 | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 | 0 | 0 | #REF! | 234 | 217.4218 | 0 | 0 | 217.4218 | 16.5783 |  | 0
| 46 | LCP-170210 |  |  | 2017 | 2017-10-19 | 2017-10-19 | 2019-05-03 | 561 | 2019-04-19 | 2019-10-19 | [5 empty] | SAO | STAFF |  | Carryover |  | PROJETO | CHARLES BARBAN | CURING EXHAUST SYSTEM - FSP | EHS | CLSD | OK, FINALIZADO | OK | OK | OK | [5 empty] | #REF! | [6 empty] | 0 |  | 0 |  | 68 | 0 | 68 | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 | 0 | 0 | #REF! | 68 | 62.6972 | 0 | 0 | 62.6972 | 5.3028 |  | 0
| 47 | LCP-180002 |  | 18/0040 | 2018 | 2018-03-27 | 2018-03-27 | 2021-02-24 | 1065 | 2019-09-25 | 2020-03-26 | [5 empty] | AME | STAFF | EHS | Carryover | 1450024 | PROJETO | DIEGO RAGONHA | FAM AVCB PHASE II EMERGENCY LIGHTINING AND ALARMS | EHS | CLSD | OK, FINALIZADO | OK | OK | OK | [5 empty] | #REF! | [6 empty] | 1618.2744 | 190 | 26.1277 | 75 | 3492 | 160.4 | 3652.4 | 9.7634 | 0 | 0 | 0 | 9.7634 | 0 | 0 | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 9.7634 | 0 | 9.7634 | 9.7634 | 0 | #REF! |  | 9.7634 | 0 | 0 | #REF! | 3492 | 3328.7948 | 0 | 0 | 3328.7948 | 163.2053 | 0 | 0
| 48 | LCP-180003 |  |  | 2017 | 2017-12-21 | 2017-12-21 | 2020-12-28 | 1103 | 2019-06-21 | 2019-12-21 | [5 empty] | MC |  |  | Carryover | 1486809 | PROJETO | DIEGO RAGONHA | GEM PROJECT EMC GRAVATAÍ | SAG | CLSD | OK, FINALIZADO | OK | OK | OK | [5 empty] | #REF! | [6 empty] | 840.8428 | 150 | 154.3102 | 10.0296 | 3767.5 | 250 | 4017.5 | 6.4282 | 0 | -6.9704 | 7 | 13.3985 | 0 | 0 | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 6.4282 | 0 | 6.4282 | 6.4282 | 0 | #REF! |  | 6.4282 | 0 | 0 | #REF! | 3767.5 | 3610.5726 | 0 | 0 | 3610.5726 | 156.9274 | 0 | 0
| 49 | LCP-180005 |  |  | 2018 | 2018-02-06 | 2018-02-06 | 2019-08-20 | 560 | 2019-08-07 | 2020-02-06 | [5 empty] | AME | B2 |  | Carryover |  | PROJETO | FABIO MORAES | QUICK CHANGE OVER NGTTS#3 | Productivity | CLSD | OK, FINALIZADO | OK | OK | OK | [5 empty] | #REF! | [6 empty] | 216.9343 |  | 0 |  | 499.89 | 68 | 567.89 | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 | 0 | 0 | #REF! | 499.89 | 469.4339 | 0 | 0 | 469.4339 | 30.4561 |  | 0
| 50 | LCP-180009 |  | 18/003 | 2018 | 2018-01-15 | 2018-01-15 | 2019-09-11 | 604 | 2019-07-16 | 2020-01-15 | [5 empty] | AME | B2 |  | Carryover |  | PROJETO | HUELITON MAGNANI | VOC REDUCTION IN APEX APLIER | EHS | CLSD | OK, FINALIZADO | OK | OK | OK | [5 empty] | #REF! | [6 empty] | 29.0262 |  | 0 |  | 206.3 | 22.5 | 228.8 | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 | 0 | 0 | #REF! | 206.3 | 205.1404 | 0 | 0 | 205.1404 | 1.1596 |  | 0
| 51 | LCP-180010 |  |  | 2018 | 2018-03-26 | 2018-03-26 | 2021-01-05 | 1016 | 2019-09-24 | 2020-03-25 | [5 empty] | AME | B1 | VULCANIZAÇÃO | Carryover |  | PROJETO | RICARDO TEIXEIRA | (3) NEW 52 HYDRAULIC CONSUMER PRESSES | Capability | CLSD | OK, FINALIZADO | OK | OK | OK |  |  |  | ICP-180009 |  | #REF! | [6 empty] | 2023.9338 | 39.4308 | 260.4164 | 63.7491 | 2961.5 | 245 | 3206.5 | 54.7106 | 15 | 14.0575 | 8.8916 | 40.6531 | 0 | 0 | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 54.7106 | 0 | 54.7106 | 54.7106 | 0 | #REF! |  | 54.7106 | 0 | 0 | #REF! | 2961.5 | 2734.6366 | 0 | 0 | 2734.6366 | 226.8634 | 0 | 0
| 52 | LCP-180011 |  |  | 2017 | 2017-12-14 | 2017-12-15 | 2017-12-15 | 0 | 2019-06-15 | 2019-12-15 | [5 empty] | AME | B2 |  | Carryover |  | PROJETO | FABIO MORAES | IMPROVEMENT OF EXHAUST COMMERCIAL FINAL FINISH AREA | EHS | CLSD | PROJETO CANCELADO | OK | OK | OK | [5 empty] | #REF! | [6 empty] | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| 53 | LCP-180013 |  | 18/0045 | 2018 | 2018-03-21 | 2018-03-21 | 2019-11-06 | 595 | 2019-09-19 | 2020-03-20 | [5 empty] | AME | A |  | Carryover |  | PROJETO | GUSTAVO PARRAS | MIXER#2 BODY REPLACEMENT | Facilities Sustaining | CLSD | OK, FINALIZADO | OK | OK | OK | [5 empty] | #REF! | [6 empty] | 377.7798 | 0 | 7.0725 |  | 1426.22 | 55.55 | 1481.77 | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 | 0 | 0 | #REF! | 1426.215 | 1422.4791 | 0 | 0 | 1422.4791 | 3.7359 |  | 0
| 54 | LCP-180014 |  | 17/0086 | 2018 | 2018-02-08 | 2018-02-08 | 2020-12-28 | 1054 | 2019-08-09 | 2020-02-08 | [5 empty] | AME | A |  | Carryover |  | PROJETO | GUSTAVO PARRAS | SEMI AUTOMATIC BEAD STAPLER | Productivity | CLSD | OK, FINALIZADO | OK | OK | OK | [5 empty] | #REF! | [6 empty] | 65.3525 | 46.4 | 0.59936 |  | 271 | 10 | 281 | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 | 0 | 0 | #REF! | 271 | 225.2098 | 0 | 0 | 225.2098 | 45.7902 |  | 0
0 | 55 | LCP-180015 |  | 18/0026 | 2018 | 2018-03-15 | 2018-03-15 | 2020-01-31 | 687 | 2019-09-13 | 2020-03-14 | [5 empty] | AME | A |  | Carryover |  | PROJETO | GUSTAVO PARRAS | UPGRADE OF DRIVES NRM#2 - CAL4R#2 | Facilities Sustaining | CLSD | OK, FINALIZADO | OK | OK | OK | [5 empty] | #REF! | [6 empty] | 71.7791 | 39.5913 | 9.1708 |  | 454 | 5 | 459 | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 | 0 | 0 | #REF! | 454 | 424.0856 | 0 | 0 | 424.0856 | 29.9144 |  | 0
| 56 | LCP-180018 |  |  | 2018 | 2018-05-21 | 2018-05-21 | 2019-07-25 | 430 | 2019-11-19 | 2020-05-20 | [5 empty] | AME | B1 |  | Carryover |  | PROJETO | RICARDO TEIXEIRA | AUTOMATIC BARCODE READER - FF CONSUMER | Productivity | CLSD | OK, FINALIZADO | OK | OK | OK | [5 empty] | #REF! | [6 empty] | 35.5168 | 0 | 0.31917 |  | 160 | 15 | 175 | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 | 0 | 0 | #REF! | 160 | 156.6309 | 0 | 0 | 156.6309 | 3.3691 |  | 0
| 57 | LCP-180019 |  |  | 2018 | 2018-03-15 | 2018-03-15 | 2019-05-03 | 414 | 2019-09-13 | 2020-03-14 | [5 empty] | AME | STAFF |  | Carryover |  | PROJETO | ANDERSON BASSO | AME - ANNUAL MISCELANEOUS <50K ALL PLANTS | Facilities Sustaining | CLSD | OK, FINALIZADO | OK | OK | OK | [5 empty] | #REF! | [6 empty] | 9.8458 |  | 0 |  | 1212 | 0 | 1212 | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 | 0 | 0 | #REF! | 1212 | 1152.578 | 0 | 0 | 1152.578 | 59.422 |  | 0
| 58 | LCP-180043 |  |  | 2018 | 2018-06-26 | 2018-06-26 | 2019-11-08 | 500 | 2019-12-25 | 2020-06-25 | [5 empty] | AME | A |  | Carryover |  | PROJETO | HENRIQUE CARDOSO | AME - REPLACEMENT OF HOTFORMER CHILLER | Energy Conservation | CLSD | OK, FINALIZADO | OK | OK | OK | [5 empty] | #REF! | [6 empty] | 56.426 |  | 0 |  | 206.35 | 10 | 216.35 | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 | 0 | 0 | #REF! | 206.35 | 206.3414 | 0 | 0 | 206.3414 | 0.00858 |  | 0
| 59 | LCP-180049 |  | 18/0087 | 2018 | 2018-05-03 | 2018-05-03 | 2019-11-06 | 552 | 2019-11-01 | 2020-05-02 | [5 empty] | AME | A |  | Carryover |  | PROJETO | GUSTAVO PARRAS | AME - UPG PLC OF BB#3 | Facilities Sustaining | CLSD | OK, FINALIZADO | OK | OK | OK | [5 empty] | #REF! | [6 empty] | 30.99 |  | 0 |  | 187.1 | 15.3 | 202.4 | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 | 0 | 0 | #REF! | 187.1 | 179.2305 | 0 | 0 | 179.2305 | 7.8694 |  | 0
| 60 | LCP-180051 |  |  | 2018 | 2018-02-15 | 2018-04-19 | 2019-05-02 | 378 | 2019-10-18 | 2020-04-18 | [5 empty] | BRZ | STAFF |  | Carryover |  | PROJETO | RICARDO TEIXEIRA | BRZ - FAM WH Loading Docks Adequacy - 5 Remaining Equipments | SAG | CLSD | OK, FINALIZADO | OK | OK | OK | [5 empty] | #REF! | [6 empty] | 15.97 |  | 0 |  | 112.1 | 5.3 | 117.4 | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 | 0 | 0 | #REF! | 112.1 | 101.4706 | 0 | 0 | 101.4706 | 10.6294 |  | 0
| 61 | LCP-180056 |  | 18/0023 | 2018 | 2018-05-18 | 2018-05-18 | 2019-09-04 | 474 | 2019-11-16 | 2020-05-17 | [5 empty] | AME | A |  | Carryover |  | PROJETO | DIEGO CASTANHARO | AME- Cement house cointaiment area | EHS | CLSD | OK, FINALIZADO | OK | OK | OK | [5 empty] | #REF! | [6 empty] | 6.633 |  | 0 |  | 68.5 | 9.8 | 78.3 | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 | 0 | 0 | #REF! | 68.5 | 65.7357 | 0 | 0 | 65.7357 | 2.7643 |  | 0
| 62 | LCP-180078 |  | 18/0152 | 2018 | 2018-10-18 | 2018-10-18 | 2019-09-27 | 344 | 2020-04-17 | 2020-10-17 | [5 empty] | BRZ | STAFF |  | Carryover |  | PROJETO | DIEGO CASTANHARO | BRZ - FAM WH Security Control (Control System & Cameras) | SAG | CLSD | OK, FINALIZADO | OK | OK | OK | [5 empty] | #REF! | [6 empty] | 29.4527 |  | 0 |  | 56.65 | 0 | 56.65 | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 | 0 | 0 | #REF! | 56.65 | 55.8909 | 0 | 0 | 55.8909 | 0.75909 |  | 0
| 63 | LCP-180080 |  |  | 2018 | 2018-04-28 | 2018-11-07 | 2020-12-29 | 783 | 2020-05-07 | 2020-11-06 | [5 empty] | AME | B2 | CONSTRUÇÃO | Carryover |  | PROJETO | FABIO MORAES | COMMERCIAL TIRE BUILDING MACHINE | Capability | CLSD | OK, FINALIZADO | OK | OK | OK |  |  |  | ICP-180013 |  | #REF! | [6 empty] | 6188.7674 | 403 | 671.8303 | 5.3449 | 10188.98 | 1640.69 | 11829.67 | 31.9877 | 0 | 0.34495 | 5 | 31.6428 | 0 | 0 | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 31.9877 | 0 | 31.9877 | 31.9877 | 0 | #REF! |  | 31.9877 | 0 | 0 | #REF! | 10218.982 | 6927.7917 | 0 | 0 | 6927.7917 | 3291.1903 | 0 | 0
| 64 | LCP-180081 |  | 20/0036 | 2018 | 2018-03-22 | 2018-08-17 | 2020-12-29 | 865 | 2020-02-15 | 2020-08-16 | [5 empty] | MC |  |  | Carryover | 1784196 | PROJETO | DIEGO RAGONHA | GEM PROJECT SÃO CAETANO DO SUL | SAG | CLSD | OK, FINALIZADO | OK | OK | OK | Scope Change |  |  |  |  | #REF! | [6 empty] | 2414.5149 | 150 | 104.8282 | -0.35293 | 5863 | 194.6 | 6057.6 | -0.75345 | 0 | -5.3529 | 5 | 4.5995 | 0 | 0 | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | -0.75345 | 0 | -0.75345 | -0.75345 | 0 | #REF! |  | -0.75345 | 0 | 0 | #REF! | 5863 | 5094.0186 | 0 | 0 | 5094.0186 | 768.9814 | 0 | 0
| 65 | LCP-180082 |  | 18/0065 | 2018 | 2018-04-09 | 2018-04-09 | 2019-03-25 | 350 | 2019-10-08 | 2020-04-08 | [5 empty] | AME | STAFF |  | Carryover |  | PROJETO | DIEGO CASTANHARO | NEW RUBBER PROCESS ANALYZER (RPA) | Quality | CLSD | OK, FINALIZADO | OK | OK | OK | [5 empty] | #REF! | [6 empty] | 1.25 |  | 0 |  | 211.8 | 0 | 211.8 | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 | 0 | 0 | #REF! | 211.8 | 186.1761 | 0 | 0 | 186.1761 | 25.6239 |  | 0
| 66 | LCP-180088 |  | 18/0077 | 2018 | 2018-06-06 | 2018-06-06 | 2019-07-25 | 414 | 2019-12-05 | 2020-06-05 | [5 empty] | AME | B2 |  | Carryover |  | PROJETO | GUSTAVO PARRAS | UPGRADE OF CURING WEB APPLICATION | IT | CLSD | OK, FINALIZADO | OK | OK | OK | [5 empty] | #REF! | [6 empty] | 36.7446 |  | 0 |  | 114.11 | 0 | 114.11 | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 | 0 | 0 | #REF! | 114.114 | 95.8164 | 0 | 0 | 95.8164 | 18.2976 |  | 0
| 67 | LCP-180090 |  | 18/0067 | 2018 | 2018-10-17 | 2018-10-17 | 2019-08-26 | 313 | 2020-04-16 | 2020-10-16 | [5 empty] | RET | STAFF |  | Carryover |  | PROJETO | CHARLES BARBAN | RET - UPGRADE DRIVE GV3000 TO POWERFLEX EXTRUDER | Facilities Sustaining | CLSD | OK, FINALIZADO | OK | OK | OK | [5 empty] | #REF! | [6 empty] | 80.3815 | 0 | 0.00149 |  | 211.9 | 12.96 | 224.86 | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 | 0 | 0 | #REF! | 211.9 | 203.5814 | 0 | 0 | 203.5814 | 8.3186 |  | 0
| 68 | LCP-180095 |  | 18/0107 | 2018 | 2018-06-26 | 2018-06-26 | 2021-06-28 | 1098 | 2019-12-25 | 2020-06-25 | [5 empty] | AME | A | CALANDRA | Carryover |  | PROJETO | GUSTAVO PARRAS | AME - METAL DETECTOR IN CALANDERS (FORD PROJECT) | Quality | CLSD | OK, FINALIZADO | OK | OK | OK | Scope Change |  |  |  |  | #REF! | [6 empty] | 71.9081 | 19.5 | 9.8376 | 50 | 296 | 5 | 301 | 24.6174 | 15 | 0 | 15 | 8.2248 | 1.5 | 2.9222 | 3.5 | 0.92999 | 5.5 | 5.401 | 7 | 7.1394 | [13 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 24.6174 | 0 | 24.6174 | 24.6174 | 0 | #REF! |  | 11.147 | 13.4704 | 0 | #REF! | 296 | 259.9362 | 0 | 0 | 259.9362 | 36.0638 | 0 | 0
| 69 | LCP-180097 |  | 18/0071 | 2018 | 2018-05-31 | 2018-05-31 | 2020-02-26 | 636 | 2019-11-29 | 2020-05-30 | [5 empty] | AME | A |  | Carryover |  | PROJETO | GUSTAVO PARRAS | UPGRADE FACKTOR LINK/ GML D#4 | Facilities Sustaining | CLSD | OK, FINALIZADO | OK | OK | OK | [5 empty] | #REF! | [6 empty] | 41.2854 | 25.2469 | 19.7699 |  | 275.96 | 7 | 282.96 | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 | 0 | 0 | #REF! | 275.956 | 255.6238 | 0 | 0 | 255.6238 | 20.3322 |  | 0
| 70 | LCP-180101 |  |  | 2018 | 2018-07-19 | 2018-07-19 | 2019-05-03 | 288 | 2020-01-17 | 2020-07-18 | [5 empty] | RET | STAFF |  | Carryover |  | PROJETO | CHARLES BARBAN | RET - ANNUAL MISCELLANEOUS <50K ALL PLANTS | Facilities Sustaining | CLSD | OK, FINALIZADO | OK | OK | OK | [5 empty] | #REF! | [6 empty] | -1.3 |  | 0 |  | 75 | 0 | 75 | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 | 0 | 0 | #REF! | 75 | 66.3575 | 0 | 0 | 66.3575 | 8.6425 |  | 0
| 71 | LCP-180104 |  |  | 2018 | 2018-05-18 | 2018-05-18 | 2020-02-10 | 633 | 2019-11-16 | 2020-05-17 | [5 empty] | AME | B1 |  | Carryover |  | PROJETO | RICARDO TEIXEIRA | AME - FVM GRINDERS AUTOMATION | Energy Conservation | CLSD | OK, FINALIZADO | OK | OK | OK | [5 empty] | #REF! | [6 empty] | 100.7238 |  | 0 |  | 116.58 | 3 | 119.58 | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 | 0 | 0 | #REF! | 116.58 | 103.4854 | 0 | 0 | 103.4854 | 13.0946 |  | 0
| 72 | LCP-180108 |  | 18/0106 | 2018 | 2018-07-12 | 2018-07-12 | 2019-11-08 | 484 | 2020-01-10 | 2020-07-11 | [5 empty] | RET | STAFF |  | Carryover |  | PROJETO | CHARLES BARBAN | RET - ADEQ. OF NR17 & NR12 | EHS | CLSD | OK, FINALIZADO | OK | OK | OK | [5 empty] | #REF! | [6 empty] | 27.9038 | 0 | 0 |  | 99.1 | 3.4 | 102.5 | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 | 0 | 0 | #REF! | 99.1 | 91.0531 | 0 | 0 | 91.0531 | 8.0469 |  | 0
| 73 | LCP-180111 |  | 18/0150 | 2018 | 2018-04-24 | 2018-10-25 | 2019-09-02 | 312 | 2020-04-24 | 2020-10-24 | [5 empty] | BRZ | STAFF |  | Carryover |  | PROJETO | DIEGO CASTANHARO | REG - LAPG VDA FIRE PROTECTION LINE | SAG | CLSD | OK, FINALIZADO | OK | OK | OK | [5 empty] | #REF! | [6 empty] | 69.1694 |  | 0 |  | 111.75 | 0 | 111.75 | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 | 0 | 0 | #REF! | 111.75 | 104.376 | 0 | 0 | 104.376 | 7.374 |  | 0
| 74 | LCP-180113 |  |  | 2018 | 2018-05-24 | 2018-05-24 | 2019-07-25 | 427 | 2019-11-22 | 2020-05-23 | [5 empty] | AME | STAFF |  | Carryover |  | PROJETO | HEDSLEY QUINTAL | GENERATION CONTROL SYSTEM - POWER HOUSE ADEQUACY | Facilities Sustaining | CLSD | OK, FINALIZADO | OK | OK | OK | [5 empty] | #REF! | [6 empty] | 0.8 |  | 0 |  | 64.7 | 8.1 | 72.8 | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 | 0 | 0 | #REF! | 64.7 | 62.255 | 0 | 0 | 62.255 | 2.445 |  | 0
| 75 | LCP-180114 |  | 18/0159 | 2018 | 2018-11-21 | 2018-11-21 | 2021-06-28 | 950 | 2020-05-21 | 2020-11-20 | [5 empty] | AME | B2 | PRÉDIO 3 | Carryover |  | PROJETO | GUSTAVO PARRAS | LAMINATOR PROFILE AUTOMATION | Facilities Sustaining | CLSD | OK, FINALIZADO | OK | OK | OK | Scope Change |  |  |  |  | #REF! | [6 empty] | 110.3746 | 207.7526 | 51.8944 | 94.2938 | 267.8 | 37.75 | 305.55 | 38.5557 | 8 | 4.2938 | 5 | 0.22029 | 5 | 0.09915 | 15 | 8.9046 | 10 | 2.8587 | 20 | 22.1791 | [13 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 38.5557 | 0 | 38.5557 | 38.5557 | 0 | #REF! |  | 4.6133 | 33.9424 | 0 | #REF! | 267.8 | 200.9049 | 0 | 0 | 200.9049 | 66.8951 | 0 | 0
| 76 | LCP-180115 |  |  | 2018 | 2018-08-17 | 2018-08-17 | 2020-12-28 | 864 | 2020-02-15 | 2020-08-16 | [5 empty] | AME | A |  | Carryover |  | PROJETO | HENRIQUE CARDOSO | AME - CLOSED WATER SYSTEM - MIXERS SUBSTATIONS | Energy Conservation | CLSD | OK, FINALIZADO | OK | OK | OK | [5 empty] | #REF! | [6 empty] | 230.2222 | 3.8 | 15.6748 |  | 329.75 | 10 | 339.75 | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 | 0 | 0 | #REF! | 329.75 | 328.5437 | 0 | 0 | 328.5437 | 1.2063 |  | 0
| 77 | LCP-180116 |  |  | 2018 | 2018-08-23 | 2018-08-23 | 2020-01-28 | 523 | 2020-02-21 | 2020-08-22 | [5 empty] | AME | STAFF |  | Carryover |  | PROJETO | HENRIQUE CARDOSO | HVAC – CENTRAL OFFICE | Energy Conservation | CLSD | OK, FINALIZADO | OK | OK | OK | [5 empty] | #REF! | [6 empty] | 251.1682 | 2.033 | 2.0255 |  | 338.5753 | 10 | 348.5753 | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 | 0 | 0 | #REF! | 338.5753 | 338.5753 | 0 | 0 | 338.5753 | 0 |  | 0
| 78 | LCP-180117 |  | 18/0110 | 2018 | 2018-10-25 | 2018-10-17 | 2021-02-25 | 862 | 2020-04-16 | 2020-10-16 | SIM |  |  |  |  | SAO | STAFF |  | Carryover |  | PROJETO | CHARLES BARBAN | SAO - NEW ORBITREAD MACHINE | SAG | CLSD | OK, FINALIZADO | OK | OK | OK | [5 empty] | #REF! | [6 empty] | 3.38 | 378.7 | 1.9461 | 376.7 | 387.67 | 37.4 | 425.07 | 312.4518 | 0 | 0 | 0 | 292.8049 | 0 | 0 | 0 | 5.0639 | 70 | 3.3316 | 12 | 6.5518 |  | 4.6996 | [11 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 312.4518 | 0 | 312.4518 | 312.4518 | 0 | #REF! |  | 292.8049 | 14.9473 | 4.6996 | #REF! | 387.67 | 323.3751 | 0 | 0 | 323.3751 | 64.2949 | 0 | 0
| 79 | LCP-180137 |  |  | 2018 | 2018-11-28 | 2018-11-28 | 2021-01-04 | 768 | 2020-05-28 | 2020-11-27 | [5 empty] | AME | UTIL | CASA FORÇA | Carryover |  | PROJETO | HENRIQUE CARDOSO | (10) VDF PANEL INSTALLATION | Energy Conservation | CLSD | OK, FINALIZADO | OK | OK | OK | [5 empty] | #REF! | [6 empty] | 160.4959 | 42.3498 | 46.5994 | 0.36386 | 213 | 25 | 238 | 0.32969 | 5 | 0.26386 | 0.1 | 0.06583 | 0 | 0 | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0.32969 | 0 | 0.32969 | 0.32969 | 0 | #REF! |  | 0.32969 | 0 | 0 | #REF! | 213 | 207.5797 | 0 | 0 | 207.5797 | 5.4203 | 0 | 0
| 80 | LCP-180139 |  |  | 2018 | 2018-10-02 | 2018-10-02 | 2021-02-25 | 877 | 2020-04-01 | 2020-10-01 | [5 empty] | AME | UTIL | CASA FORÇA | Carryover |  | PROJETO | HENRIQUE CARDOSO | POWER HOUSE STEAM TURBINE | Energy Conservation | CLSD | OK, FINALIZADO | OK | OK | OK | [5 empty] | #REF! | [6 empty] | 885.011 | 71.4 | 58.1944 | 8.864 | 1326.87 | 24.32 | 1351.19 | 1.3028 | 5 | -6.136 | 5 | 7.4388 | 0 | 0 | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 1.3028 | 0 | 1.3028 | 1.3028 | 0 | #REF! |  | 1.3028 | 0 | 0 | #REF! | 1326.865 | 1314.9529 | 0 | 0 | 1314.9529 | 11.912 | 0 | 0
| 81 | LCP-180142 |  | 18/0138 | 2018 | 2018-08-16 | 2018-08-16 | 2019-10-15 | 425 | 2020-02-14 | 2020-08-15 | [5 empty] | AME | STAFF |  | Carryover |  | PROJETO | RICARDO TEIXEIRA | ADEQUACY OF NR#12 COMPLIANCE - PHASE IV | EHS | CLSD | OK, FINALIZADO | OK | OK | OK | [5 empty] | #REF! | [6 empty] | 136.4013 |  | 0 |  | 240 | 0 | 240 | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 | 0 | 0 | #REF! | 240 | 233.9375 | 0 | 0 | 233.9375 | 6.0625 |  | 0
| 82 | LCP-180149 |  | 18/0154 | 2018 | 2018-10-17 | 2018-10-17 | 2021-01-05 | 811 | 2020-04-16 | 2020-10-16 | [5 empty] | AME | B1 | VULCANIZAÇÃO | Carryover |  | PROJETO | RICARDO TEIXEIRA | EXHAUST SYSTEM - LINES A/B & G/H CONSUMER PRESSES | EHS | CLSD | OK, FINALIZADO | OK | OK | OK | [5 empty] | #REF! | [6 empty] | 226.3079 | 163 | 142.4931 | 54.1823 | 473.676 | 19.09 | 492.766 | 40.7685 | 20 | 16.7019 | 5 | 4.9976 | 26 | 8.7775 | 12 | 10.2915 | 0 | -0.22495 | 0 | 0.22495 | [13 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 40.7685 | 0 | 40.7685 | 40.7685 | 0 | #REF! |  | 30.4769 | 10.2915 | 0 | #REF! | 473.676 | 409.6436 | 0 | 0 | 409.6436 | 64.0324 | 0 | 0
| 83 | LCP-180150 |  | 18/0111 | 2018 | 2018-08-16 | 2018-08-16 | 2021-02-25 | 924 | 2020-02-14 | 2020-08-15 | [5 empty] | SAO | STAFF |  | Carryover |  | PROJETO | CHARLES BARBAN | SAO - SHEROGRAPHY UPGRADE (OBSEOLESCENCE AND SOFTWARE) | SAG | CLSD | OK, FINALIZADO | OK | OK | OK | [5 empty] | #REF! | [6 empty] | 40.8879 | 55.7 | 26.215 | 9.9 | 77.8 | 0 | 77.8 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 | 0 | 0 | #REF! | 77.8 | 67.8852 | 0 | 0 | 67.8852 | 9.9148 | 0 | 0
| 84 | LCP-180155 |  | 18/153 | 2018 | 2018-10-17 | 2018-10-17 | 2019-10-14 | 362 | 2020-04-16 | 2020-10-16 | [5 empty] | SAO | STAFF |  | Carryover |  | PROJETO | CHARLES BARBAN | SAO - NR12 PROJECT | EHS | CLSD | OK, FINALIZADO | OK | OK | OK | [5 empty] | #REF! | [6 empty] | 21.5825 |  | 0 |  | 145.15 | 0 | 145.15 | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 | 0 | 0 | #REF! | 145.15 | 16.6178 | 0 | 0 | 16.6178 | 128.5322 |  | 0
| 85 | LCP-180157 |  | 20/0031 | 2018 | 2018-11-01 | 2018-11-01 | 2019-12-20 | 414 | 2020-05-01 | 2020-10-31 | [5 empty] | AME | STAFF |  | Carryover | 457281 | PROJETO | HEDSLEY QUINTAL | FIRE FIGHTING SYSTEM BUILDING 75 | EHS | CLSD | OK, FINALIZADO | OK | OK | OK | [5 empty] | #REF! | [6 empty] | 100.4942 | 10.6 | 1.065 |  | 109 | 3 | 112 | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 | 0 | 0 | #REF! | 109 | 102.4259 | 0 | 0 | 102.4259 | 6.5741 |  | 0
| 86 | LCP-180163 |  |  | 2018 | 2018-08-23 | 2018-08-23 | 2019-05-03 | 253 | 2020-02-21 | 2020-08-22 | [5 empty] | MC |  |  | Carryover |  | PROJETO | CHARLES BARBAN | 2018 MISCELLANEOUS PROJECT TO MC PLANTs | Facilities Sustaining | CLSD | OK, FINALIZADO | OK | OK | OK | [5 empty] | #REF! | [6 empty] | -0.73 |  | 0 |  | 74.5 | 0 | 74.5 | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 | 0 | 0 | #REF! | 74.5 | 23.3571 | 0 | 0 | 23.3571 | 51.1429 |  | 0
| 87 | LCP-180174 |  | 18/0139 | 2018 | 2018-09-09 | 2018-09-09 | 2021-06-28 | 1023 | 2020-03-09 | 2020-09-08 | [5 empty] | AME | A | ENTUBADORA | Carryover | 2252277 | PROJETO | GUSTAVO PARRAS | METAL DETECTOR IN EXTRUDERS | Quality | CLSD | OK, FINALIZADO | OK | OK | OK | [5 empty] | #REF! | [6 empty] | 68.2762 | 321.4 | 227.7045 | 26.9051 | 390.22 | 5 | 395.22 | 47.4119 | 15 | 7.6994 | 3.2057 | 2.6141 | 7 | 11.7751 | 3 | 3.6896 | 8 | 14.0112 | 5 | 7.6225 | [13 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 47.4119 | 0 | 47.4119 | 47.4119 | 0 | #REF! |  | 22.0887 | 25.3232 | 0 | #REF! | 390.224 | 343.8909 | 0 | 0 | 343.8909 | 46.3331 | 0 | 0
| 88 | LCP-180177 |  | 18/0134 | 2018 | 2018-09-13 | 2018-09-13 | 2019-07-25 | 315 | 2020-03-13 | 2020-09-12 | [5 empty] | AME | B2 |  | Carryover |  | PROJETO | FABIO MORAES | NEW DUCTS TO COMMERCIAL CURING AREA | EHS | CLSD | OK, FINALIZADO | OK | OK | OK | [5 empty] | #REF! | [6 empty] | 0.17 |  | 0 |  | 106.42 | 15 | 121.42 | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 | 0 | 0 | #REF! | 106.415 | 92.5152 | 0 | 0 | 92.5152 | 13.8998 |  | 0
| 89 | LCP-180178 |  | 18/0155 | 2018 | 2018-11-16 | 2018-11-16 | 2020-12-28 | 773 | 2020-05-16 | 2020-11-15 | [5 empty] | AME | B2 | CONSTRUÇÃO | Carryover |  | PROJETO | RICARDO TEIXEIRA | WIND UP LET OFF NGTTS#5 & #8 | EHS | CLSD | OK, FINALIZADO | OK | OK | OK | [5 empty] | #REF! | [6 empty] | 112.3915 | 47.5 | 37.8231 | 3.4014 | 242.75 | 22 | 264.75 | 2.8157 | 4 | 3.4014 | 0 | -0.58574 | 0 | 0 | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 2.8157 | 0 | 2.8157 | 2.8157 | 0 | #REF! |  | 2.8157 | 0 | 0 | #REF! | 242.75 | 235.9864 | 0 | 0 | 235.9864 | 6.7636 | 0 | 0
| 90 | LCP-180179 |  | 18/0148 | 2018 | 2018-10-08 | 2018-10-08 | 2021-01-22 | 837 | 2020-04-07 | 2020-10-07 | [5 empty] | AME | A | CALANDRA | Carryover |  | PROJETO | GUSTAVO PARRAS | UPG DRIVES & CONTROLS – CAL3R | Facilities Sustaining | CLSD | OK, FINALIZADO | OK | OK | OK | Scope Change |  |  |  |  | #REF! | [6 empty] | 600.6645 | 169.1746 | 103.3256 | 13.8226 | 783.3 | 15.5 | 798.8 | 13.0323 | 4.3 | 0.82259 | 5 | 3.5077 | 9 | 8.702 | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 13.0323 | 0 | 13.0323 | 13.0323 | 0 | #REF! |  | 13.0323 | 0 | 0 | #REF! | 783.3 | 749.7649 | 0 | 0 | 749.7649 | 33.5351 | 0 | 0
| 91 | LCP-180180 |  | 18/0156 | 2018 | 2018-11-11 | 2018-11-11 | 2021-01-04 | 785 | 2020-05-11 | 2020-11-10 | [5 empty] | AME | STAFF |  | Carryover |  | PROJETO | RICARDO TEIXEIRA | ANCHOR SYSTEM & SAFETY LINE - PHASE II | EHS | CLSD | OK, FINALIZADO | OK | OK | OK | Scope Change |  |  |  |  | #REF! | [6 empty] | 186.0257 | 110.8585 | 75.3477 |  | 560.6 | 0 | 560.6 | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 | 0 | 0 | #REF! | 560.6 | 261.3734 | 0 | 0 | 261.3734 | 299.2266 |  | 0
| 92 | LCP-180205 |  |  | 2018 | 2018-09-11 | 2018-11-09 | 2020-06-02 | 571 | 2020-05-09 | 2020-11-08 | [5 empty] | BRZ | B2 |  | Carryover |  | PROJETO | HENRIQUE CARDOSO | SORTER B2 - MRT TIRES ADEQUACY | SAG | CLSD | OK, FINALIZADO | OK | OK | OK | [5 empty] | #REF! | [6 empty] | 23.4677 | 0 | 1.8439 |  | 38.64 | 5.5 | 44.14 | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 | 0 | 0 | #REF! | 38.637 | 38.4285 | 0 | 0 | 38.4285 | 0.20846 |  | 0
| 93 | LCP-190004 |  |  | 2019 | 2018-11-09 | 2018-12-07 | 2019-07-30 | 235 | 2020-06-06 | 2020-12-06 | [5 empty] | BRZ | STAFF |  | Carryover |  | PROJETO | DIEGO RAGONHA | DRIVE OVER READER BERTOLINI | SAG | CLSD | OK, FINALIZADO | OK | OK | OK | [5 empty] | #REF! | [6 empty] | 163.3608 | 0 | 8.7749 |  | 190.97 | 0 | 190.97 | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 | 0 | 0 | #REF! | 190.971 | 171.8408 | 0 | 0 | 171.8408 | 19.1302 |  | 0
| 94 | LCP-190006 |  | N/A | 2019 | 2019-01-22 | 2019-01-22 | 2019-01-23 | 1 | 2020-07-22 | 2021-01-21 | [5 empty] | AME | A |  | Carryover | 941509 | PROJETO | GUSTAVO PARRAS | EDGE STRIP KNIFE FOR PLY CUTTER | Quality | CLSD | BUDGET CANCELADO | OK | OK | OK | [5 empty] | #REF! | [6 empty] | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 | 0 | 0 | #REF! | 68.7 | 0 | 0 | 0 | 0 | 68.7 |  | 0
| 95 | LCP-190011 |  | 19/0014 | 2019 | 2019-01-22 | 2019-01-22 | 2020-09-29 | 616 | 2020-07-22 | 2021-01-21 | [5 empty] | AME | A |  | Carryover | 941377 | PROJETO | DIEGO CASTANHARO | QCO - MOTHER ROLL CALEMARD | Quality | CLSD | OK, FINALIZADO | OK | OK | OK | [5 empty] | #REF! | [6 empty] | 26.9724 | 35.2458 | 14.3694 |  | 57 | 0 | 57 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 | 0 | 0 | #REF! | 57 | 41.4433 | 0 | 0 | 41.4433 | 15.5567 |  | 0
| 96 | LCP-190019 |  |  | 2019 | 2019-02-20 | 2019-02-20 | 2020-01-13 | 327 | 2020-08-20 | 2021-02-19 | [5 empty] | AME | STAFF |  | Carryover | 965303 | PROJETO | ANDERSON BASSO | AME - ANNUAL MISCELANEOUS <50K ALL PLANTS | Facilities Sustaining | CLSD | OK, FINALIZADO | OK | OK | OK | [5 empty] | #REF! | [6 empty] | 1160.0741 | -6.5961 | 36.1973 |  | 1236 | 0 | 1236 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 | 0 | 0 | #REF! | 1236 | 1197.407 | 0 | 0 | 1197.407 | 38.593 |  | 0
| 98 | LCP-190025 |  | 19/0070 | 2019 | 2019-03-21 | 2019-03-21 | 2020-01-23 | 308 | 2020-09-18 | 2021-03-20 | [5 empty] | BRZ | STAFF |  | Carryover | 1303242 | PROJETO | DIEGO CASTANHARO | BRZ - WAREHOUSE SAFETY IMPROVEMENTS - AM PLANT | SAG | CLSD | OK, FINALIZADO | OK | OK | OK | [5 empty] | #REF! | [6 empty] | 16.6837 | 0 | 0.00583 |  | 26.2 | 0 | 26.2 | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 | 0 | 0 | #REF! | 26.2 | 16.6895 | 0 | 0 | 16.6895 | 9.5105 |  | 0
| 99 | LCP-190047 |  |  | 2019 | 2019-03-14 | 2019-03-14 | 2020-01-09 | 301 | 2020-09-11 | 2021-03-13 | [5 empty] | RET | STAFF |  | Carryover | 1302696 | PROJETO | CHARLES BARBAN | RET - ANNUAL MISCELLANEOUS <50K ALL PLANTS | Facilities Sustaining | CLSD | OK, FINALIZADO | OK | OK | OK | [5 empty] | #REF! | [6 empty] | 63.9708 |  | 0 |  | 75 | 0 | 75 | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 | 0 | 0 | #REF! | 75 | 63.9708 | 0 | 0 | 63.9708 | 11.0292 |  | 0
| 100 | LCP-190057 |  | 19/0080 | 2019 | 2019-07-10 | 2019-07-09 | 2021-03-30 | 630 | 2021-01-06 | 2021-07-08 | [5 empty] | AME | A | ENTUBADORA | Carryover | 1653298 | PROJETO | GUSTAVO PARRAS | AME - UP GRADE EXTRUSORA Q5 ( AUTOMAX ) PHASE 2 | Facilities Sustaining | CLSD | OK, FINALIZADO | OK | 2021-04-30 | OK | [5 empty] | #REF! | [6 empty] | 125.523 | 236.503 | 55.0877 | 34.8839 | 375.72 | 18 | 393.72 | 48.6922 | 9.1 | 4.884 | 5 | 6.033 | 4 | 5.993 | 18 | 0.28991 | 30 | 31.4923 | 14.4 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 48.6922 | 0 | 48.6922 | 48.6922 | 0 | #REF! |  | 16.91 | 31.7822 | 0 | #REF! | 375.719 | 229.3028 | 0 | 0 | 229.3028 | 146.4162 | 0 | 0
| 101 | LCP-190061 |  | 19/0039 | 2019 | 2019-03-05 | 2019-05-24 |  | -1690.336 | 2020-11-21 | 2021-05-23 | SIM | SIM | SIM | AQ4/21 |  | AME | B2 | CONSTRUÇÃO | Carryover | 1400773 | PROJETO | RICARDO TEIXEIRA | SECURITY IMPROVEMENT IN (8) APEX APPLIER - NGTTS | EHS | CLSD | OK, FINALIZADO | OK | 2021-11-30 | 2021-10-30 | [5 empty] | #REF! | [6 empty] | 0 | 186.4 | 38.172 | 110.0005 | 372.8 | 0 | 372.8 | 232.9908 | 0 | 0 | 0 |  | 50.0005 | 3.5127 | 1.8 | 10.8611 | 5 | 23.1737 | 10 | 25.0528 | 20 | 2.3876 | 37.7 | 70.3591 | 50 | 42.8444 |  | 33.7085 | 8.9 | 21.1258 |  | -0.03487 | -0.03487 | 0 | [12 empty] | 0 | [12 empty] | 0.03487 | 0 | 233.0257 | -0.03487 | 232.9908 | 220.7999 | 12.1909 | #REF! |  | 3.5127 | 59.0876 | 115.5911 | #REF! | 372.8005 | 271.1629 | 0 | 0 | 271.1629 | 101.6376 | 0 | 0
| 102 | LCP-190066 |  |  | 2019 | 2019-04-30 | 2019-04-30 | 2019-06-27 | 58 | 2020-10-28 | 2021-04-29 | [5 empty] | AME | A |  | Carryover | 1401193 | PROJETO | HENRIQUE CARDOSO | REPLACEMENT OF BARREL AND SCREW - Q#5 | Facilities Sustaining | CLSD | OK, FINALIZADO | OK | OK | OK | [5 empty] | #REF! | [6 empty] | 59.0826 |  | 0 |  | 89.85 | 3 | 92.85 | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 | 0 | 0 | #REF! | 89.85 | 59.6848 | 0 | 0 | 59.6848 | 30.1652 |  | 0
| 103 | LCP-190068 |  |  | 2019 | 2019-05-23 | 2019-05-23 | 2020-01-09 | 231 | 2020-11-20 | 2021-05-22 | [5 empty] | MC |  |  | Carryover | 1361619 | PROJETO | CHARLES BARBAN | MC Geral - Miscelanius Quartely | SAG | CLSD | OK, FINALIZADO | OK | OK | OK | [5 empty] | #REF! | [6 empty] | 27.5205 | 0 | 28.5871 |  | 75 | 0 | 75 | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 | 0 | 0 | #REF! | 75 | 56.1076 | 0 | 0 | 56.1076 | 18.8924 |  | 0
| 104 | LCP-190069 |  |  | 2019 | 2019-03-22 | 2019-06-19 | 2019-03-23 | -88 | 2020-12-17 | 2021-06-18 | [5 empty] | BRZ | STAFF |  | Carryover | 1467335 | PROJETO | TI | WAREHOUSE MANAGEMENT CONTROL | SAG | CLSD | PROJETO CANCELADO, SERÁ USADO O BUDGET EM OUTRO PROJETO USD20K | OK | OK | OK | [5 empty] | #REF! | [6 empty] | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 | 0 | 0 | #REF! | 20 | 0 | 0 | 0 | 0 | 20 |  | 0
| 105 | LCP-190078 |  | 19/0081 | 2019 | 2019-05-17 | 2019-05-17 | 2021-01-05 | 599 | 2020-11-14 | 2021-05-16 | [5 empty] | AME | A | CALANDRA | Carryover | 1457603 | PROJETO | DIEGO CASTANHARO | REPLACEMENT OF ROLLS CAL3R | Facilities Sustaining | CLSD | OK, FINALIZADO | OK | OK | OK | Scope Change |  |  |  |  | #REF! | [6 empty] | 381.2657 | 1131.7854 | 767.3315 |  | 1675.63 | 33 | 1708.63 | -1.7347e-18 | 0 | -0.01002 | 0 | 0.01002 | 0 | 0 | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | -1.7347e-18 | 0 | -1.7347e-18 | -1.7347e-18 | 0 | #REF! |  | -1.7347e-18 | 0 | 0 | #REF! | 1675.63 | 1150.0131 | 0 | 0 | 1150.0131 | 525.6169 | 0 | 0
| 106 | LCP-190085 |  |  | 2019 | 2019-04-11 | 2019-08-29 | 2020-01-23 | 147 | 2021-02-26 | 2021-08-28 | [5 empty] | BRZ | STAFF |  | Carryover | 2082187 | PROJETO | RICARDO TEIXEIRA | BRZ - BLUE RACKS FOR CONSUMER TIRES | SAG | CLSD | OK, FINALIZADO | OK | OK | OK | Scope Change |  |  |  |  | #REF! | [6 empty] | 382.68 | 0 | 26.1123 |  | 140 | 0 | 140 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 | 0 | 0 | #REF! | 140 | 115.4854 | 0 | 0 | 115.4854 | 24.5146 |  | 0
| 107 | LCP-190086 |  |  | 2019 | 2019-04-12 | 2019-04-13 | 2019-04-13 | 0 | 2020-10-11 | 2021-04-12 | [5 empty] | BRZ | STAFF |  | Carryover |  | PROJETO | CHARLES BARBAN | PHYSICAL LAYOUT REVIEW | SAG | CLSD | PROJETO CANCELADO, SERÁ USADO O BUDGET EM OUTRO PROJETO USD20K | OK | OK | OK | [5 empty] | #REF! | [6 empty] | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| 108 | LCP-190089 |  |  | 2019 | 2019-07-10 | 2019-06-28 | 2021-02-26 | 609 | 2020-12-26 | 2021-06-27 | [5 empty] | AME | B2 | FINAL FINISH | Carryover | 1588840 | PROJETO | FABIO MORAES | AME - X-ray B upgrade | Facilities Sustaining | CLSD | OK, FINALIZADO | OK | 2021-04-28 | OK |  |  |  | ICP-190027 |  | #REF! | [6 empty] | 0 | 385.7 | 326.7517 | -28.0706 | 385.7 | 32.9 | 418.6 | -26.8809 | -21 | 8.3294 | -36.4 | -35.2103 | 0 | 0 | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | -26.8809 | 0 | -26.8809 | -26.8809 | 0 | #REF! |  | -26.8809 | 0 | 0 | #REF! | 385.7 | 299.8709 | 0 | 0 | 299.8709 | 85.8291 | 0 | 0
| 109 | LCP-190092 |  | 19/0071 | 2019 | 2019-06-19 | 2019-06-19 | 2020-09-03 | 442 | 2020-12-17 | 2021-06-18 | [5 empty] | AME | B1 |  | Carryover | 1584552 | PROJETO | RICARDO TEIXEIRA | SHIPMENT SAFETY IMPROVEMENT | EHS | CLSD | OK, FINALIZADO | OK | OK | OK | [5 empty] | #REF! | [6 empty] | 0.90276 | 7.9089 | 10.3965 |  | 11.5 | 0 | 11.5 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 | 0 | 0 | #REF! | 11.5 | 11.2993 | 0 | 0 | 11.2993 | 0.20074 |  | 0
| 110 | LCP-190117 |  | 19/0110 | 2019 | 2019-06-21 | 2019-06-19 | 2021-01-25 | 586 | 2020-12-17 | 2021-06-18 | [5 empty] | AME | B2 | FINAL FINISH | Carryover | 1677555 | PROJETO | HUELITON MAGNANI | CAP-X-RAY GREEN POINT MARKER | Quality | CLSD | OK, FINALIZADO | OK | 2021-03-31 | OK | [5 empty] | #REF! | [6 empty] | 23.1224 | 41.0875 | 26.8801 | 9.7675 | 67.5 | 6.5 | 74 | 4.6606 | 2 | 1.7675 | 0 | 0.07349 | 8 | 2.8196 | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 4.6606 | 0 | 4.6606 | 4.6606 | 0 | #REF! |  | 4.6606 | 0 | 0 | #REF! | 67.5 | 54.6631 | 0 | 0 | 54.6631 | 12.8369 | 0 | 0
| 111 | LCP-190120 |  |  | 2019 | 2019-06-19 | 2019-06-19 | 2020-01-28 | 223 | 2020-12-17 | 2021-06-18 | [5 empty] | AME | STAFF |  | Carryover | 1670990 | PROJETO | HENRIQUE CARDOSO | CAP-PROT.SYST.RETROFITTING-MAIN SUBSTATI | Facilities Sustaining | CLSD | OK, FINALIZADO | OK | OK | OK | [5 empty] | #REF! | [6 empty] | 59.2008 | 18.8398 | 10.6448 |  | 85 | 8.5 | 93.5 | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 | 0 | 0 | #REF! | 85 | 69.8456 | 0 | 0 | 69.8456 | 15.1544 |  | 0
| 112 | LCP-190129 |  | 20/0031 | 2019 | 2019-07-10 | 2019-07-30 | 2020-06-02 | 308 | 2021-01-27 | 2021-07-29 | [5 empty] | AME | STAFF |  | Carryover | 1920845 | PROJETO | DIEGO RAGONHA | FIRE FIGHTING SYSTEM BUILDING 76 | EHS | CLSD | OK, FINALIZADO | OK | OK | OK | [5 empty] | #REF! | [6 empty] | 85.744 | 4.7415 | 0.59536 |  | 96.3 | 3 | 99.3 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 | 0 | 0 | #REF! | 96.3 | 86.3394 | 0 | 0 | 86.3394 | 9.9606 |  | 0
| 113 | LCP-190132 |  |  | 2019 | 2019-07-11 | 2019-08-02 | 2020-12-28 | 514 | 2021-01-30 | 2021-08-01 | [5 empty] | BRZ | STAFF |  | Carryover | 1883734 | PROJETO | RICARDO TEIXEIRA | VEHICLE DYNAMICS AREA (VDA) REPAVING | SAG | CLSD | OK, FINALIZADO | OK | OK | OK | [5 empty] | #REF! | [6 empty] | 23.0842 | 820.5369 | 699.3673 | 14.6 | 844.223 | 194.255 | 1038.478 | 18.6633 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 14.6 | 14.9609 |  | 3.7024 | [11 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 18.6633 | 0 | 18.6633 | 18.6633 | 0 | #REF! |  | 0 | 14.9609 | 3.7024 | #REF! | 844.2232 | 741.1147 | 0 | 0 | 741.1147 | 103.1084 | 0 | 0
| 114 | LCP-190138 |  |  | 2019 | 2019-07-11 | 2019-07-22 | 2019-11-28 | 129 | 2021-01-19 | 2021-07-21 | [5 empty] | BRZ | STAFF |  | Carryover | 1904716 | PROJETO | CHARLES BARBAN | WHEEL PULSE TRANSDUCERS - CWPTA | SAG | CLSD | OK, FINALIZADO | OK | OK | OK | [5 empty] | #REF! | [6 empty] | 15.1072 | 0 | 0 |  | 15.6 | 1.1 | 16.7 | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 | 0 | 0 | #REF! | 15.6 | 15.1072 | 0 | 0 | 15.1072 | 0.49278 |  | 0
| 115 | LCP-190140 |  |  | 2019 | 2019-07-12 | 2019-10-15 | 2021-01-05 | 448 | 2021-04-14 | 2021-10-14 | [5 empty] | MC |  |  | Carryover | 2272070 | PROJETO | RICARDO TEIXEIRA | UPGRADE RING 18" CUV IN MC ANCHIETA | SAG | CLSD | OK, FINALIZADO | OK | 2021-03-31 | OK | [5 empty] | #REF! | [6 empty] | 0 | 400 | 310.0503 | 2.9873 | 427.82 | 0 | 427.82 | 2.9714 | 0 | -1.1127 | 0 | 2.6313 | 1.2 | 1.4528 | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 2.9714 | 0 | 2.9714 | 2.9714 | 0 | #REF! |  | 2.9714 | 0 | 0 | #REF! | 427.8204 | 313.0217 | 0 | 0 | 313.0217 | 114.7987 | 0 | 0
| 116 | LCP-190142 |  | 19/0094 | 2019 | 2019-07-15 | 2019-08-23 | 2021-07-30 | 707 | 2021-02-20 | 2021-08-22 | SIM |  |  |  |  | AME | A | BANBURY | Carryover | 2082380 | PROJETO | GUSTAVO PARRAS | NEW OIL LINE SYDININI | Quality | CLSD | OK, FINALIZADO | OK | OK | OK | [5 empty] | #REF! | [6 empty] | 78.3839 | 542.417 | 360.2711 | 108.0915 | 616.41 | 0 | 616.41 | 128.455 | 15 | 18.0915 | 10 | 29.0408 | 0 | 13.2556 | 10 | 32.3148 | 0 | 7.9704 | 7.5651 | 8.7999 | 15 | 18.9819 | [11 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 128.455 | 0 | 128.455 | 128.455 | 0 | #REF! |  | 60.3879 | 49.0851 | 18.9819 | #REF! | 616.4098 | 567.11 | 0 | 0 | 567.11 | 49.2998 | 0 | 0
| 117 | LCP-190143 |  | 19/0045 | 2019 | 2019-07-15 | 2019-07-30 | 2019-11-28 | 121 | 2021-01-27 | 2021-07-29 | [5 empty] | RET | STAFF |  | Carryover | 1920524 | PROJETO | CHARLES BARBAN | MOLD CLEAN S.B.O | Facilities Sustaining | CLSD | OK, FINALIZADO | OK | OK | OK | [5 empty] | #REF! | [6 empty] | 20.1496 | 0 | 0 |  | 67 | 0 | 67 | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 | 0 | 0 | #REF! | 67 | 20.1496 | 0 | 0 | 20.1496 | 46.8504 |  | 0
| 118 | LCP-190144 |  | 20/0007 | 2019 | 2019-07-11 | 2019-07-30 | 2021-01-05 | 525 | 2021-01-27 | 2021-07-29 | [5 empty] | AME | A | CALANDRA | Carryover | 1917345 | PROJETO | DIEGO CASTANHARO | WIRE CALENDER EDGE TRIMMING DEVICE | Quality | CLSD | OK, FINALIZADO | OK | OK | OK | [5 empty] | #REF! | [6 empty] | 1.568 | 88.9 | 0 | -1.568 | 90.5 | 0 | 90.5 | -1.568 | 0 | -1.568 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | -1.568 | 0 | -1.568 | -1.568 | 0 | #REF! |  | -1.568 | 0 | 0 | #REF! | 90.5 | 0 | 0 | 0 | 0 | 90.5 | 0 | 0
| 119 | LCP-190149 |  | 19/0090 | 2019 | 2019-07-23 | 2019-08-21 | 2020-12-03 | 470 | 2021-02-18 | 2021-08-20 | [5 empty] | AME | B1 |  | Carryover | 1958617 | PROJETO | GUSTAVO PARRAS | B1 - UPGRADE HMI HF PLT2 | Facilities Sustaining | CLSD | OK, FINALIZADO | OK | OK | OK | Scope Change |  |  |  |  | #REF! | [6 empty] | 96.0455 | 61.2 | 36.8249 |  | 157.2 | 0 | 157.2 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 | 0 | 0 | #REF! | 157.2 | 132.8704 | 0 | 0 | 132.8704 | 24.3296 |  | 0
| 120 | LCP-190150 |  |  | 2019 | 2019-07-23 | 2019-08-26 |  | -1596.336 | 2021-02-23 | 2021-08-25 | SIM | SIM | SIM | XQ1/22 | BQ1/22 | AME | B1 | FINAL FINISH | Carryover | 1985371 | PROJETO | FABIO MORAES | B1 - UPGRADE PC-ETMS BALANCE AND FVM MACHINE | Facilities Sustaining | REL | Teste na FVM19 no dia 17. Se der certo, vai instalar nas demais maquinas PROBLEMA NO COMPUTADOR falha tela azul. Aguardando posição da Região - Allen Edmonds Material chegou no Brasil, mais só chegará na FAM em Novembro. | 2022-02-28 | 2022-01-31 | 2021-10-30 | Scope Change |  |  |  |  | #REF! | [6 empty] | 200.2526 | 90.8328 | 49.2516 | 45 | 304 | 0 | 304 | 34.4275 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 28.5328 | 0 |  |  | -0.17843 |  | 6.0731 | 10.4131 |  | 10.4131 |  | 10.4131 |  |  |  |  | 10.4131 | 10.4131 | [11 empty] | 0 | [12 empty] | 0 | 0 | 34.4275 | 0 | 44.8406 | 44.8406 | 0 | #REF! |  | 0 | 28.5328 | 5.8947 | #REF! | 304 | 283.9317 | 22.7381 | 0 | 306.6698 | -2.6698 | 0 | 10.4131
| 121 | LCP-190151 |  | 19/0095 | 2019 | 2019-07-23 | 2019-08-22 | 2020-03-24 | 215 | 2021-02-19 | 2021-08-21 | [5 empty] | AME | B1 |  | Carryover | 1959852 | PROJETO | GUSTAVO PARRAS | METAL DETECTOR IN APEXER (NAKATA) | Quality | CLSD | OK, FINALIZADO | OK | OK | OK | [5 empty] | #REF! | [6 empty] | 28.8596 | 48.3056 | 11.837 |  | 79 | 3 | 82 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 | 0 | 0 | #REF! | 79 | 40.6966 | 0 | 0 | 40.6966 | 38.3034 |  | 0
| 122 | LCP-190157 |  |  | 2019 | 2019-07-23 | 2019-07-24 | 2019-07-24 | 0 | 2021-01-21 | 2021-07-23 | [5 empty] | AME | B2 |  | Carryover | 2098754 | PROJETO | FABIO MORAES | TRANSFER O'RING NGTT'S #01,02,04,05 AND 06 | Quality | CLSD | BUDGET CANCELADO, REFEITO P/ 02 MAQ. LCP-190159 | OK | OK | OK | [5 empty] | #REF! | [6 empty] | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| 123 | LCP-190159 |  |  | 2019 | 2019-07-23 | 2019-11-07 | 2021-02-10 | 461 | 2021-05-07 | 2021-11-06 | [5 empty] | AME | B2 | CONSTRUÇÃO | Carryover | 2368366 | PROJETO | FABIO MORAES | (02) TRANSFER ORING NGTTS & MONO CUTTER IN ANGLE | Quality | CLSD | OK, FINALIZADO | OK | OK | OK |  |  |  | ICP-190047 |  | #REF! | [6 empty] | 0 | 0 | 180.0292 | 9.1654 | 298.96 | 0 | 298.96 | -0.33455 | 0 | -0.33455 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | -0.33455 | 0 | -0.33455 | -0.33455 | 0 | #REF! |  | -0.33455 | 0 | 0 | #REF! | 298.962 | 179.6947 | 0 | 0 | 179.6947 | 119.2673 | 0 | 0
| 124 | LCP-190173 |  |  | 2019 | 2019-08-15 | 2019-08-29 | 2020-03-24 | 208 | 2021-02-26 | 2021-08-28 | [5 empty] | BRZ | STAFF |  | Carryover | 2097632 | PROJETO | PATRICIA | DOR PROJECT IC TRANSPORTS | SAG | CLSD | OK, FINALIZADO | OK | OK | OK | [5 empty] | #REF! | [6 empty] | 137.6529 | 0 | 13.678 |  | 180.02 | 0 | 180.02 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 | 0 | 0 | #REF! | 180.0195 | 151.3309 | 0 | 0 | 151.3309 | 28.6886 |  | 0
| 125 | LCP-190178 |  | 19/0106 | 2019 | 2019-08-21 | 2019-09-07 | 2020-01-23 | 138 | 2021-03-07 | 2021-09-06 | [5 empty] | AME | A |  | Carryover | 2112948 | PROJETO | DIEGO CASTANHARO | REPLACE AND UPGRADE OF ROLLS IN WIRE CALENDER | Facilities Sustaining | CLSD | OK, FINALIZADO | OK | OK | OK | Scope Change |  |  |  |  | #REF! | [6 empty] | 420.0987 | -30.3299 | -25.0477 |  | 445.88 | 26.32 | 472.2 | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 | 0 | 0 | #REF! | 445.883 | 395.051 | 0 | 0 | 395.051 | 50.832 |  | 0
| 126 | LCP-190179 |  | N/A | 2019 | 2019-09-06 | 2019-09-07 | 2019-09-07 | 0 | 2021-03-07 | 2021-09-06 | [5 empty] | AME | A |  | Carryover |  | PROJETO | DIEGO CASTANHARO | GUM CAL#01 ROLL REPLACEMENT | Quality | CLSD | BUDGET CANCELADO, SUBSTITUIDO PELO LCP-190190 | OK | OK | OK | [5 empty] | #REF! | [6 empty] | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 | 0 | 0 | #REF! | [7 empty] | 0
| 127 | LCP-190184 |  | 20/0008 | 2019 | 2019-08-12 | 2020-01-03 | 2021-01-04 | 367 | 2021-07-03 | 2022-01-02 | [5 empty] | AME | A |  | Carryover | 2422247 | PROJETO | DIEGO CASTANHARO | WIRE CALENDER WIGWAG FEED CONVEYOR | Quality | CLSD | OK, FINALIZADO | OK | OK | OK | [5 empty] | #REF! | [6 empty] | 0 | 132.4 | 0 |  | 132.4 | 0 | 132.4 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 | 0 | 0 | #REF! | 132.4 | 0 | 0 | 0 | 0 | 132.4 |  | 0
| 128 | LCP-190186 |  | 20/0037 | 2019 | 2019-09-05 | 2019-10-09 | 2021-03-31 | 539 | 2021-04-08 | 2021-10-08 | [5 empty] | SAO | STAFF |  | Carryover | 2238197 | PROJETO | CHARLES BARBAN | CORSAIR Project | SAG | CLSD | OK, FINALIZADO | OK | OK | OK |  |  |  | ICP-190041 |  | #REF! | [6 empty] | 50.3685 | 1358.2448 | 1240.3935 | 96.5893 | 1490 | 1135 | 2625 | 60.19 | 10 | 2.5893 | 28 | 27.1386 | 30 | 23.7407 | 9 | 3.6524 | 5 | -0.18157 | 3 | 3.2505 | [13 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 60.19 | 0 | 60.19 | 60.19 | 0 | #REF! |  | 53.4687 | 6.7213 | 0 | #REF! | 1490 | 1350.9521 | 0 | 0 | 1350.9521 | 139.0479 | 0 | 0
| 129 | LCP-190187 |  | N/A | 2019 | 2019-09-05 | 2019-09-06 | 2019-09-06 | 0 | 2021-03-06 | 2021-09-05 | [5 empty] | AME | A |  | Carryover | 2359750 | PROJETO | DIEGO CASTANHARO | ADDITIONAL DS3 BEAD CHUCK | Quality | CLSD | PROJETO CANCELADO - REPROVADO POR FINANÇAS (QUALIDADE ANALISAR O PROJETO) | OK | OK | OK | [5 empty] | #REF! | [6 empty] | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| 130 | LCP-190188 |  |  | 2019 | 2019-09-17 | 2019-10-10 | 2020-01-09 | 91 | 2021-04-09 | 2021-10-09 | [5 empty] | SAO | STAFF |  | Carryover | 2266751 | PROJETO | CHARLES BARBAN | SAO - ANNUAL MISCELLANEOUS <50K ALL PLANTS | SAG | CLSD | OK, FINALIZADO | OK | OK | OK | [5 empty] | #REF! | [6 empty] | 0 | 50 | 9.4718 |  | 10.5 | 0 | 10.5 | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 | 0 | 0 | #REF! | 10.99 | 9.4718 | 0 | 0 | 9.4718 | 1.5182 |  | 0
| 131 | LCP-190198 |  | N/A | 2019 | 2019-09-17 | 2019-09-18 | 2019-09-18 | 0 | 2021-03-18 | 2021-09-17 | [5 empty] | AME | A |  | Carryover |  | PROJETO | DIEGO CASTANHARO | REPLACEMENT OF LINNER AND SCREW EXTRUDER MIXER#01 | Quality | CLSD | PROJETO CANCELADO - MOTIVO: ABAIXO DE US$ 50K (SEGURADO PELO LANZA) | OK | OK | OK | [5 empty] | #REF! | [6 empty] | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| 132 | LCP-190199 |  |  | 2019 | 2019-09-18 | 2019-10-24 | 2021-01-05 | 439 | 2021-04-23 | 2021-10-23 | [5 empty] | BRZ | STAFF |  | Carryover | 2272176 | PROJETO | DIEGO RAGONHA | MOBILE DOCK LEVELER FOR NEW WAREHOUSE | SAG | CLSD | OK, FINALIZADO | OK | OK | OK | [5 empty] | #REF! | [6 empty] | 26.2972 | 0 | 11.1645 | 5.0496 | 46 | 0 | 46 | 4.9531 | 0 | 5.0496 | 0 | -0.09653 | 0 | 0 | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 4.9531 | 0 | 4.9531 | 4.9531 | 0 | #REF! |  | 4.9531 | 0 | 0 | #REF! | 46.003 | 42.4147 | 0 | 0 | 42.4147 | 3.5882 | 0 | 0
| 133 | LCP-190202 |  | 20/0103 | 2019 | 2019-09-24 | 2019-12-13 | 2021-09-27 | 654 | 2021-06-12 | 2021-12-12 | SIM | SIM | SIM | AQ4/21 |  | AME | A | BANBURY | Carryover | 2347067 | PROJETO | GUSTAVO PARRAS | MIXER#6 BODY REPLACEMENT | Facilities Sustaining | CLSD | OK, FINALIZADO | OK | 2021-07-31 | 2021-10-31 |  |  |  | ICP-200033 |  | #REF! | NÃO POSSUI RISCOS | NÃO POSSUI RISCOS | NÃO POSSUI RISCOS | N/A | N/A | N/A | 0 | 1431.3 | 916.5256 | 456.9338 | 1431.34 | 38 | 1469.34 | 468.7653 | 270 | 211.9338 | 10 | 40.8434 | 0 | 2.5068 | 7 | 30.1451 | 0 | 29.079 | 0 | 29.2908 | 29.7 | 87.7381 | 9.1 | 20.9149 | 9 | 14.8828 | 1.2 | 1.4306 | [5 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 468.7653 | 0 | 468.7653 | 468.7653 | 0 | #REF! |  | 255.284 | 88.5149 | 123.5359 | #REF! | 1431.34 | 1385.2909 | 0 | 0 | 1385.2909 | 46.0491 | 0 | 0
| 134 | LCP-190203 |  | 20/0045 | 2019 | 2019-09-24 | 2019-11-05 | 2021-01-28 | 450 | 2021-05-05 | 2021-11-04 | [5 empty] | AME | UTIL | CASA FORÇA | Carryover | 2382119 | PROJETO | HENRIQUE CARDOSO | SAFETY SYSTEM RIVER PUMP AREA | EHS | CLSD | OK, FINALIZADO | OK | OK | OK | [5 empty] | #REF! | [6 empty] | 29.6714 | 26.3109 | 35.2954 | 0.53947 | 72.1 | 0 | 72.1 | 0.53947 | 0.7 | 0.53947 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0.53947 | 0 | 0.53947 | 0.53947 | 0 | #REF! |  | 0.53947 | 0 | 0 | #REF! | 72.1 | 65.5063 | 0 | 0 | 65.5063 | 6.5937 | 0 | 0
| 135 | LCP-190204 |  | 19/0118 | 2019 | 2019-09-25 | 2019-11-18 |  | -1515.336 | 2021-05-18 | 2021-11-17 |  | SIM | SIM | AQ4/21 |  | AME | B1 | FINAL FINISH | Carryover | 2352674 | PROJETO | RICARDO TEIXEIRA | INFLATION TESTING MACHINE | Quality | CLSD | OK, FINALIZADO | OK | 2021-07-31 | 2021-09-30 |  |  |  | ICP-200001 |  | #REF! | [6 empty] | 0 | 131.6 | 99.4594 | 24.4993 | 131.6 | 0 | 131.6 | 30.7639 | 10 | 4.4993 | 4 | 0.39062 | 0 | 0.17464 | 2 | 1.8841 | 3 | 13.1693 | 0 | 0.56834 | 9.252 |  | 9.252 | 10.0775 |  | -0.09676 |  | 0.09272 |  | 0.00404 |  |  |  | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 30.7639 | 0 | 30.7639 | 30.7598 | 0.00404 | #REF! |  | 5.0646 | 15.6218 | 9.9807 | #REF! | 131.6 | 130.2233 | 0 | 0 | 130.2233 | 1.3767 | 0 | 0
| 136 | LCP-190208 |  | 19/0117 | 2019 | 2019-10-01 | 2019-12-03 | 2021-06-30 | 575 | 2021-06-02 | 2021-12-02 | [5 empty] | AME | B1 | FINAL FINISH | Carryover | 2340229 | PROJETO | GUSTAVO PARRAS | AME- (1) BALANCE MACHINE MARKER (DOWN SIDE) | Quality | CLSD | OK, FINALIZADO | OK | 2021-06-30 | OK |  |  |  | ICP-190053 |  | #REF! | [6 empty] | 0 | 560.5 | 441.7209 | 29.2325 | 560.5 | 0 | 560.5 | 83.7061 | 15 | 2.3387 | 7.8938 | 10.1102 | 8 | 17.8083 | 2 | 6.6119 | 5 | 16.5136 | 5 | 10.202 | 5 | 6.5673 | [5 empty] | 13.554 | [5 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 83.7061 | 0 | 83.7061 | 83.7061 | 0 | #REF! |  | 30.2573 | 33.3276 | 6.5673 | #REF! | 560.5 | 525.4271 | 0 | 0 | 525.4271 | 35.0729 | 0 | 0
| 139 | LCP-190225 |  |  | 2019 | 2019-10-14 | 2019-11-18 | 2019-11-18 | 0 | 2021-05-18 | 2021-11-17 | [5 empty] | BRZ | B1 |  | Carryover | 2398291 | PROJETO | RICARDO TEIXEIRA | BLUE RACKS FOR MRT TIRES | Facilities Sustaining | CLSD | BUDGET CANCELADO: DECISÃO FOI NÃO COMPRAR MAIS OS RACKS MRT | OK | OK | OK | [5 empty] | #REF! | [6 empty] | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 | 0 | 0 | #REF! | 140 | 0 | 0 | 0 | 0 | 140 |  | 0
| 140 | LCP-190227 |  |  | 2019 | 2019-10-14 | 2019-10-15 | 2019-10-15 | 0 | 2021-04-14 | 2021-10-14 | [5 empty] | AME | B1 |  | Carryover |  | PROJETO | RICARDO TEIXEIRA | UPGRADE (54) RTD CARD CONSUMER CURING PRESSES | Facilities Sustaining | CLSD | PROJETO CANCELADO MOTIVO: O VALOR UNITARIO É ABAIXO DE US$ 5K | OK | OK | OK | [5 empty] | #REF! | [6 empty] | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| 141 | LCP-190228 |  |  | 2019 | 2019-10-14 | 2019-10-15 | 2019-10-15 | 0 | 2021-04-14 | 2021-10-14 | [5 empty] | AME | B2 |  | Carryover | 2422075 | PROJETO | HUELITON MAGNANI | UPGRADE PANELVIEW MRT CURING PRESS | Facilities Sustaining | CLSD | PROJETO CANCELADO CANCELADO DEVIDO AO ALTO TEMPO DE APROVAÇÃO (NÃO INVESTE EM 2019) | OK | OK | OK | [5 empty] | #REF! | [6 empty] | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| 142 | LCP-190229 |  | 20/0051 | 2019 | 2019-10-14 | 2019-11-02 | 2021-01-05 | 430 | 2021-05-02 | 2021-11-01 | [5 empty] | AME | B2 | VULCANIZAÇÃO | Carryover | 2368666 | PROJETO | HUELITON MAGNANI | UPGRADE TYLOR SYSTEM IN MRT CURING PRESSES | Facilities Sustaining | CLSD | FASE 1 - IMPLEMENTAÇÃO EM 2 MÁQUINAS PQ13/14 e PQ19/20 | OK | 2021-03-31 | OK | [5 empty] | #REF! | [6 empty] | 0 | 0 | 96.4938 | 6 | 120 | 0 | 120 | 3.8178 | 0 | 0 | 6 |  | 4 | 3.8178 | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 3.8178 | 0 | 3.8178 | 3.8178 | 0 | #REF! |  | 3.8178 | 0 | 0 | #REF! | 120 | 100.3116 | 0 | 0 | 100.3116 | 19.6884 | 0 | 0
| 143 | LCP-190231 |  | 20/0002 | 2019 | 2019-10-14 | 2019-12-05 | 2021-03-30 | 481 | 2021-06-04 | 2021-12-04 | [5 empty] | AME | A |  | Carryover | 2421971 | PROJETO | DIEGO CASTANHARO | HOTFORMER UPGRADE LINNER AND SCREW | Facilities Sustaining | CLSD | OK, FINALIZADO | OK | 2021-03-30 | OK | [5 empty] | #REF! | [6 empty] | 150.1974 | 74.8 | 47.0905 | 18 | 225 | 0 | 225 | 0 | 0 | 0 | 0 |  | 2 | 0 | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 | 0 | 0 | #REF! | 225 | 197.2879 | 0 | 0 | 197.2879 | 27.7121 | 0 | 0
| 144 | LCP-190232 |  |  | 2019 | 2019-10-14 | 2019-10-15 | 2019-10-15 | 0 | 2021-04-14 | 2021-10-14 | [5 empty] | AME | B2 |  | Carryover | 2380800 | PROJETO | RICARDO TEIXEIRA | NEW CARS BEAR TRAP FOR CONSUMER TIRES | Facilities Sustaining | CLSD | PROJETO CANCELADO REJEITADO POR FINANÇÃO - NÃO É CAPITAL | OK | OK | OK | [5 empty] | #REF! | [6 empty] | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| 145 | LCP-190233 |  |  | 2019 | 2019-10-14 | 2019-10-15 | 2019-10-15 | 0 | 2021-04-14 | 2021-10-14 | [5 empty] | AME | B1 |  | Carryover | 2380886 | PROJETO | RICARDO TEIXEIRA | UPGRADE LASER MARKER TIRE BUILD MACHINE | Facilities Sustaining | CLSD | PROJETO CANCELADO REPROVADO PELA REGIÃO - MAURICIO DENARDO | OK | OK | OK | [5 empty] | #REF! | [6 empty] | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| 146 | LCP-190234 |  | 19/0061 | 2019 | 2019-10-14 | 2019-10-15 | 2019-10-15 | 0 | 2021-04-14 | 2021-10-14 | [5 empty] | AME | A |  | Carryover | 2380972 | PROJETO | DIEGO CASTANHARO | UPGRADE OF CUSHION DRIVES IN DUPLEX | Facilities Sustaining | CLSD | PROJETO CANCELADO MOTIVO: MATERIAL NÃO CHEGA EM 2019 - NÃO TERA GASTO EM 2019 | OK | OK | OK | [5 empty] | #REF! | [6 empty] | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 | 0 | 0 | #REF! | [7 empty] | 0
| 147 | LCP-190235 |  | N/A | 2019 | 2019-10-14 | 2019-10-15 | 2019-10-15 | 0 | 2021-04-14 | 2021-10-14 | [5 empty] | AME | A |  | Carryover | 2422159 | PROJETO | GUSTAVO PARRAS | UPGRADE OF CUSHION MILL DRIVES | Facilities Sustaining | CLSD | BUDGET CANCELADO | OK | OK | OK | [5 empty] | #REF! | [6 empty] | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| 148 | LCP-190237 |  | N/A | 2019 | 2019-10-14 | 2019-10-15 | 2019-10-15 | 0 | 2021-04-14 | 2021-10-14 | [5 empty] | AME | A |  | Carryover | 2381301 | PROJETO | DIEGO CASTANHARO | UPGRADE OF LINNER AND SCREW EXTRUDER MIXER#1 | Facilities Sustaining | CLSD | PROJETO CANCELADO BUDGET REJEITADO POR ELAINE LORENZI, EM 01/11/19 | OK | OK | OK | [5 empty] | #REF! | [6 empty] | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| 149 | LCP-190238 |  | N/A | 2019 | 2019-10-14 | 2019-10-15 | 2019-10-15 | 0 | 2021-04-14 | 2021-10-14 | [5 empty] | AME | A |  | Carryover | 2381471 | PROJETO | DIEGO CASTANHARO | UPGRADE OF MIXER#5 EXTRUDER DRIVES | Facilities Sustaining | CLSD | PROJETO CANCELADO MOTIVO: O MATERIAL NÃO CHEGA EM 2019 (NÃO TERA GASTO EM 2019) | OK | OK | OK | [5 empty] | #REF! | [6 empty] | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 | 0 | 0 | #REF! | [7 empty] | 0
| 150 | LCP-190239 |  |  | 2019 | 2019-10-14 | 2019-10-15 | 2019-10-15 | 0 | 2021-04-14 | 2021-10-14 | [5 empty] | AME | B1 |  | Carryover |  | PROJETO | RICARDO TEIXEIRA | UPGRADE PANELVIEW TIRE BUILD MACHINE | Facilities Sustaining | CLSD | PROJETO CANCELADO MOTIVO: NÃO TERA GASTO EM 2019 = item abaixo de US$ 5 K | OK | OK | OK | [5 empty] | #REF! | [6 empty] | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| 151 | LCP-190251 |  |  | 2019 | 2019-11-28 | 2019-12-17 | 2019-12-17 | 0 | 2021-06-16 | 2021-12-16 | [5 empty] | BRZ | STAFF |  | Carryover | 2462310 | PROJETO | PATRICIA | UMBRELLA PROJECT CONTROL MAX | Productivity | CLSD | PROJETO CANCELADO DECISÃO DO TIME DE INOVAÇÀO (PATRICIA) CANCELAMENTO DO PROJETO | OK | OK | OK | [5 empty] | #REF! | [6 empty] | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 | 0 | 0 | #REF! | 55.65 | 0 | 0 | 0 | 0 | 55.65 |  | 0
| 152 | LCP-200001 |  | 19/0119 | 2019 | 2019-09-06 | 2019-12-10 | 2021-07-27 | 595 | 2021-06-09 | 2021-12-09 | SIM | SIM | SIM | AQ4/21 |  | AME | A | CALANDRA | Carryover | 2357919 | PROJETO | DIEGO CASTANHARO | AME-REPL & UPG OF ROLLS IN CAL3R | Facilities Sustaining | CLSD | OK, FINALIZADO | OK | 2021-11-30 | 2021-10-31 | [5 empty] | #REF! | NÃO POSSUI RISCOS | NÃO POSSUI RISCOS | NÃO POSSUI RISCOS | N/A | N/A | N/A | 0 | 1209 | 273.3232 | 814.2 | 1208.957 | 24.078 | 1233.035 | 807.6703 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 785.8603 | 0 | 1.5434 |  | -0.05022 | 4 |  |  | 1.0002 |  |  | 19.4 | 19.3167 |  |  |  | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 807.6703 | 0 | 807.6703 | 807.7536 | -0.08332 | #REF! |  | 0 | 787.4036 | 0.94994 | #REF! | 1208.957 | 1080.9935 | 0 | 0 | 1080.9935 | 127.9635 | 0 | 0
| 153 | LCP-200008 |  | 19/0109 | 2019 | 2019-09-06 | 2019-11-06 | 2021-11-29 | 754 | 2021-05-06 | 2021-11-05 | SIM | SIM | SIM | AQ4/21 |  | AME | A | CALANDRA | Carryover | 2358387 | PROJETO | DIEGO CASTANHARO | AME-REPL & UPG OF ROLLS IN CAL4R1 | Facilities Sustaining | CLSD | OK, FINALIZADO | OK | 2021-12-31 | 2021-09-30 | [5 empty] | #REF! | RISCO DO MATERIAL NÃO SER ENTREGUE NO MÊS ATUAL, SENDO ENTREGUE POSTERIORMENTE | 8240433863 (Rolo Comerio Ercole) | NÃO POSSUI RISCOS | 25.150,00 EUR | Está no Porto. Será requisitado em Novembro |  | 2.1484 | 953.7 | 203.1832 | 199.0418 | 955.782 | 48.156 | 1003.938 | 122.8646 | 0 | 1.4418 | 0 | 1.3903 | 0 | 0 | 0 | 22.3798 | 0 | 2.1657 | 0 | 3.0792 |  | 1.5587 | [6 empty] | 35 | 91.1804 |  | -0.33136 | -0.33136 | 0 | [12 empty] | 0 | [12 empty] | 0.33136 | 0 | 123.196 | -0.33136 | 122.8646 | 67.0155 | 55.8491 | #REF! | Item sendo comprado pelo Estoque | 2.8321 | 27.6247 | 1.5587 | #REF! | 955.782 | 328.1963 | 0 | 0 | 328.1963 | 627.5857 | 0 | 0
| 154 | LCP-200009 |  | 20/0001 | 2019 | 2019-09-06 | 2019-12-03 |  | -1499.336 | 2021-06-02 | 2021-12-02 | SIM | SIM | SIM | XQ3/22 | DQ3/22 | AME | A | CALANDRA | Carryover | 2357839 | PROJETO | DIEGO CASTANHARO | AME-REPL & UPG OF ROLLS IN CAL4R2 | Facilities Sustaining | REL | -5K : Rolo trincado, sem reparo, será devolvido ao estoque e será comprado um novo. 35K em 2022 chegará 1 novo rolo 3 TROCAS 2022: Falta trocar 03 rolos: Aguardando parada de máquina para troca de 01 rolo, após a troca desse será enviado para retrofit e retorna para outra posição assim funciona para proximo rolo. Tempo de máquina para troca 24hrs, tempo retrofit, 30 dias cada rolo. | 2022-07-31 | 2022-06-30 | 2021-10-31 | [5 empty] | #REF! | NÃO POSSUI RISCOS | NÃO POSSUI RISCOS | NÃO POSSUI RISCOS | N/A | N/A | N/A | 53.2412 | 815.2937 | 56.6968 | 261 | 864.938 | 48.156 | 913.094 | 126.6843 | 0 | 0 | 0 | 19.9 | 116 | 60.7238 | 0 | 1.7516 | 0 | 20.4053 | 18.371 | 1.1873 | 17 | 22.4661 |  | 0.45424 |  | 2.1714 | -5.5 | 0.71102 | -5.5 | -4.6119 |  | 1.5253 | 1.5253 | 33.5 |  |  |  | 33.5 | [8 empty] | 0 | [12 empty] | -1.5253 | 0 | 125.1589 | 1.5253 | 160.1843 | 159.2708 | 0.91346 | #REF! |  | 80.6238 | 23.3442 | 25.0918 | #REF! | 864.938 | 236.6222 | 53.7122 | 0 | 290.3345 | 574.6035 | 35 | -1.5
| 156 | LCP-200023 |  |  | 2019 | 2019-12-11 | 2020-02-24 | 2021-09-24 | 578 | 2021-08-24 | 2022-02-23 |  | SIM |  | BQ1/22 |  | AME | B2 | FINAL FINISH | Carryover | 2729964 | PROJETO | FABIO MORAES | UPGRADE KOKUSAI #01 | Facilities Sustaining | TECO | 17k serviço Spindle Ao receber a Invoice o Budget será reaberto o TECO, para ajudar o PO local Pode dar TECO - Pedidos que Não serao usados já foram cancelados Solicitado retirada do TECO no dia 22/10 para ajustes no PO local de importação, TECO aprovado para retirada em 25/10 e retirado em 26/10 PO local ajustado e TECO retornado no mesmo dia (26/10) | OK | 2021-12-31 | 2021-12-31 | Scope Change | 26/05/21 - Spindle replacement Machine upgrade start-up Kokusai - comissionamennto de viagem e custo adicional COVID-19 | 9.76% | ICP-200008 |  | #REF! | [6 empty] | 0 | 300 | 354.8465 | 86 | 571.5185 | 5.45 | 576.9685 | 214.5628 | 0 | 11.2417 | 0 | 6.9047 | 0 | 12.376 | 0 | 11.7996 | 0 | 16.5105 | 0 | 9.9054 |  | 7.0549 | 36 | 40.676 |  | 0.22431 | 0 | 39.2284 | 23.7 | 57.756 |  | 0.88539 | 0.88539 | 16.1 | 16.1 | [11 empty] | 0 | [12 empty] | -0.88539 | 0 | 213.6774 | 0.88539 | 230.6628 | 196.6214 | 34.0414 | #REF! | 9K de impostos + 17k de M.O (via ICP) | 30.5224 | 38.2155 | 47.9551 | #REF! | 571.4485 | 569.4093 | 0 | 0 | 569.4093 | 2.0392 | 0 | 16.1
| 157 | LCP-200026 |  |  | 2020 | 2020-01-07 | 2020-02-06 | 2020-12-31 | 329 | 2021-08-06 | 2022-02-05 | [5 empty] | AME | STAFF | ENGENHARIA | Carryover | 2657378 | PROJETO | ANDERSON BASSO | AME-MISCELANEOUS QUARTELY 2020 | Facilities Sustaining | CLSD | OK, FINALIZADO | OK | OK | OK | [5 empty] | #REF! | [6 empty] | 0 | 1000 | 821.016 | 37.937 | 1000 |  | 1000 | 29.4657 | 40 | 3.6549 | 34.2821 | 20.7212 | 4.5 | 5.0895 | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 29.4657 | 0 | 29.4657 | 29.4657 | 0 | #REF! |  | 29.4657 | 0 | 0 | #REF! | 1000 | 850.4817 | 0 | 0 | 850.4817 | 149.5183 | 0 | 0
| 158 | LCP-200028 |  |  | 2020 | 2020-01-08 | 2020-01-28 | 2020-12-28 | 335 | 2021-07-28 | 2022-01-27 | [5 empty] | AME | B2 | FINAL FINISH | Carryover | 2669295 | PROJETO | FABIO MORAES | REPLACEMENT OF RING IN KOKUSAI | Facilities Sustaining | CLSD | OK, FINALIZADO | OK | OK | OK | Overrun |  | 4.2% |  |  | #REF! | [6 empty] | 0 | 299.6 | 284.9588 | -0.55757 | 312.5526 |  | 312.5526 | -0.55757 | 0 | -0.55757 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | -0.55757 | 0 | -0.55757 | -0.55757 | 0 | #REF! |  | -0.55757 | 0 | 0 | #REF! | 312.5526 | 284.4012 | 0 | 0 | 284.4012 | 28.1514 | 0 | 0
| 159 | LCP-200030 |  | 20/007 | 2020 | 2020-01-15 | 2020-02-26 | 2020-11-24 | 272 | 2021-08-26 | 2022-02-25 | [5 empty] | AME | A |  | Carryover | 2732555 | PROJETO | DIEGO CASTANHARO | REPL OF ACCELERATOR TUBE - EBP SYSTEM FOR CAL3R | Facilities Sustaining | CLSD | OK, FINALIZADO | OK | OK | OK | Scope Change | 28/09/21 - Adicional 2 semanas de serviço tecnico. Retrablaho e neutralização de radioatividade. Impostoso. |  |  |  | #REF! | [6 empty] | 0 | 302.2 | 355.3152 |  | 372.819 |  | 372.819 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 | 0 | 0 | #REF! | 372.819 | 355.3152 | 0 | 0 | 355.3152 | 17.5038 |  | 0
| 160 | LCP-200037 |  | 20/0010 | 2020 | 2020-01-07 | 2020-01-28 | 2020-12-28 | 335 | 2021-07-28 | 2022-01-27 | [5 empty] | AME | A |  | Carryover | 2668149 | PROJETO | DIEGO CASTANHARO | REPLACE OF ROLLS IN HOTFORMER | Facilities Sustaining | CLSD | OK, FINALIZADO | OK | OK | OK | [5 empty] | #REF! | [6 empty] | 0 | 341.866 | 225.7206 |  | 341.866 |  | 341.866 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 | 0 | 0 | #REF! | 341.866 | 225.7206 | 0 | 0 | 225.7206 | 116.1454 |  | 0
| 162 | LCP-200076 |  | 20/0083 | 2020 | 2020-02-28 | 2020-09-08 |  | -1221.336 | 2022-03-09 | 2022-09-08 |  | SIM |  | BQ1/22 |  | AME | A | CALANDRA | Carryover | 2807147 | PROJETO | DIEGO CASTANHARO | HOTFORMER UPG LINNER AND SCREW STATIONS #04 | Facilities Sustaining | REL | Instalação irá aguardar definição da Manutenção. Materiais irão chegar no dia 23/12 | 2022-01-30 | 2021-12-31 | 2022-07-31 | Overrun | Devido os impostos creditados nesse equipamento | 9.9% |  |  | #REF! | [6 empty] | 0 | 0 | 76.7486 | 64.375 | 158.2879 |  | 158.2879 | 75.5117 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 64.375 |  | 0 |  | 64.375 |  | 64.375 |  | 64.375 | 68.6325 | [5 empty] | 6.8791 | 6.8791 | 0 | [12 empty] | 0 | [12 empty] | -6.8791 | 0 | 68.6325 | 6.8791 | 75.5117 | 68.6325 | 6.8791 | #REF! | Item sendo comprado pelo Estoque | 0 | 0 | 68.6325 | #REF! | 158.2879 | 152.2603 | 0 | 0 | 152.2603 | 6.0276 | 0 | 0
| 164 | LCP-200092 |  |  | 2020 | 2020-01-01 | 2020-05-28 | 2021-11-26 | 547 | 2021-11-26 | 2022-05-28 |  | SIM | SIM | AQ4/21 |  | AME | A | CALANDRA | Carryover | 2897680 | PROJETO | FABIO MORAES | AME-METAL DETECTOR IN CAL 4R2 | Quality | CLSD | OK, FINALIZADO | OK | 2021-11-30 | 2022-03-31 | [5 empty] | #REF! | [6 empty] | 0 | 150 | 67.9718 | 170.1483 | 245 |  | 245 | 63.4378 | 0 | 17.3483 | 0 |  | 12.8 | 16.5898 | 0 | 1.4282 | 5.9 | 6.4663 | 10 |  | 10 |  | 10 |  |  | 10.6393 |  |  |  | 9.8568 |  | 1.1092 | 1.1092 | 0 | [12 empty] | 0 | [12 empty] | -1.1092 | 0 | 62.3287 | 1.1092 | 63.4378 | 52.4719 | 10.966 | #REF! |  | 33.9381 | 7.8945 | 10.6393 | #REF! | 245 | 131.4096 | 0 | 0 | 131.4096 | 113.5904 | 0 | 0
| 165 | LCP-200115 |  |  | 2020 | 2020-07-29 | 2020-09-01 | 2020-12-28 | 118 | 2022-03-02 | 2022-09-01 | [5 empty] | AME | B2 | CONSTRUÇÃO | Carryover | 3078383 | PROJETO | FABIO MORAES | AME - BT DRUM WYKO UPGRADE | Facilities Sustaining | CLSD | OK, FINALIZADO | OK | 2021-01-31 | OK |  |  |  | ICP-200023 |  | #REF! | [7 empty] | 0 | 90.9321 | 1.063 | 99.994 |  | 99.994 | 1.0724 | 0 | 1.063 | 0 | -0.00948 | 0 | 0.01892 | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 1.0724 | 0 | 1.0724 | 1.0724 | 0 | #REF! |  | 1.0724 | 0 | 0 | #REF! | 99.994 | 92.0045 | 0 | 0 | 92.0045 | 7.9895 | 0 | 0
| 166 | LCP-200116 |  | 21/0008 | 2020 | 2020-07-29 | 2020-10-02 | 2021-12-27 | 451 | 2022-04-02 | 2022-10-02 | [5 empty] | RET | STAFF |  | Carryover | 3078126 | PROJETO | CHARLES BARBAN | SBO - UPGRADE PLC AUTOMAX EXTRUDER | Facilities Sustaining | CLSD | OK, FINALIZADO | OK | 2021-11-30 | 2022-08-31 | [5 empty] | #REF! | [7 empty] | 0 | 9.2556 | 473.6252 | 492.202 |  | 492.202 | 414.8113 | 0 | -0.87479 | 0 |  | 99.5 | 45.9035 | 150 | 212.2041 | 30 | 32.3192 | 40 | 40.6365 | 33 | 37.475 | 17.2 | 16.4248 | 5 | 5.1537 | 20 | 11.718 | 16.3 | 12.9044 |  | 0.94696 | 0.94696 | 0 | [12 empty] | 0 | [12 empty] | -0.94696 | 0 | 413.8644 | 0.94696 | 414.8113 | 417.26 | -2.4487 | #REF! |  | 45.0287 | 285.1597 | 59.0535 | #REF! | 492.22 | 424.067 | 0 | 0 | 424.067 | 68.1531 | 0 | 0
| 167 | LCP-200117 |  |  | 2020 | 2020-07-01 | 2020-09-01 | 2021-12-17 | 472 | 2022-03-02 | 2022-09-01 |  | SIM |  |  |  | AME | B2 | CONSTRUÇÃO | Carryover | 3079739 | PROJETO | FABIO MORAES | REWIND STATIONS MRT BUILD MACHINES | Facilities Sustaining | CLSD | OK, FINALIZADO | OK | 2021-10-31 | OK | Scope Change | Devido a diferença no valor do frete |  | ICP-200024 | B2 | #REF! | [7 empty] | 0 | 0 | 109.9179 | 109.9179 |  | 109.9179 | 109.6741 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0.25571 |  | 0.57756 | 76 | 0.42019 | 106 | 105.8296 | 2.6 |  | 2.5 |  |  | 2.5911 | 2.5911 | 0 | [12 empty] | 0 | [12 empty] | -2.5911 | 0 | 107.083 | 2.5911 | 109.6741 | 109.583 | 0.09105 | #REF! |  | 0 | 0.25571 | 106.8273 | #REF! | 109.9179 | 109.6741 | 0 | 0 | 109.6741 | 0.24379 | 0 | 0
| 169 | LCP-200120 |  |  | 2020 | 2020-07-01 | 2020-09-01 | 2020-11-24 | 84 | 2022-03-02 | 2022-09-01 | [5 empty] | MC |  |  | Carryover | 3084730 | PROJETO | DIEGO RAGONHA | UPGRADE TPMS SYSTEM MC GRAVATAI | SAG | CLSD | OK, FINALIZADO | OK | OK | OK | [5 empty] | #REF! | [6 empty] | 0 | 0 | 14.2041 |  | 18.2 |  | 18.2 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 | 0 | 0 | #REF! | 18.2 | 14.2041 | 0 | 0 | 14.2041 | 3.9959 |  | 0
| 170 | LCP-200121 |  |  | 2020 | 2020-07-29 | 2020-09-14 | 2021-02-10 | 149 | 2022-03-15 | 2022-09-14 | [5 empty] | AME | B2 | CONSTRUÇÃO | Carryover | 3106839 | PROJETO | FABIO MORAES | AME - PRODUCTIVITY MRT | Productivity | CLSD | OK, FINALIZADO | OK | 2021-02-28 | OK | [5 empty] | #REF! | [7 empty] | 0 | 32.0096 | 0.4243 | 98.6604 |  | 98.6604 | 0.4243 | 0 | 0.4243 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0.4243 | 0 | 0.4243 | 0.4243 | 0 | #REF! |  | 0.4243 | 0 | 0 | #REF! | 98.6604 | 32.4339 | 0 | 0 | 32.4339 | 66.2264 | 0 | 0
| 171 | LCP-200124 |  | 20/0068 | 2020 | 2020-08-01 | 2020-10-01 | 2021-05-26 | 237 | 2022-04-01 | 2022-10-01 | [5 empty] | AME | A | BANBURY | Carryover | 3101044 | PROJETO | DIEGO CASTANHARO | AME - BAMBURIES BATCH-OFF CRANES | EHS | CLSD | OK, FINALIZADO | OK | OK | OK | [5 empty] | #REF! | [7 empty] | 0 | 49.868 | 7.874 | 63.145 |  | 63.145 | 9.2855 | 1.7 | 0.87402 | 7 | 6.2154 | 0.7 | 1.4677 | 0 |  | 0.7 | 0.72833 | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 9.2855 | 0 | 9.2855 | 9.2855 | 0 | #REF! |  | 8.5571 | 0.72833 | 0 | #REF! | 63.145 | 59.1534 | 0 | 0 | 59.1534 | 3.9916 | 0 | 0
| 172 | LCP-200125 |  |  | 2020 | 2020-08-01 | 2020-09-01 | 2021-07-28 | 330 | 2022-03-02 | 2022-09-01 | [5 empty] | MC |  |  | Carryover | 3114884 | PROJETO | RICARDO TEIXEIRA | UPGRADE MICROPOISE BALANCE MACHINE ANCHIETA | SAG | CLSD | OK, FINALIZADO | OK | OK | OK | [5 empty] | #REF! | [7 empty] | 0 | 83.5518 | 89.9734 | 234.983 |  | 234.983 | 155.5111 | 0 | -18.9461 | 9.2 | 16.2795 | 0 | 0 | 0 |  | 79.114 | 115.3229 | 35 | 41.8798 |  | 0.69568 |  | 0.27935 | [9 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 155.5111 | 0 | 155.5111 | 155.5111 | 0 | #REF! |  | -2.6666 | 157.2027 | 0.97503 | #REF! | 239.983 | 239.0629 | 0 | 0 | 239.0629 | 0.92007 | 0 | 0
| 173 | LCP-200126 |  |  | 2020 | 2020-08-01 | 2020-09-02 | 2021-07-30 | 331 | 2022-03-03 | 2022-09-02 | [5 empty] | MC |  |  | Carryover | 3106596 | PROJETO | RICARDO TEIXEIRA | UPGRADE DRIVE VTW MICRIPOISE BALANCE MACHINE - GRAVATAI | SAG | TECO | Limpar Pedidos e Liberar para CLOSE | OK | 2021-06-30 | OK | [5 empty] | #REF! | PROJETO NÃO IRÁ ACONTECER, MICROPOISE COBROU HORAS A MENOS DO QUE FOI PREVISTO NO CONTRATO OBS.: INVOICE DANDO ENTRADA ENTRE FINANÇAS E FISCAL | NÃO POSSUI RISCOS | OK | N/A | N/A | N/A |  | 0 | 57.3454 | 160 | 361.223 |  | 361.223 | 290.5858 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 160 | 210.1429 | 70 | 76.7245 |  | -0.10788 | 7.5 | 1.0821 | 7.5 | 2.7441 | 4.7 | [6 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 290.5858 | 0 | 290.5858 | 290.5858 | 0 | #REF! |  | 0 | 286.8675 | 3.7183 | #REF! | 361.223 | 347.9312 | 8.0744 | 0 | 356.0057 | 5.2174 | 0 | 0
| 174 | LCP-200129 |  | 21/0014 | 2020 | 2020-08-01 | 2020-09-01 |  | -1228.336 | 2022-03-02 | 2022-09-01 | [5 empty] | AME | A | CALANDRA | Carryover | 3101444 | PROJETO | DIEGO CASTANHARO | AME - SAFETY UPGRADE BEADWINDER #03 | EHS | TECO | Projeto Sera Capitalizado só quando tudo for instalado. Falta instalar Drive | OK | 2021-12-31 | 2022-07-31 | [5 empty] | #REF! | [7 empty] | 0 | 44.5156 | 2.2372 | 53.661 |  | 53.661 | 5.4927 | 0 | 2.2372 | 0 |  | 4 | 3.2555 | 0 |  | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 5.4927 | 0 | 5.4927 | 5.4927 | 0 | #REF! |  | 5.4927 | 0 | 0 | #REF! | 53.961 | 50.0083 | 0 | 0 | 50.0083 | 3.9527 | 0 | 0
| 176 | LCP-200131 |  |  | 2020 | 2020-08-01 | 2020-09-02 |  | -1227.336 | 2022-03-03 | 2022-09-02 |  | SIM |  | BQ1/22 |  | AME | B2 | VULCANIZAÇÃO | Carryover | 3102230 | PROJETO | FABIO MORAES | AME - UPGRADE GENERAL PANEL CURING PRESSES MRT | Productivity | REL | Valor de Dezembro (parada de fabrica Natal e Ano novo) é referente a instalação do sistema de Nitrogenio, ar compimido e vapor. | 2022-02-28 | 2022-03-31 | 2022-07-31 | [5 empty] | #REF! | [7 empty] | 0 | 149.0797 | 274.2781 | 420.8898 | 15 | 435.8898 | 135.599 | 0 | 0.27812 | 0 | 4.3416 | 5.5 | 83.1902 | 0 | 1.9691 | 4 | 5.2252 | 0 | 0.40784 |  | 3.9674 |  | 1.4207 |  | 2.9633 |  |  |  |  | 34.5 | 31.8355 | 31.8355 | 1.8355 | 1.8355 | [11 empty] | 0 | [12 empty] | 2.6645 | 0 | 103.7635 | 31.8355 | 137.4345 | 171.7635 | -34.329 | #REF! |  | 87.8099 | 7.6021 | 8.3514 | #REF! | 420.8898 | 284.6787 | 1.8355 | 0 | 286.5142 | 134.3756 | 0 | 1.8355
| 177 | LCP-200137 |  |  | 2020 | 2020-08-01 | 2020-09-01 | 2021-06-01 | 273 | 2022-03-02 | 2022-09-01 | [5 empty] | AME | UTIL | CASA FORÇA | Carryover | 3113964 | PROJETO | HENRIQUE CARDOSO | UPGRADE XLE#7 AIR COMPRESSOR | Facilities Sustaining | CLSD | OK, FINALIZADO | OK | OK | OK | Overrun |  | 9.89% |  |  | #REF! | [7 empty] | 0 | 54.1526 | 10.9 | 65.72 |  | 65.72 | 10.4062 | 3 | 0 | 4.9 | 3.5657 | 6 | 7.3192 | 0 | -2.5725 | 2 | 2.1076 | 0 | -0.01369 | [13 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 10.4062 | 0 | 10.4062 | 10.4062 | 0 | #REF! |  | 10.8849 | -0.47863 | 0 | #REF! | 65.72 | 64.5588 | 0 | 0 | 64.5588 | 1.1612 | 0 | 0
| 178 | LCP-200142 |  |  | 2020 | 2020-08-01 | 2020-10-01 | 2021-07-30 | 302 | 2022-04-01 | 2022-10-01 | [5 empty] | MC |  |  | Carryover | 3114682 | PROJETO | RICARDO TEIXEIRA | BARCODE SYSTEM IN SEQUENCING AREA ANCHIETA | SAG | TECO | Limpar Pedidos e Liberar para CLOSE | OK | 2021-05-31 | OK | [5 empty] | #REF! | [7 empty] | 0 | 36.6059 | 1.0839 | 44.95 |  | 44.95 | 1.9303 | 0 | -0.9161 | 0 | 1.36 | 0.2 | 0.09496 | 1 | 0.84175 | 0.5 | 0.36594 | 0 | 0.18374 |  | -0.05605 |  | 0.05605 | [9 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 1.9303 | 0 | 1.9303 | 1.9303 | 0 | #REF! |  | 0.5389 | 1.3914 | 0 | #REF! | 44.95 | 38.5363 | 0.02351 | 0 | 38.5598 | 6.3902 | 0 | 0
| 179 | LCP-200145 |  | 20/0084 | 2020 | 2020-08-01 | 2020-09-08 | 2021-05-26 | 260 | 2022-03-09 | 2022-09-08 | [5 empty] | AME | A | CALANDRA | Carryover | 3145065 | PROJETO | DIEGO CASTANHARO | AUTOMATIC LOADING WIND UP – GUM CALENDER #2 | Productivity | CLSD | OK, FINALIZADO | OK | OK | OK | [5 empty] | #REF! | [7 empty] | 0 | 43.2493 | 20.26 | 71.727 |  | 71.727 | 27.9889 | 0 | 8.26 | 12 | 9.5318 | 3 | 7.5097 | 0 | 1.2751 | 1 | 1.4123 | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 27.9889 | 0 | 27.9889 | 27.9889 | 0 | #REF! |  | 25.3015 | 2.6875 | 0 | #REF! | 71.727 | 71.2382 | 0 | 0 | 71.2382 | 0.48881 | 0 | 0
| 180 | LCP-200149 |  | 20/0106 | 2020 | 2020-09-01 | 2020-10-08 |  | -1190.336 | 2022-04-08 | 2022-10-08 | [5 empty] | AME | FACIL | EHS | Carryover | 3178494 | PROJETO | HUELITON MAGNANI | MASTER PLAN SECURITY AMERICANA PLANT | EHS | REL | Iluminação Externa em Execução 2022 | 2022-04-30 | 2022-04-30 | 2022-08-31 | Overrun | Iidentificada uma oportunidade durante a instalação das cameras e precisou-se corrigir a iluminacao do local | 9.9% |  | Utilidades/Facilidades | #REF! | NÃO POSSUI RISCOS | NÃO POSSUI RISCOS | NÃO POSSUI RISCOS | N/A | N/A | N/A | 0 | 0 | 255.3602 | 96.7826 | 391.9397 |  | 391.9397 | 125.7456 | 5 | 27.7826 | 4 | 2.1976 | 5 | 13.9744 | 2 | 14.5689 | 2 | 4.3026 | 1 | 7.9262 | 5 | 6.2678 | 9 | 2.2143 | 12.6 | 1.7563 | 10.7 |  | 10.7 | 25.1374 | 15 | 19.6176 | 19.6176 | 5.5 |  |  | 3.4 | 2.1 | [8 empty] | 0 | [12 empty] | -4.6176 | 0 | 106.128 | 19.6176 | 131.2456 | 128.3906 | 2.855 | #REF! |  | 43.9545 | 26.7977 | 10.2383 | #REF! | 391.9397 | 381.1058 | 2.2543 | 0 | 383.3601 | 8.5796 | 0 | 5.5
| 181 | LCP-200159 | N/A |  | 2021 | 2020-09-21 | 2021-01-18 | 2021-07-30 | 193 | 2022-07-19 | 2023-01-18 | [5 empty] | BRZ | STAFF |  | Carryover | 3344507 | PROJETO | RICARDO TEIXEIRA | COMFORT LANES REPAVING | Facilities Sustaining | CLSD | OK, FINALIZADO | OK | OK | OK | Overrun |  | 7.64% |  |  | #REF! | [9 empty] | 94.836 | 94.836 | 15.111 | 109.947 | 97.7414 | 0 | 0 | 0 | 6.3461 | 0 | 5.2211 | 0 | 4.9852 | 80 | 81.189 | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 97.7414 | 0 | 97.7414 | 97.7414 | 0 | #REF! |  | 11.5672 | 86.1742 | 0 | #REF! | 103.236 | 97.7414 | 0 | 0 | 97.7414 | 5.4946 | 0 | 0
| 182 | LCP-200169 |  | 20/0116 | 2020 | 2020-10-08 | 2020-11-24 |  | -1144.336 | 2022-05-25 | 2022-11-24 | [5 empty] | AME | STAFF | EHS | Carryover | 3293510 | PROJETO | ROGÉRIO SIA | ENGINEERING CONTRACTOR’S SHOP STANDARDIZATION | EHS | REL | 20K Medição 11K Possivel faturamento de Material | 2022-03-31 | 2021-02-28 | 2022-09-30 | Overrun |  | 9.9% |  |  | #REF! | [8 empty] | 0 | 172.2 | 172.2 | 23.6 | 195.8 | 144.3442 | 0 | 0 | 0 |  | 0 | 0 | 6 | 6.0274 | 0 |  | 0 | 1.3899 |  |  | 30 | 38.3983 | 31.7 | 21.1335 | 7.9 | 26.7565 | 4.4 | 28.7184 | 40 | 21.9202 | 21.9202 | 45.1 | 8.1 | 10 | 10 | 17 | [8 empty] | 0 | [12 empty] | 18.0798 | 0 | 122.424 | 21.9202 | 189.4442 | 171.6056 | 17.8386 | #REF! |  | 0 | 7.4173 | 59.5318 | #REF! | 189.2478 | 144.3442 | 35.5675 | 0 | 179.9118 | 9.336 | 0 | 45.1
| 183 | LCP-200170 |  | 20/0112 | 2020 | 2020-07-01 | 2020-11-20 |  | -1148.336 | 2022-05-21 | 2022-11-20 | [5 empty] | AME | A | BANBURY | Carryover | 3293366 | PROJETO | GUSTAVO PARRAS | AME - UPGRADE DRIVE + MOTOR AC MILL MIXER#3 | Facilities Sustaining | REL | DEZ: 75K Motor Chega dia 20/12 TRAFO JÁ CHEGOU | 2022-04-30 | 2022-04-04 | 2022-09-30 |  |  |  | ICP-210011 |  | #REF! | RISCO DE ENTREGA DO PAINEL DA ROCKWELL, 55K | 8240513854 | RISCO DE 15K, CASO O PAINEL NÃO SEJA ENTREGUE NA DATA PREVISTA | N/A | N/A | N/A |  |  | 0 | 300 | 300.184 | 12.389 | 312.573 | 149.4533 | 0 | 0 | 2 |  | 0 | 0.64381 | 1 |  | 2 |  | 2 | 20.4592 | 4.6 | 0.09743 | 7 | 33.5151 | 7.7 | 6.1471 | 4.9 | 8.6909 | 96.6 | 15.4629 | 67.71 | 64.4368 | 64.4368 | 119.7 | 36.7 | 25 | 25 | 33 | [8 empty] | 0 | [12 empty] | 3.2732 | 0 | 85.0166 | 64.4368 | 269.1533 | 291.6536 | -22.5003 | #REF! | Aguardando conclusão do Projeto Mecanico da Base para seguir com SC - Será berta SC dia 22/10 | 0.64381 | 20.4592 | 39.7597 | #REF! | 300.1846 | 149.4533 | 102.8631 | 7.6221 | 259.9386 | 40.246 | 0 | 119.7
| 184 | LCP-200175 |  |  | 2020 | 2020-10-19 | 2020-12-03 | 2021-08-11 | 251 | 2022-06-03 | 2022-12-03 | [5 empty] | BRZ | STAFF |  | Carryover | 3325174 | PROJETO | RICARDO TEIXEIRA | RETROFIT–BLUE RACKS FOR CONSUMER TIRES | Facilities Sustaining | TECO | Projeto finalizado. Pode ser encerrado (CLOSE). | OK | 2021-08-31 | OK | Scope Change | 31/03/21 Troca de desenho blue rack. |  |  |  | #REF! | [8 empty] | 0 | 266.53 | 573.53 |  | 573.53 | 571.6906 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 80 | 185.7817 | 100 | 385.9089 | [11 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 571.6906 | 0 | 571.6906 | 571.6906 | 0 | #REF! |  | 0 | 185.7817 | 385.9089 | #REF! | 573.53 | 571.6906 | 0 | 0 | 571.6906 | 1.8395 | 0 | 0
| 185 | LCP-200177 |  |  | 2020 | 2020-10-22 | 2020-10-30 | 2021-07-27 | 270 | 2022-04-30 | 2022-10-30 | [5 empty] | MC |  |  | Carryover | 3294503 | PROJETO | RICARDO TEIXEIRA | NEW POWER GENERATOR | SAG | TECO | Projeto finalizado. Pode ser encerrado (CLOSE). | OK | 2021-05-30 | 2022-08-31 | [5 empty] | #REF! | [7 empty] | 0 | 0 | 70 | 107.814 | 5 | 112.814 | 49.7749 | 0 | 0 | 0 |  | 0 | 0 | 0 | 49.7749 | 0 |  | 0 | [14 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 49.7749 | 0 | 49.7749 | 49.7749 | 0 | #REF! |  | 0 | 49.7749 | 0 | #REF! | 107.814 | 49.7749 | 0 | 0 | 49.7749 | 58.0391 | 0 | 0
| 186 | LCP-200185 |  |  | 2020 | 2020-11-30 | 2020-12-14 |  | -1123.336 | 2022-06-14 | 2022-12-14 |  |  |  |  | ZQ4/23 | AME | B1 | CONST. TRADIC. | Carryover | 3458408 | PROJETO | FABIO MORAES | (VMI) AMERICANA CONSUMER HMC TIRE BUILDING | Capability | REL | DEZ: 111K Fundação 128k Painel das Eseteiras (INTERENG) - 23/12 100k Carro Flat | 2022-05-14 | 2022-05-31 | 2022-10-31 | Scope Change | Gate 2B |  | ICP-200043 |  | #REF! | [7 empty] | 900 | 0 | 4816 | 26690 | 3223 | 29913 | 855.3275 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 1.5407 |  | 0.67117 |  | 23.449 | 12.194 | 4.9561 | 9.903 | 26.458 | 28.72 | 294.8047 | 309 | 503.4478 | 503.4478 | 20005.6 | 5.6 | 100 | 300 | 200 | 300 | 7000 | 300 | 400 | 1200 | 200 | 500 | 9500 | 400 |  | 400 | [10 empty] | -194.4478 | 0 | 351.8796 | 503.4478 | 20860.9275 | 11150.895 | 9710.0325 | #REF! |  | 0 | 1.5407 | 29.0763 | #REF! | 26690 | 855.3275 | 10012.8436 | 1290.7982 | 12158.9693 | 14531.0307 | 10000 | 10005.6
| 189 | LCP-210010 | 3247 | 21/0013 | 2021 | 2020-12-22 | 2021-02-15 |  | -1061.336 | 2022-08-16 | 2023-02-15 | [5 empty] | AME | A | BANBURY | New | 3722056 | PROJETO | DIEGO CASTANHARO | REPLACEMENT OF THE PRIMARY GEARBOX MIXER#06 | Facilities Sustaining | REL | Em processo de Fabricação (NACIONAL) Prazo de Fabricação (informar a Região): 22 semanas (6 meses) Qual o fornecedor? Será então SEW | 2022-06-30 | 2022-04-30 | 2022-12-31 | [5 empty] | #REF! | RISCO DO FORNECEDOR NÃO ENTREGAR O REDUTOR EM DEZEMBRO, PODENDO SER ENTREGUE POSTERIORMENTE EM 2022 | 8240579875 (Redutor SEW) | NÃO POSSUI RISCOS | N/A | N/A | N/A |  |  |  | 46.988 | 156.626 |  | 156.626 | 94.9446 |  |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 2.246 |  | 2.0996 |  | 1.6932 |  | 1.107 | 97.0944 | 87.7988 | 87.7988 | 56.6382 |  |  |  | 56.6382 | [8 empty] | 0 | [12 empty] | 9.2955 | 0 | 7.1458 | 87.7988 | 151.5828 | 160.8769 | -9.2942 | #REF! |  | 0 | 0 | 4.3456 | #REF! | 156.626 | 94.9446 | 5.2159 | 0 | 100.1605 | 56.4655 | 56.6382 | 0
| 190 | LCP-210011 | 997 | 21/0023 | 2021 | 2020-12-22 | 2021-02-15 |  | -1061.336 | 2022-08-16 | 2023-02-15 | [5 empty] | AME | UTIL | ETE | New | 3722461 | PROJETO | HUELITON MAGNANI | WASTEWATER TANK IMPROVEMENT | EHS | REL | Parada do Natal. Interligação no separador de agua e oleo, e instalação das Bombas | 2022-02-28 | 2022-02-28 | 2022-12-31 | Overrun | Aumento de preço de varios equipamentos | 9.8% |  | Utilidades/Facilidades | #REF! | NÃO POSSUI RISCOS | NÃO POSSUI RISCOS | NÃO POSSUI RISCOS | N/A | N/A | N/A |  |  |  | 130.1 | 142.8498 |  | 142.8498 | 132.137 |  |  | 0 |  | 0 | 0 | 0 |  | 0 | 6.4592 | 5 | 21.8328 | 5 | 35.8934 | 5 | 20.9089 | 4.2912 | 20.5722 | 6.9 | 9.7476 | 5.3 | 7.9989 | 10.3 | 8.7239 | 8.7239 | 1.6 |  |  | 1.6 | [9 empty] | 0 | [12 empty] | 1.5761 | 0 | 123.4131 | 8.7239 | 133.737 | 129.1141 | 4.6228 | #REF! |  | 0 | 28.292 | 77.3745 | #REF! | 142.8498 | 132.137 | 0 | 4.9622 | 137.0991 | 5.7507 | 0 | 1.6
| 191 | LCP-210014 | 3032 | 21/0014 | 2021 | 2020-12-23 | 2021-03-10 |  | -1035.336 | 2022-09-08 | 2023-03-10 | [5 empty] | AME | A | CALANDRA | New | 3711102 | PROJETO | DIEGO CASTANHARO | UPGRADE OF DRIVES BEADWINDER#03 | Facilities Sustaining | REL | Chegando restante materiais e instalação em andamento 2022 Provisionamento será realizado | 2022-02-28 | 2022-04-30 | 2023-01-31 | [5 empty] | #REF! | NÃO POSSUI RISCOS | NÃO POSSUI RISCOS | NÃO POSSUI RISCOS | N/A | N/A | N/A |  |  |  | 102.811 | 102.811 |  | 102.811 | 81.8896 |  |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 39 | 7.2166 | 52.9 | 4.2919 | 50.8 | 42.055 | 0.7 | 0.43432 | 40 | 21.7466 | 3.1 | 6.1451 | 6.1451 | 12 | 1 | 11 | [10 empty] | 0 | [12 empty] | -3.0451 | 0 | 75.7445 | 6.1451 | 93.8896 | 93.9978 | -0.10827 | #REF! |  | 0 | 0 | 53.5635 | #REF! | 102.811 | 81.8896 | 10.5845 | 0 | 92.4741 | 10.3369 | 0 | 12
| 192 | LCP-210016 | 1540 |  | 2021 | 2020-12-26 | 2021-04-09 | 2021-12-27 | 262 | 2022-10-08 | 2023-04-09 | [5 empty] | AME | B1 | CONST. TBM | New | 3753624 | PROJETO | RICARDO TEIXEIRA | IMPROVEMENT CLIMATIZATION IN THE TBM'S | Quality | TECO | Finalizado. NF 8240580919 será entregue em Janeiro/22 | OK | 2021-11-30 | 2023-02-28 | [5 empty] | #REF! | SERVIÇO FINALIZADO, AGUARDANDO OS LAUDOS DA EMPRESA | NÃO POSSUI RISCOS | OK | N/A | N/A | N/A |  |  |  | 0 | 75.3973 |  | 75.3973 | 65.2338 |  |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 30 | 5.2233 | 38 | 9.0753 | 45.2 | 35.9108 | 9.3 | 13.276 | 1.8 |  | 1.8 | 1.7484 | 1.7484 | 0 | [12 empty] | 0 | [12 empty] | 0.0516 | 0 | 63.4854 | 1.7484 | 65.2338 | 65.2854 | -0.0516 | #REF! |  | 0 | 0 | 50.2095 | #REF! | 75.3973 | 65.2339 | 0 | 0 | 65.2339 | 10.1635 | 0 | 0
|  | LCP-210019 |  |  | 2021 | [11 empty] | AME | UTIL | SUBESTAÇÃO | Em aprovação |  | PROJETO | HUELITON MAGNANI | (07) PROTECTION SYSTEM RETROFITING - PRIMARY SUBSTATION | Energy Conservation | CRTD | Não excluir esta linha. Pois tem o valor do AOP alocado neste projeto. Projeto se tornou um Quartely | [8 empty] | #REF! | [9 empty] | 30 |  |  | 0 | 0 | [25 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| 195 | LCP-210022 | N/A |  | 2021 | 2021-01-13 | 2021-01-31 |  | -1076.336 | 2022-08-01 | 2023-01-31 | [5 empty] | BRZ | STAFF |  | New | 3631637 | PROJETO | RICARDO TEIXEIRA | PROJECT RUNNER | SAG | REL | Pendências e atendimento de novas necessidades levantadas pelos usuarios + Equipamentos de IT (data show sala de reuniões) + Dirigivel | 2022-06-30 | 2021-12-30 | 2022-11-30 | [5 empty] | #REF! | SC'S DE IT PARA COMPRA DE EQUIPAMENTOS AUDIOVISUAIS EM ANDAMENTO | NÃO POSSUI RISCOS | OK | N/A | N/A | N/A |  |  |  | 772.5 | 772.534 | 551.635 | 1324.169 | 588.6017 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 150 | 292.8455 | 145 | 88.0726 | 155 | 169.7551 | 26 | 12.6497 | 9.1 | 7.9864 |  | 3.4172 | 43.6 | 13.8751 | 13.8751 | 29.7493 |  | 29.7493 | [10 empty] | 0 | [12 empty] | 29.7248 | 0 | 574.7265 | 13.8751 | 618.351 | 620.2093 | -1.8583 | #REF! |  | 0 | 292.8455 | 270.4774 | #REF! | 772.534 | 588.6017 | 36.7826 | 0 | 625.3843 | 147.1497 | 0 | 29.7493
| 196 | LCP-210025 | 973 |  | 2021 | 2021-01-13 | 2021-03-11 |  | -1034.336 | 2022-09-09 | 2023-03-11 | [5 empty] | AME | B1 | FINAL FINISH | New | 3675973 | PROJETO | CARLOS SERAFIM | UPG AKROSCAN SYSTEM FOR LINES FVM | Facilities Sustaining | REL | CAMERAS PRETAS DEZ: M.O do Antony que irá instalar remotamente (Goodyear de Akron) ENG Akron (Antony) Valores Locais - Em processo de abertura de SCs: TRADUCAO, MO LOCAL, SOFTWARE, | 2022-02-28 | 2021-12-31 | 2023-01-31 |  |  |  | ICP-210016 |  | #REF! | NÃO POSSUI RISCOS, OS ITENS ESTÃO PREVISTOS A CHEGAREM EM OUTUBRO | NÃO POSSUI PEDIDOS COM RISCOS | SUPORTE DE AKRON,EM ANDAMENTO | 15,487.32 USD | 2021-10-01 | AEREO |  |  |  | 221.2 | 241.2 | 8.5 | 249.7 | 202.9344 |  |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  |  | 1.4512 |  |  | 169.4 | 172.5665 | 17.4335 | 3.8319 | 38.3 | 21.3177 | 2.7 | 3.7671 | 3.7671 | 0 | [12 empty] | 0 | [12 empty] | -1.0671 | 0 | 199.1673 | 3.7671 | 202.9344 | 240.8496 | -37.9152 | #REF! | 30K M.O do Anthony (Goodyear Akron) Aguardando resposta do Anthony e 15K de impostos de importação | 0 | 0 | 174.0177 | #REF! | 241.2 | 202.9344 | 0.05859 | 27 | 229.993 | 11.207 | 0 | 0
| 198 | LCP-210040 | N/A |  | 2021 | 2021-02-24 | 2021-03-18 | 2021-12-23 | 280 | 2021-12-31 | 2022-03-31 |  | SIM |  | AQ4/21 |  | RET |  |  | New | 3753725 | PROJETO | CHARLES BARBAN | FSB - 2021 MISCELLANEOUS ANNUAL BUDGET | Facilities Sustaining | CLSD | OK, FINALIZADO | OK | 2021-12-31 | OK | [5 empty] | #REF! | [9 empty] | 70 |  |  | 0 | 68.4953 |  |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 14.5 | 13.3996 |  |  |  |  | 55.5 | 49.492 | 16 |  |  | 5.6037 | 5.6037 | 0 | [12 empty] | 0 | [12 empty] | -5.6037 | 0 | 62.8915 | 5.6037 | 68.4953 | 90.8915 | -22.3963 | #REF! |  | 0 | 0 | 13.3996 | #REF! | 92 | 68.4953 | 0 | 0 | 68.4953 | 23.5047 | 0 | 0
| 199 | LCP-210045 | 1099 |  | 2021 | 2021-02-19 | 2021-06-16 |  | -938.336 | 2022-12-15 | 2023-06-16 | [5 empty] | AME | A | CALANDRA | New | 4098373 | PROJETO | CARLOS SERAFIM | CREEL ROOM TRANSFER FROM GADSTEN PLANT | Productivity | REL | DEZ: Materiais Pedido Local OK FRETE: Marítimo Prontidão para 24/Novembro Chegada do equipamento em Dez 11K Mão de obra 85K Possivel Troca de peças danificadas. Aguardando chegada do equipamento para ter certeza | 2022-10-31 | 2022-11-30 | 2023-04-30 | Overrun |  | 33.57% |  |  | #REF! | ENTREGA DOS MATERIAIS NACIONAIS (FREIOS) E ENTREGA DO CREEL ROOM EM AMERICANA, EM FASE DE EMBALAGEM PELA EMPRESA PROPAC | 8240686114 - CREEL ROOM / SC122560553 - FREIOS | NÃO POSSUI RISCOS | 177,395.00 USD (BV) | PREVISTO PARA OUT/21 CHEGA EM DEZEMBRO | MARITIMO |  |  |  | 0 | 185 | 105.77 | 290.77 | 27.0906 |  |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | [8 empty] | 0.09402 |  | 12.5736 | 13.4 | 14.423 | 14.423 | 158 |  |  | 9 | 20 | 20 | 10 | 10 | 10 | 9 | 70 |  |  | 0 | [12 empty] | -1.023 | 0 | 12.6676 | 14.423 | 185.0906 | 185.094 | -0.00345 | #REF! | 50K SC será aberta para Retrofit das peças | 0 | 0 | 0 | #REF! | 185 | 27.0906 | 11.2906 | 54.4135 | 92.7947 | 92.2053 | 89 | 69
| 201 | LCP-210055 | Informar |  | 2021 | 2021-03-09 | 2021-04-19 |  | -996.336 | 2022-10-18 | 2023-04-19 | [5 empty] | AME | B1 | CONST. TRADIC. | New | 3872158 | PROJETO | CARLOS SERAFIM | AME – WULO CONSUMMER BUILDING - STEP 1 - NT20 | EHS | REL | OUT: Material INTERENG NOV/DEZ: Materiais de Proteções + Instalação | 2022-09-30 | 2022-02-28 | 2023-02-28 | [5 empty] | #REF! | NÃO POSSUI RISCOS, MATERIAIS SENDO ENTREGUES PELA INTERENG | NÃO POSSUI PEDIDOS COM RISCOS | NÃO POSSUI RISCOS | N/A | N/A | N/A |  |  |  | 100 | 100 | 9.85 | 109.85 | 87.7155 |  |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  |  | 9.17 | 13 | 15.3198 | 21.7 | 6.7465 | 24.8 | 16.9605 | 37.1 | 28.919 | 18.8 | 10.5998 | 10.5998 | 8.2 | 8.2 | [11 empty] | 0 | [12 empty] | 8.2002 | 0 | 77.1157 | 10.5998 | 95.9155 | 96.2968 | -0.38124 | #REF! | SC Será aberta até 15/10 | 0 | 0 | 31.2363 | #REF! | 100 | 87.7155 | 10.6815 | 0 | 98.3971 | 1.603 | 0 | 8.2
| 202 | LCP-210077 | N/A |  | 2021 | 2021-04-05 | 2021-04-19 | 2021-12-17 | 242 | 2022-10-18 | 2023-04-19 | [5 empty] | RET |  |  | New | 3963949 | PROJETO | CHARLES BARBAN | AERO - VENTILATION AND EXHAUSTING SYSTEM | EHS | CLSD | OK, FINALIZADO | OK | 2021-10-30 | OK | [5 empty] | #REF! | [10 empty] | 126.86 |  | 126.86 | 46.032 |  |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 35.0307 | 12 | 10.7743 | 0.2 | 0.22705 |  |  |  | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 46.032 | 0 | 46.032 | 46.0049 | 0.02705 | #REF! |  | 0 | 0 | 35.0307 | #REF! | 126.86 | 46.032 | 0 | 0 | 46.032 | 80.828 | 0 | 0
| 205 | LCP-210084 | 11932 |  | 2021 | 2021-04-19 | 2021-06-07 |  | -947.336 | 2022-12-06 | 2023-06-07 | [5 empty] | AME | A | GERAL | New | 4177784 | PROJETO | DIEGO CASTANHARO | AME - UPG BARREL AND SCREWS | Facilities Sustaining | REL | Julho: 20K Requisitado do Estoque - CAL4R1 ISO 5 - Requisitado D#4 (17k) - Requisitado 8x3 (33k) - 2022 Mixer#1 - Dez 2022: Instalação Alinhar Cashflow Alniezi | 2022-11-30 | 2022-03-31 | 2023-04-30 | [5 empty] | #REF! | [9 empty] | 0 | 347.099 |  | 347.099 | 312.1688 | [6 empty] | 0 |  | 0 |  | 0 |  |  | 20.8616 |  | 189.8162 |  |  |  | 22.3339 |  | 16.4037 | 25.3357 | 62.7533 | 62.7533 | 33.9 | [9 empty] | 33.9 |  |  | 0 | [12 empty] | -37.4176 | 0 | 249.4155 | 62.7533 | 346.0688 | 346.3107 | -0.24198 | #REF! |  | 0 | 0 | 210.6778 | #REF! | 381.114 | 312.1688 | 63.3189 | 3.664 | 379.1517 | 1.9623 | 135.599 | -101.699
| 206 | LCP-210085 | 3103 |  | 2021 | 2021-04-19 | 2021-05-25 |  | -959.336 | 2022-11-23 | 2023-05-25 | [5 empty] | AME | A | CALANDRA | New | 4144541 | PROJETO | DIEGO CASTANHARO | CAL4R2 - UPG OF THE BELT STEEL SYSTEM | Facilities Sustaining | REL | DEZ: 100K Chegada estrutura das esteiras metalicas Entrega prevista para o dia 21/12 23K Provisão da Instalação no Natal | 2022-02-28 | 2021-12-31 | 2023-03-31 | [5 empty] | #REF! | RISCO DE NÃO ENTREGAR OS MATERIAIS PREVISTOS EM NOVEMBRO, PODENDO SER ENTREGUES EM DEZEMBRO | 8240657149 (Módulo tensionador) | NÃO POSSUI RISCOS | N/A | N/A | N/A |  |  |  | 0 | 184.033 |  | 184.033 | 166.8422 | [6 empty] | 0 |  | 0 |  | 0 | [5 empty] | 60 | 45.8039 |  | 8.6518 | 113.3 | 12.1151 | 101.3 | 100.2715 | 100.2715 | 0 | [12 empty] | 0 | [12 empty] | 1.0285 | 0 | 66.5708 | 100.2715 | 166.8422 | 167.7557 | -0.91348 | #REF! | SC Será aberta até 15/10 - M.O | 0 | 0 | 45.8039 | #REF! | 184.033 | 166.8422 | 0 | 0 | 166.8422 | 17.1908 | 0 | 0
| 207 | LCP-210086 | 3833 |  | 2021 | 2021-04-19 | 2021-07-14 |  | -909.336 | 2023-01-12 | 2023-07-14 | [5 empty] | AME | B2 | FINAL FINISH | New | 4129586 | PROJETO | CARLOS SERAFIM | AME - NEW MRT KOKUSAI MACHINE | Quality | REL | ICP Downpayment Novembro $367K Valor da Máquina: $1,2M OUT 2022: CHEGADA DA MAQ | 2022-12-31 | 2022-12-31 | 2023-05-31 | [5 empty] | #REF! | [9 empty] | 0 | 2764 | 112.278 | 2876.278 | 4.1766 | [6 empty] | 0 |  | 0 |  | 0 | [10 empty] | 4.1766 |  |  |  | 2759.8 |  |  |  | 11.2 | 260 | 200 | 228 | 24.6 | 30 | 1791 | 120 | 95 | 0 | [12 empty] | 0 | 0 | 4.1766 | 0 | 2763.9766 | 2764 | -0.02341 | #REF! |  | 0 | 0 | 0 | #REF! | 2764 | 4.1766 | 1.4126 | 0 | 5.5892 | 2758.4108 | 2764 | -4.2
| 208 | LCP-210092 | N/A |  | 2021 | 2021-04-28 | 2021-05-28 | 2021-12-23 | 209 | 2022-11-26 | 2023-05-28 | [5 empty] | RET |  |  | New | 4149542 | PROJETO | CHARLES BARBAN | RET - UPG PLC AND PRESS TEMP CONTROL | Facilities Sustaining | TECO | Apenas 2 pedidos em aberto - Contatores da INTERENG - Chegarão até Fev/22 | OK | 2021-12-31 | 2023-03-31 | Overrun |  | 6.9% |  |  | #REF! | [9 empty] | 50 | 106.779 |  | 106.779 | 86.2031 |  |  | 12.5 |  |  |  | 0 |  | 0 |  | 0 |  |  |  |  | 29.9912 | 5 | 7.609 | 2.4 | 41.067 | 5.8 | 6.9741 | 0 | 0.5619 | 0.5619 | 0 | [12 empty] | 0 | [12 empty] | -0.5619 | 0 | 85.6412 | 0.5619 | 86.2031 | 84.4672 | 1.736 | #REF! |  | 0 | 0 | 37.6002 | #REF! | 106.779 | 86.2031 | 2.8266 | 0 | 89.0297 | 17.7493 | 0 | 0
| 209 | LCP-210098 | 7918 |  | 2021 | 2021-05-10 | 2021-06-30 |  | -924.336 | 2022-12-29 | 2023-06-30 | [5 empty] | AME | A | ENTUBADORA | New | 4247961 | PROJETO | GUSTAVO PARRAS | AME - UPG WIND-UP EXTRUDER 8x8 SW | Capability | REL | DEZ: 25K Cameras 2022: Materiais e Instalação | 2022-10-30 | 2022-10-30 | 2023-04-30 |  |  |  | ICP-210051 |  | #REF! | Risco de 50K (Chegada das cameras) | AGUARDANDO PEDIDO DE COMPRAS | NÃO POSSUI RISCOS | 50K (CAMERAS) | 2021 | AEREO |  |  |  |  | 286.955 | 50 | 336.955 | 49.7517 | [8 empty] | 0 |  | 0 | [7 empty] | 5 |  | 25 | 21.4027 | 26 | 28.349 | 28.349 | 107.7 | 7.7 | 10 | 10 | 30 | 30 | 5 | 5 | 5 | 5 |  |  |  | 0 | [12 empty] | -2.349 | 0 | 21.4027 | 28.349 | 157.4517 | 287 | -129.5483 | #REF! |  | 0 | 0 | 0 | #REF! | 286.955 | 49.7517 | 39.3222 | 6.6961 | 95.7699 | 191.1851 | 237 | -129.3
| 210 | LCP-210100 | N/A |  | 2021 | 2021-05-11 | 2021-05-28 |  | -956.336 | 2022-11-26 | 2023-05-28 | [5 empty] | RET |  |  | New | 4154934 | PROJETO | CHARLES BARBAN | FSB - FM GLOBAL ADEQUANCY | EHS | REL | Previsão de Término Fev/22 | 2022-02-28 | 2022-01-30 | 2023-03-31 | [5 empty] | #REF! | [9 empty] | 30 | 60.6 |  | 60.6 | 33.6326 | [8 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 22 | 24.3305 | 19.7 | 9.3022 |  |  |  | 7 |  | 7 | [10 empty] | 0 | [12 empty] | 0 | 0 | 33.6326 | 0 | 40.6326 | 60.6305 | -19.9978 | #REF! |  | 0 | 0 | 0 | #REF! | 60.6 | 33.6326 | 7.1182 | 0 | 40.7508 | 19.8492 | 0 | 7
| 212 | LCP-210102 | N/A |  | 2021 | 2021-05-14 | 2021-06-22 |  | -932.336 | 2022-12-21 | 2023-06-22 | [5 empty] | RET |  |  | New | 4175146 | PROJETO | CHARLES BARBAN | NR12 ADEQUANCY AERO RETREAD MACHINES | EHS | REL | Previsão de Término Fev/22 | 2022-02-28 | 2022-02-28 | 2023-04-30 | [5 empty] | #REF! | [9 empty] | 60 | 70.6 |  | 70.6 | 44.7811 | [8 empty] | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 35 | 34.2469 | 36.1 | 10.5342 | 10.5342 | 19.1 | 19.1 | [11 empty] | 0 | [12 empty] | 25.5658 | 0 | 34.2469 | 10.5342 | 63.8811 | 70.6 | -6.7189 | #REF! |  | 0 | 0 | 0 | #REF! | 70.6 | 44.7811 | 18.0408 | 0 | 62.822 | 7.778 | 0 | 19.1
| 213 | LCP-210103 | 12538 |  | 2021 | 2021-05-14 | 2021-08-26 |  | -866.336 | 2023-02-24 | 2023-08-26 | [5 empty] | AME | STAFF | EHS | New | 4462054 | PROJETO | HUELITON MAGNANI | AME - RESTAURANT’S KITCHEN ADEQUACY | EHS | REL | DEZ: Entrega Projeto Março: Inicio da Instalacão | 2022-08-31 | 2023-01-31 | 2023-06-30 |  |  |  |  | Utilidades/Facilidades | #REF! | RISCO DA COZINHA NÃO PARAR O FUNCIONAMENTO E NÃO TER O CONTAINER LOCADO (TURN KEY) 75K US$ | AGUARDANDO GERAR O PEDIDO DE COMPRAS | RISCO DA COZINHA NÃO PARAR O FUNCIONAMENTO E NÃO TER O CONTAINER LOCADO (TURN KEY) 75K US$ | N/A | N/A | N/A |  |  |  | 0 | 345.9268 | 53.1032 | 399.0301 | 54.6334 | [8 empty] | 0 |  | 0 | [8 empty] | 0.50517 | 0 | 1.6106 | 46.3 | 52.5177 | 52.5177 | 291.32 |  |  |  | 10 | 11.84 | 31.04 | 31.04 | 31.04 | 31.04 | 31.04 | 31.04 | 83.24 | 0 | [12 empty] | -6.2177 | 0 | 2.1158 | 52.5177 | 345.9534 | 345.9352 | 0.01827 | #REF! |  | 0 | 0 | 0 | #REF! | 345.9268 | 54.6334 | 218.8262 | 0 | 273.4596 | 72.4672 | 270.93 | 20.39
| 214 | LCP-210106 | 13699 |  | 2021 | 2021-05-17 | 2021-06-07 |  | -947.336 | 2022-12-06 | 2023-06-07 | [5 empty] | AME | UTIL | CASA FORÇA | New | 4193543 | PROJETO | HUELITON MAGNANI | AME - CENTAC#17 100 PSI AIR COMPRESSOR | Facilities Sustaining | REL | 22K -vMaterial e Projeto da Monovia Talha (empresa SOS maquinas) | 2022-01-31 | 2021-12-31 | 2023-04-30 | Overrun |  | 1.75% |  | Utilidades/Facilidades | #REF! | RISCO DE NÃO FAZER A MONOVIA, VALOR ESTÁ FICANDO ACIMA DO ESTIMADO - 28,6K US$ | AGUARDANDO GERAR O PEDIDO DE COMPRAS | RISCO DE NÃO FAZER A MONOVIA, VALOR ESTÁ FICANDO ACIMA DO ESTIMADO - 28,6K US$ | N/A | N/A | N/A |  |  |  | 0 | 100.1 | 33.6 | 133.7 | 96.1152 | [8 empty] | 0 |  | 0 |  |  |  | 10 |  | 70 | 60.207 |  |  | 28.6 | 5.5105 | 23.1 | 30.3977 | 30.3977 | 0 | [12 empty] | 0 | [12 empty] | -7.2977 | 0 | 65.7175 | 30.3977 | 96.1152 | 88.807 | 7.3082 | #REF! | Alterar SC para valor total até 15/10 | 0 | 0 | 60.207 | #REF! | 100.1 | 96.1152 | 2.036 | 0 | 98.1511 | 1.9489 | 0 | 0
| 215 | LCP-210107 | 9442 |  | 2021 | 2021-05-17 | 2021-06-04 |  | -950.336 | 2022-12-03 | 2023-06-04 | [5 empty] | AME | A | BANBURY | New | 4193801 | PROJETO | DIEGO CASTANHARO | UPGRADE COOLING SYSTEM BB#4 | Facilities Sustaining | REL | Pedido não foi fechado com DOwnpayment Para 2021 = 60K (Chiller, Bombas, Trocador Calor) Nov: 30K do projeto Dez: 30k materiais *aguardando PO Srs. Boa tarde! Fizemos hoje primeira reunião para definição de qual caminho seguir do projeto de resfriamento de manta do BB#04. Pontos discutido para melhor desenvolvimento do projeto. • Temperatura saída manta 120 graus; • Espessura da manta 12 mm; • Troca do sabão ( Temperatura ambiente ); • Tempo da manta em transporte; • Comprimento batch off + Exaustão; • Comprimento looping no transportador cabide; • Possibilidade trocar esteira resfriamento por uma esteira vazada; • Enclausuramento da esteira de resfriamento; • Cortina de ar gelado – Antes Wig Wag; • Capacidade de equipamentos ( Chillers / Bombas / Trocador de Calor ); Na próxima semana teremos outra reunião com as sugestão para definição e aprovação para seguir com projeto. Valor de novembro transferido para dezembro, aguardando definição do projeto. | 2022-10-30 | 2022-12-31 | 2023-04-30 |  |  |  |  | Utilidades/Facilidades | #REF! | NÃO POSSUI RISCOS | NÃO POSSUI RISCOS | NÃO POSSUI RISCOS | N/A | N/A | N/A |  |  |  | 200 | 247.637 |  | 247.637 | 0 | [8 empty] | 0 |  | 0 | [9 empty] | 30 |  |  |  |  | 247.566 |  | 26.2 | 3.8 | 20 | 20 | 50 | 37.6 | 37.666 | 50 | 2.3 |  |  | 0 | [12 empty] | 0 | 0 | 0 | 0 | 247.566 | 247.606 | -0.04 | #REF! |  | 0 | 0 | 0 | #REF! | 247.637 | 0 | 99.023 | 0 | 99.023 | 148.614 | 187.6 | 59.966
| 217 | LCP-210114 | 14371 |  | 2021 | 2021-05-21 | 2021-06-30 | 2021-11-25 | 148 | 2022-12-29 | 2023-06-30 | [5 empty] | AME | B2 | CONSTRUÇÃO | New | 4256296 | PROJETO | DIEGO CASTANHARO | AME -COMPLEXITY AND CONCURRENCY INCREASE | Capability | TECO | Projeto finalizado. Pode ser encerrado (CLOSE). | OK | 2021-12-31 | OK | Overrun | 15/10/21 Devido aumento do material para fabricação desses equipamentos e ficou faltando 49 skids | 9.89% |  |  | #REF! | NÃO POSSUI RISCOS | NÃO POSSUI RISCOS | NÃO POSSUI RISCOS | N/A | N/A | N/A |  |  |  | 0 | 231.434 |  | 231.434 | 238.6125 | [8 empty] | 0 |  | 0 |  |  |  | 85 | 10.9584 | 80 | 108.6427 | 15.2 | 68.8793 | 43.9 | 50.1178 |  | 0.01431 | 0.01431 | 0 | [12 empty] | 0 | [12 empty] | -0.01431 | 0 | 238.5982 | 0.01431 | 238.6125 | 232.3804 | 6.2321 | #REF! | Aguardando Over run para comprometer o restante | 0 | 0 | 119.6011 | #REF! | 254.334 | 238.6125 | 0 | 0 | 238.6125 | 15.7215 | 0 | 0
| 218 | LCP-210118 | 9504 |  | 2021 | 2021-05-27 | 2021-06-22 |  | -932.336 | 2022-12-21 | 2023-06-22 | [5 empty] | AME | A | BANBURY | New | 4226107 | PROJETO | DIEGO CASTANHARO | COOLING SYSTEM UPGRADE MIXER#02–PHASE I | Facilities Sustaining | REL | Dez: Vai faturar Metade do Projeto Ele/Mec | 2022-11-30 | 2022-12-31 | 2023-04-30 |  |  |  |  | Utilidades/Facilidades | #REF! | RISCO DEVIDO FECHAMENTO DE PEDIDO, PROJETO TURN KEY |  |  | N/A | N/A | N/A |  |  |  |  | 183.585 |  | 183.585 | 32.7324 | [8 empty] | 0 |  | 0 | [9 empty] | 30 | 19.8666 | 12.5 | 12.8659 | 12.8659 | 151.166 |  | 20 |  |  | 60 |  |  | 63.5 | 7.666 |  |  |  | 0 | [12 empty] | -0.36585 | 0 | 19.8666 | 12.8659 | 183.8984 | 183.506 | 0.39241 | #REF! |  | 0 | 0 | 0 | #REF! | 183.585 | 32.7324 | 145.2317 | 0 | 177.9641 | 5.6209 | 123.5 | 27.666
| 219 | LCP-210120 | 9445 |  | 2021 | 2021-05-28 | 2021-06-30 |  | -924.336 | 2022-12-29 | 2023-06-30 | [5 empty] | AME | A | BANBURY | New | 4270167 | PROJETO | DIEGO CASTANHARO | AME - COOLING SYSTEM UPGRADE MIXER#03 | Facilities Sustaining | REL | Dez: Vai faturar Metade do Projeto Ele/Mec | 2022-11-30 | 2022-12-31 | 2023-04-30 |  |  |  |  | Utilidades/Facilidades | #REF! | RISCO DEVIDO FECHAMENTO DE PEDIDO, PROJETO TURN KEY |  |  | N/A | N/A | N/A |  |  |  |  | 183.962 |  | 183.962 | 32.7324 | [8 empty] | 0 |  | 0 | [9 empty] | 30 | 19.8666 | 12.5 | 12.8659 | 12.8659 | 151.666 |  | 20 |  |  | 60 |  |  | 64 | 7.666 |  |  |  | 0 | [12 empty] | -0.36585 | 0 | 19.8666 | 12.8659 | 184.3984 | 184.006 | 0.39241 | #REF! |  | 0 | 0 | 0 | #REF! | 183.962 | 32.7324 | 145.2317 | 0 | 177.9641 | 5.9979 | 124 | 27.666
| 221 | LCP-210123 | 15312 |  | 2021 | 2021-06-01 | 2021-06-22 |  | -932.336 | 2022-12-21 | 2023-06-22 | [5 empty] | AME | B2 | FINAL FINISH | New | 4251643 | PROJETO | CARLOS SERAFIM | AME - REPLACEMENT X-RAY SET TUBE (A & C) | Facilities Sustaining | REL | Sendo comprado pelo Almoxarifado Chegada do material Importado em Novembro Frete: Aéreo Pedido do Almoxarifado: 8240644584 8240615986 8240664072 | 2022-01-31 | 2021-12-31 | 2023-04-30 | [5 empty] | #REF! | MATERIAL SENDO COMPRADO PELO ALMOXARIFADO, PREVISTO CHEGAR EM NOVEMBRO/21 | NÃO POSSUI PEDIDOS COM RISCOS | N/A | N/A | N/A | N/A |  |  |  | 0 | 130 |  | 130 | 183.4682 | [8 empty] | 0 |  | 0 |  | 50 | 65.0239 |  | 8.3198 |  | 8.125 |  |  | 56.8613 | 41.3028 |  | 60.6968 | 60.6968 | 0 | [12 empty] | 0 | [12 empty] | -60.6968 | 0 | 122.7714 | 60.6968 | 183.4682 | 138.3299 | 45.1383 | #REF! | Item sendo comprado pelo Estoque | 0 | 0 | 81.4687 | #REF! | 195 | 183.4682 | 0 | 0 | 183.4682 | 11.5318 | 0 | 0
| 225 | LCP-210134 | 10312 |  | 2021 | 2021-06-11 | 2021-08-10 |  | -882.336 | 2023-02-08 | 2023-08-10 | [5 empty] | AME | FACIL | EHS | New | 4413319 | PROJETO | HUELITON MAGNANI | AME – INTERNAL LIGHTING ADEQUACY | EHS | REL | DEZ: Chegada de luminárias até 17/12 | 2022-12-31 | 2022-12-31 | 2023-06-30 |  |  |  |  | Utilidades/Facilidades | #REF! | NÃO POSSUI RISCOS | NÃO POSSUI RISCOS | NÃO POSSUI RISCOS | N/A | N/A | N/A |  |  |  | 0 | 166.0112 | 32.3595 | 198.3708 | 101.3819 | [10 empty] | 0 | [5 empty] | 20 | 14.0532 | 15.4 | 37.024 | 35 | 9.2814 | 44.5 | 41.0233 | 41.0233 | 64.5 | 1.1 | 5 | 8 | 9.4 | 5 | 5 | 5.1667 | 5.1667 | 5.1667 | 5.1667 | 5.1667 | 5.1667 | 0 | [12 empty] | 3.4767 | 0 | 60.3586 | 41.0233 | 165.8819 | 165.8772 | 0.00471 | #REF! |  | 0 | 0 | 14.0532 | #REF! | 166.0112 | 101.3819 | 55.0502 | 4.3032 | 160.7353 | 5.2759 | 86 | -21.5
| 187 | LCP-210140 | 14331 |  | 2021 | 2021-06-16 | 2021-07-15 |  | -908.336 | 2023-01-13 | 2023-07-15 | [5 empty] | AME | A | CALANDRA | New | 4306091 | PROJETO | HUELITON MAGNANI | AME - CAL 3R COOLING IMPROVEMENT | Productivity | REL | - DEZ: Chegada do Chiller - OK Restante é Mão Obra GTEL | 2022-03-31 | 2022-05-31 | 2023-05-31 |  |  |  |  | Utilidades/Facilidades | #REF! | RISCO DE NÃO SER ENTRE ENTREGUE O CHILLER EM 2021 - APROXIMADAMENTE 350K (BRL) | AGUARDANDO GERAR O PEDIDO DE COMPRAS | POSSUI RISCOS CASO O CHILLER NÃO SEJA ENTREGUE EM 2021 - APROXIMADAMENTE 350K (BRL) | N/A | N/A | N/A |  |  |  | 0 | 132.15 | 7.8 | 139.95 | 54.9136 | [10 empty] | 0 | [5 empty] | 2 |  |  |  |  | 12.9675 | 35.8884 | 41.946 | 41.946 | 77 | 0 | 0 | 37 | 10 | 10 | 10 | 5 | 5 |  |  |  |  | 0 | [12 empty] | -6.0576 | 0 | 12.9675 | 41.946 | 131.9136 | 132 | -0.0864 | #REF! | Valor da SC de M.O vai passar de 25K para 70K | 0 | 0 | 0 | #REF! | 132.15 | 54.9136 | 69.6751 | 2.8926 | 127.4813 | 4.6687 | 0 | 77
| 233 | LCP-210146 | 16258 |  | 2021 | 2021-06-18 | 2021-06-30 |  | -924.336 | 2022-12-29 | 2023-06-30 | [5 empty] | AME | A | CALANDRA | New | 4305421 | PROJETO | CARLOS SERAFIM | AME - WIRE CALENDER NR12 - BRZ MANDATORY | EHS | REL | 3 Painéis Intereng chegarão no dia 23/12 Instalação 2022 | 2022-11-30 | 2022-12-31 | 2023-04-30 | [5 empty] | #REF! | NÃO POSSUI RISCOS | NÃO POSSUI PEDIDOS COM RISCOS | NÃO POSSUI RISCOS | N/A | N/A | N/A |  |  |  | 0 | 575.6093 |  | 575.6093 | 88.8463 | [10 empty] | 0 |  |  |  |  | 10.1521 | 11.6 | 41.4454 | 19.9859 | 18.9953 | 62.3 |  | 60.3 | 18.2536 | 18.2536 | 483.6 | 30 | 62 | 56.22 | 56.22 | 56.22 | 56.22 | 56.22 | 60 | 50.5 |  |  |  | 0 | [12 empty] | 42.0464 | 0 | 70.5927 | 18.2536 | 572.4463 | 572.4928 | -0.04643 | #REF! |  | 0 | 0 | 51.5975 | #REF! | 575.6093 | 88.8463 | 55.2449 | 66.8106 | 210.9018 | 364.7074 | 373.6 | 110
|  | LCP-210177 | 17605 |  | 2022 | 2021-08-09 | 2021-09-22 |  | -842.336 | 2023-03-23 | 2023-09-22 | [5 empty] | AME | A | ENTUBADORA | New | 4636423 | PROJETO | DIEGO CASTANHARO | AME - UPG EXTRUDER READ 8X3 EXTRUDER | Facilities Sustaining | REL | Downpayment | 2023-02-28 | 2023-07-31 | 2023-07-31 | [5 empty] | #REF! | [10 empty] | 183.67 |  | 183.67 | 34.6423 | [21 empty] | 34.6423 |  |  |  | 148 |  |  |  |  | 78 | 35 | 35 | [5 empty] | 0 | [12 empty] | 0 | 0 | 34.6423 | 0 | 182.6423 | 183 | -0.35769 | #REF! |  | 0 | 0 | 0 | #REF! | 183.67 | 34.6423 | 112.9764 | 0 | 147.6187 | 36.0513 | 183 | -35
|  | LCP-210180 | Informar |  | 2021 | 2021-08-17 | 2021-09-30 |  | -834.336 | 2023-03-31 | 2023-09-30 | [5 empty] | AME | B2 | VULCANIZAÇÃO | New | 4608952 | PROJETO | HUELITON MAGNANI | AME - UPGRADE PLC MRT PRESSES | Facilities Sustaining | REL | Paineis INTERENG - Chega até dia 23/12 |  | 2023-03-31 | [6 empty] | #REF! | RISCO DE NÃO SER ENTREGUES OS PAINÉIS DA INTERENG (VALOR TOTAL COMPROMETIDO) AINDA NÃO GEROU PEDIDO DE COMPRAS -> 410K | AGUARDANDO GERAR O PEDIDO DE COMPRAS | NÃO POSSUI RISCOS | N/A | N/A | N/A |  |  |  | 0 | 1251.486 |  | 1251.486 | 478.3286 | [19 empty] | 4.7713 |  | 141.9803 | 307.7808 | 331.577 | 331.577 | 432.1667 | [6 empty] | 48.5 | 50.3333 | 83.3333 | 83.3333 | 83.3333 | 83.3333 | 341.396 | 41.666 | 41.666 | 41.666 | 41.666 | 41.666 | 41.666 | 45.7 | 45.7 |  |  |  |  | -23.7962 | 0 | 146.7515 | 331.577 | 910.4952 | 910.9713 | -0.47603 | #REF! |  | 0 | 0 | 0 | #REF! | 1251.486 | 478.3286 | 138.581 | 0 | 616.9095 | 634.5765 | 500 | -67.8333
|  | LCP-210200 | Informar |  | 2021 | 2021-09-17 | 2021-11-04 |  | -799.336 | 2023-05-05 | 2023-11-04 | [5 empty] | AME | A | BANBURY | New | 4771098 | PROJETO | GUSTAVO PARRAS | AME - MIXER #3 BODY REPLACEMENT | Facilities Sustaining | REL | Set: 280 Dowpayment | 2023-05-05 | 2023-09-30 | 2023-09-30 | [5 empty] | #REF! | [10 empty] | 1662.6695 | 46 | 1708.6695 | 0 | [25 empty] | 1630 | [8 empty] | 280 | 950 | 200 | 200 | 362 | 120.6667 | 120.6667 | 120.6667 | [9 empty] | 0 | 0 | 0 | 0 | 1630 | 1662.6695 | -32.6695 | #REF! |  | 0 | 0 | 0 | #REF! | 1662.67 | 0 | 0.25819 | 0 | 0.25819 | 1662.4118 | 1300 | 330
|  | LCP-210208 |  |  | 2021 | 2021-10-05 | 2021-11-17 |  | -786.336 | 2023-05-18 | 2023-11-17 | [5 empty] | AME | A | BANBURY | New | 4824059 | PROJETO | GUSTAVO PARRAS | AME - 2500 HP MAIN MOTOR - SPARE FOR MIXERS |  | REL |  | 2023-05-30 | 2023-09-30 | 2023-09-30 | [16 empty] | 280.48 | 18 | 298.48 | 0 | [25 empty] | 280 |  | 40 | [8 empty] | 240 | [14 empty] | 0 | 0 | 0 | 0 | [9 empty] | 280.48 | 0 | 0 | 0 | 0 | 280.48
|  | LCP-210209 | Informar |  | 2021 | 2021-10-05 | 2021-10-14 | 2021-12-28 | 75 | 2023-04-14 | 2023-10-14 | [5 empty] | AME | A | BANBURY | New | 4829079 | PROJETO | GUSTAVO PARRAS | AME - MIXER#07 REPLACEMENT 2nd GEARBOX | Facilities Sustaining | TECO | Falta a entrada de 2 Notas Fiscais PO 8240733869 | OK | 2021-11-30 | 2023-08-31 | Overrun | Necessidade de substituir mais dois rolamentos e também o embuchamento do assento da carcaça de um dos lados. | 9% |  |  | #REF! | [10 empty] | 126.929 | 10.942 | 137.871 | 117.4902 | [19 empty] | 105.3675 | 10.9 | 12.1227 |  |  |  | 0 | [25 empty] | 0 | 0 | 117.4902 | 0 | 117.4902 | 116.2675 | 1.2227 | #REF! |  |  |  |  | #REF! | 126.929 | 117.4902 | 0.30262 | 0.00018 | 117.793 | 9.136
|  | LCP-210212 | 17039 |  | 2022 | 2021-10-07 | 2021-11-23 |  | -780.336 | 2023-05-24 | 2023-11-23 | [5 empty] | AME | B1 | FINAL FINISH | New | 4828989 | PROJETO | CARLOS SERAFIM | AME - MICROPOISE AIT BALANCE MACHINES (Obsolesence) | Facilities Sustaining | REL | Possibilidade de Downpayment para este ano 100K | 2023-05-24 | 2023-05-24 | 2023-09-30 |  |  |  | ICP-210069 |  | #REF! | [10 empty] | 600 | 0 | 600 | 0 | [25 empty] | 600 |  |  |  | 330 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 60 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 600 | 600 | 0 | #REF! |  | 0 | 0 | 0 | #REF! | 600 | 0 | 0 | 0 | 0 | 600 |  | 600
|  | LCP-210213 | N/A | 21/0110 | 2021 | 2021-10-07 | 2021-11-10 |  | -793.336 | 2023-05-11 | 2023-11-10 | [5 empty] | BRZ |  |  | New | 4829206 | PROJETO | EBENÉZER DAINEZ | LAPG - CHARGER FOR ELETRIC VEHICLE | New Business | REL | Aprovado em 10/11 Será entregue dia 17/12 - estações de recarga | 2023-05-30 | 2023-09-30 | 2023-09-30 | [5 empty] | #REF! | [10 empty] | 244.7538 | 10.2572 | 255.011 | 8.2792 | [22 empty] | 9 | 8.2792 | 8.2792 | 215.45 |  | 21.7 | 30 | 50 | 80 | 33.75 | [6 empty] | 0 | [12 empty] | 0.72081 | 0 | 0 | 8.2792 | 223.7292 | 195 | 28.7292 | #REF! |  | 0 | 0 | 0 | #REF! | 244.7538 | 8.2792 | 7.5473 | 15.0295 | 30.8559 | 213.8978 |  | 215.45
| 156 | LCP-210215 |  |  | 2021 | 2021-10-07 | 2021-11-19 |  | -784.336 | 2023-05-20 | 2023-11-19 | [5 empty] | AME | FACIL | FACILIDADES | New | 4878328 | PROJETO | CARLOS SERAFIM | AME - FIRE PROTECTION ADEQUACY | EHS | REL |  | 2023-05-20 | 2023-05-20 | 2023-09-30 | [5 empty] | #REF! | [10 empty] | 239 | 0 | 239 | 0 | [25 empty] | 239 |  |  | 40 | 40 | 40 | 40 | 40 | 39 | [17 empty] | 0 | 0 | 0 | 0 | 239 | [8 empty] | 239 | 0 | 0 | 173.7442 | 173.7442 | 65.2558
|  | LCP-210217 |  |  | 2021 | 2021-11-18 | 2021-12-02 |  | -770.336 | 2023-06-02 | 2023-12-02 | [5 empty] | BRZ | STAFF | GERAL | New |  | PROJETO | RICARDO TEIXEIRA | LAPG - PROVING GROUNDS REPAVE PHASE 1 | Facilities Sustaining | REL | Aprovado em 02/12 | 2023-06-02 | 2023-10-02 | 2023-10-02 | [5 empty] | #REF! | [10 empty] | 233.4 | 19.5 | 252.9 | 15.538 | [23 empty] | 15.538 | 15.538 | 217.9 | 19.5 | 35 | 25 | 27 | 30 | 27.4 | 27 | 27 | [17 empty] | -15.538 | 0 | 0 | 15.538 | [9 empty] | 233.4 | 15.538 | 15.6872 | 0 | 31.2251 | 202.1749
|  | LCP-210218 | N/A |  | 2021 | 2021-10-08 | 2021-11-22 |  | -781.336 | 2023-05-23 | 2023-11-22 | [5 empty] | BRZ |  |  | New | 4878446 | PROJETO | RICARDO TEIXEIRA | LAPG - NEW ELECTRICAL WIRE BOX SEPARATE WATER AND CABLES | Facilities Sustaining | REL | Aprovado em 22/11 | 2023-05-30 | 2023-09-30 | 2023-09-30 | [5 empty] | #REF! | [10 empty] | 74 |  | 74 | 43.12 | [23 empty] | 43.12 | 43.12 | 30.9 |  |  |  | 30.9 | [21 empty] | -43.12 | 0 | 0 | 43.12 | [9 empty] | 74 | 43.12 | 0 | 0 | 43.12 | 30.88
|  | LCP-210220 | N/A |  | 2021 | 2021-10-11 | 2021-11-22 |  | -781.336 | 2023-05-23 | 2023-11-22 | [5 empty] | AME | A | BANBURY | New | 4878535 | PROJETO | HEDSLEY QUINTAL | AME - OVERHAUL CHILLER AND FANCOIL - MIXER BB03 | Facilities Sustaining | REL | Aprovado em 22/11 | 2023-05-30 | 2023-09-30 | 2023-09-30 | [5 empty] | #REF! | [10 empty] | 132.415 |  | 132.415 | 0 | [25 empty] | 132.42 |  | 27 | 27 | 41 | 37.42 | [20 empty] | 0 | 0 | 0 | 0 | [9 empty] | 132.415 | 0 | 95.6551 | 21.42 | 117.0751 | 15.3399
|  | LCP-210221 | N/A |  | 2021 | 2021-10-13 | 2021-11-22 |  | -781.336 | 2023-05-23 | 2023-11-22 | [5 empty] | AME | A | CALANDRA | New | 4878797 | PROJETO | HEDSLEY QUINTAL | AME - CREEL ROOM E FANCOIL #11 UNISTEEL | Facilities Sustaining | REL | Aprovado em 22/11 | 2023-05-30 | 2023-09-30 | 2023-09-30 | [5 empty] | #REF! | [10 empty] | 56.115 |  | 56.115 | 0 | [25 empty] | 56.12 |  | 29 | 27.12 | [22 empty] | 0 | 0 | 0 | 0 | [9 empty] | 56.115 | 0 | 23.3011 | 24.1319 | 47.4329 | 8.6821
|  | LCP-210237 |  |  | 2021 | [11 empty] | AME | A | BANBURY | Em aprovação 2022 |  | PROJETO | RICARDO ALNIEZI | AME - Pigment Room | Capability | CRTD | Em estudo | [8 empty] | #REF! | [12 empty] | 0 | 0 | [25 empty] | 9000 | 0 | 0 | 0 | 0 | 0 |  |  | 9000 |  |  |  | 0 | 19000 | 1583.3333 | 1583.3333 | 1583.3333 | 1583.3333 | 1583.3333 | 1583.3333 | 1583.3333 | 1583.3333 | 1583.3333 | 1583.3333 | 1583.3333 | 1583.3333 | 0 | 0 | 0 | 0 | 9000 | 9000 | 0 | #REF! |  | 0 | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | #N/A | #N/A
|  | LCP-220006 |  |  | 2022 | [11 empty] | AME | STAFF | ENGENHARIA | Em aprovação 2022 |  | PROJETO | RICARDO ALNIEZI | AME - 2022 MISCELLANEOUS ANNUAL BUDGET | Facilities Sustaining | CRTD | 2022 Carta Suporte em andamento - | [8 empty] | #REF! | [12 empty] | 0 | 0 | [25 empty] | 900 |  |  |  | 45 | 45 | 45 | 135 | 135 | 135 | 135 | 135 | 90 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 900 | 900 | 0 | #REF! |  | 0 | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 |  | 900
|  | LCP-220012 |  |  | 2022 | [11 empty] | AME | A | CALANDRA | Em aprovação 2022 |  | PROJETO | DIEGO CASTANHARO | AME - New rolls for hotformer | Quality | CRTD | [23 empty] | 0 | [25 empty] | 160 |  |  |  |  | 40 | 60 | 60 | [5 empty] | 185.64 |  | 61.88 | 61.88 | 61.88 | [9 empty] | 0 | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 2021 | [11 empty] | AME | UTIL | SUBESTAÇÃO | Em aprovação |  | PROJETO | HUELITON MAGNANI | UPGRADE (06) SYNCHRONOUS VARIXX AND PROT. MODULES | Energy Conservation | CRTD | Não excluir esta linha. Pois tem o valor do AOP alocado neste projeto. Cancelado em 2021 | [8 empty] | #REF! | [9 empty] | 75.641 |  |  | 0 | 0 | [25 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | #REF! |  | 0 | 0 | 0 | #REF! | [7 empty] | 0
[5 empty] | 2021 | [11 empty] | AME | A | ENTUBADORA | Em aprovação |  | PROJETO | HUELITON MAGNANI | PICKER ROLL 8X8 |  | CRTD | Não excluir esta linha. Pois tem o valor do AOP alocado neste projeto. Projeto se tornou um Quartely | [8 empty] | #REF! | [12 empty] | 0 | 0 | [25 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | #REF! |  | 0 | 0 | 0 | #REF! | [7 empty] | 0
[5 empty] | 2021 | [11 empty] | AME |  |  | Em aprovação |  | PROJETO | HUELITON MAGNANI | ADEQUAÇÃO NR 12 - E1/E2 & LRF | Facilities Sustaining | CRTD | Não excluir esta linha. Pois tem o valor do AOP alocado neste projeto. Cancelado em 2021 | [8 empty] | #REF! | [9 empty] | 133.5 |  |  | 0 | 0 | [25 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | #REF! |  | 0 | 0 | 0 | #REF! | [7 empty] | 0
| 230 | x1 | [14 empty] | AME |  |  | New |  | Ajuste Reg | REGIÃO | AME - EQUIPMENT IN TRANSIT | Facilities Sustaining | [10 empty] | #REF! | [6 empty] | -4344.2748 | 0 | 39.2994 | 0 |  |  | 0 | 16.8886 | 0 | 0 | 0 |  | 0 | 0 | 0 | 732 | 0 | -213.9559 | -520 | 783.6615 | -783.6615 | -940 |  |  | -361.7 | -126.8519 |  | -217.965 |  | 0 |  |  |  | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 16.8886 | 0 | 16.8886 | 16.8886 | 0 | #REF! |  | 0 | 1301.7056 | -1066.8519 | #REF! | [6 empty] | 0 | 0
| 231 | x2 | [14 empty] | AME |  |  | New |  | Ajuste Reg | REGIÃO | AME - REGIONAL ADJUSTMENT | Facilities Sustaining | [10 empty] | #REF! | [7 empty] | 0 | 134.0538 | 162.7686 |  |  | 0 | -105.7937 | 0 | 162.7686 | 0 | -35.6089 | 0 | 133.2495 | 0 | 8.2864 | 0 | -451.5675 | 0 | -49.4192 |  | 21.17 |  | -4.3969 |  | 4.1974 |  | 57.8373 |  | 47.6895 |  |  |  | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | -105.7937 | 0 | -105.7937 | -153.4833 | 47.6895 | #REF! |  | 260.4093 | -492.7003 | 20.9705 | #REF! | [6 empty] | 0 | 0
[5 empty] | 2021 | [11 empty] | RET |  |  | Em aprovação |  | PROJETO | CHARLES BARBAN | AER - MOLD FOR NEW TIRE RETREAD | Facilities Sustaining | CRTD | Não excluir esta linha. Pois tem o valor do AOP alocado neste projeto. Cancelado em 2021 | [8 empty] | #REF! | [9 empty] | 80 |  |  | 0 | 0 | [25 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | #REF! |  | 0 | 0 | 0 | #REF! | [7 empty] | 0
| 163 | LCP-200077 |  | 20/0038 | 2020 | 2020-02-28 | 2020-05-28 | 2021-09-20 | 480 | 2021-11-26 | 2022-05-28 | [5 empty] | AME | A | BANBURY | Carryover | 2815734 | PROJETO | GUSTAVO PARRAS | AME - Bijinic Tank | Quality | TECO | Projeto finalizado. Pode ser encerrado (CLOSE). | OK | 2021-10-31 | 2022-03-31 | [5 empty] | #REF! | [6 empty] | 0 | 180 | 134.9855 | 63.784 | 213.85 | 41 | 254.85 | 71.7968 | 15 | 6.7839 | 10 | 11.0815 | 6.5 | 6.0356 | 15 | 16.2741 | 2 | 5.2538 | 7 | 22.0468 | 0.1 | 0.05324 |  | -0.21704 | 5 | 3.6413 |  | 0.84046 |  |  |  | 0.00314 | 0.00314 | 0 | [12 empty] | 0 | [12 empty] | -0.00314 | 0 | 71.7937 | 0.00314 | 71.7968 | 71.7937 | 0.00314 | #REF! |  | 23.901 | 43.5748 | 3.4775 | #REF! | 213.85 | 206.7824 | 0 | 0 | 206.7824 | 7.0676 | 0 | 0
| 137 | LCP-190213 |  | 20/0006 | 2019 | 2019-09-08 | 2019-11-02 | 2021-05-05 | 550 | 2021-05-02 | 2021-11-01 |  | SIM | SIM | AQ4/21 |  | AME | B2 | PREPARAÇÃO | Carryover | 2357502 | PROJETO | HUELITON MAGNANI | ALPHA SHEAR LETOFF TREATMENT | Productivity | CLSD | OK, FINALIZADO | OK | 2021-09-30 | 2021-09-30 | [5 empty] | #REF! | NÃO POSSUI RISCOS | NÃO POSSUI RISCOS | NÃO POSSUI RISCOS | N/A | N/A | N/A | 0 | 130.1218 | 98.993 | 32.8948 | 138.869 | 4.69 | 143.559 | 34.2895 | 2 | -0.10516 | 2 | 3.8985 | 0 | 9.5626 | 3.61 | 2.5694 | 12.7 | 10.0885 | 8 | 0.26028 | 7.7 |  | 7.7 | 0.63801 | 7.1 | 7.0304 | 0.8 |  | 0.8 | 0.56974 |  | -0.22267 | -0.22267 | 0 | [12 empty] | 0 | [12 empty] | 0.22267 | 0 | 34.5122 | -0.22267 | 34.2895 | 34.7425 | -0.45293 | #REF! |  | 13.3559 | 12.9181 | 7.6684 | #REF! | 138.869 | 133.1134 | 0 | 0 | 133.1134 | 5.7556 | 0 | 0
| 234 | LCP-210196 | Informar |  | 2021 | 2021-09-09 | 2021-10-14 |  | -819.336 | 2023-04-14 | 2023-10-14 | [5 empty] | AME | B1 | VULCANIZAÇÃO | New | 4741958 | PROJETO | CARLOS SERAFIM | AME - (8) PCI Cavities | Quality | REL | Proteção de NR-12, 23/12 | 2023-03-31 | 2023-08-30 | 2023-08-31 | [5 empty] | #REF! | [10 empty] | 715 | 8.2 | 723.2 | 12.1136 | [21 empty] | 3.1735 | 4.7 | 8.9401 | 8.9401 | 700.6776 |  |  | 7.6776 | 130 | 10 | 384 | 50 | 50 | 50 | 12 | 7 |  | 0 | [12 empty] | -4.2401 | 0 | 3.1735 | 8.9401 | 712.7912 | 613 | 99.7912 | #REF! |  | 0 | 0 | 0 | #REF! | 715 | 11.4595 | 7.5108 | 0 | 18.9703 | 696.0297 | 715 | -14.3224
Formulas:
Data TECO (politica 18 meses ~ 547 dias) = IF([Data de Aprovação (GBS)]="","",[Data de Aprovação (GBS)]+547)

## AME - Quarterly 2021 (hidden)
[20 empty] | APROVADO |  |  | 878960 |  | 833578.08 | 0 | 0 | 0 | 9280.27 | 38738.54 | 79836.04 | 57965.02 | 46265.05 | 154583.82 | 92279.73 | 145141.02 | 209488.59 | 27148.5914 | 42841.51 | -2.7586 | -2.7586 | 27151.35 | -3626.82 | -790.61 | 0 | 0 | 878959.24 | 830815.43 | 26964.63 | 0 | 857780.06 | 21179.18 | 11807.4704 | 0
| GESTÃO DE PROJETOS QUARTELY 2021 ($) | [23 empty] | 833.5781 | 0 | 0 | 0 | 9.2803 | 38.7385 | 79.836 | 57.965 | 46.2651 | 154.5838 | 92.2797 | 145.141 | 209.4886 | 27.1486 | 42.8415 | -0.0027586 | -0.0027586 | 27.1513 | -3.6268 | -0.79061
[47 empty] | 0.76 | 235554.43
[23 empty] | 0 |  |  | 0 |  |  | 127854.85 |  |  | 258813.89 |  |  | 446909.34
[21 empty] | 816694 | 0 |  |  | 833578.08 | 0 | 0 | 0 | 9280.27 | 38738.54 | 79836.04 | 57965.02 | 46265.05 | 154583.82 | 92279.73 | 145141.02 | 209488.59 | [7 empty] | 0 | 0 | 878959.24 | 830815.43 | 26964.63 | 0 | 857780.06 | 21179.18
0 | N. | NUM. PROJETO (WBS) | NÚMERO NO HOPPER | OSEP | HOPPER APROVADO | Passo atual no Hopper | Parado com: | Comentários Hopper | ANO | DATA DE LIBERAÇÃO | DATA CONCLUSÃO | Data Encerramento (politica 12 meses) | PLANTA | DIVISÃO | TNC | SOLICITANTE | LÍDER | NOME PROJETO | PROJECT TYPE | SYSTEM STATUS SAP | BUDGET ORIGINAL APROVADO | BUDGET FINAL APROVADO | COMENTÁRIO STATUS | Área do Projeto | TOTAL 2021 | Jan Real | Fev Real | Mar Real | Abr Real | Mai Real | Jun Real | Jul Real | Ago Real | Set Real | Out REAL | Nov REAL | Dez REAL | TOTAL 2022 Carryover | Jan Obj | Jan Real | Jan Eng | Fev | Mar | Abr | Comparativo REAL vs ESTIMADO ENG | Comentários sobre o que falta comprometer | BUDGET | ACTUAL | COMM PO | COMMITMENT | ASSIGNED | AVALILABE | Diferença com o Budet | Retirar | Budget final
| 1 | LCP-210007-01 | [9 empty] | -45758.336 | AME |  |  |  | DISPONIVEL | CONTINGENCIA |  | EM EXECUÇÃO |  |  | CONTINGENCIA |  | 0 | [12 empty] | 0 | 7000 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2 | LCP-210007-02 | 2223 |  | NÃO | CALC ROI | LAIS |  | 2021 | 2021-03-17 |  | -1485.336 | AME | A | PREPARAÇÃO | JUNIOR BUENO | HUELITON MAGNANI | UPG SISTEMA DE FREIO LET OFF ISO#5 | Facilities Sustaining | ENCERRADO | 49865 |  |  |  | 47642.12 |  |  |  |  | 9895.51 | 16846.78 | 17774.95 |  | 291.84 | 364.97 | 2468.07 |  | 0 | [8 empty] | 47642.12 | 47642.12 | 0 | 0 | 47642.12 | 0 | 0
| 3 | LCP-210007-03 | 1910 |  | SIM | BUDGET | EBENEZER |  | 2021 | 2021-03-17 |  | -1485.336 | AME | A | GERAL | CELSO COSTA | HUELITON MAGNANI | NIP POINT EM ESTEIRAS CTI-055-11-00101 | EHS | ENCERRADO | 49938 |  |  |  | 46816.19 |  |  |  |  | 2290.81 | 4665.37 | 4922.41 | 9590.77 | 9483.94 | 14836 |  | 1026.89 | 0 | [8 empty] | 46656.36 | 46816.19 | 0 | 0 | 46816.19 | -159.83 | -159.83
| 4 | LCP-210007-04 | 9437 |  | NÃO | CALC ROI | LAIS | Calculo ROI está com Eloides, precisa transf. Para a Lais | 2021 | 2021-03-17 |  | -1485.336 | AME | A | ENTUBADORA | ROBERTO DANEZI | HUELITON MAGNANI | BENCHMARK PICKER ROLL - CHILE | Productivity | ENCERRADO | 45000 |  |  |  | 29055.99 | [8 empty] | 451.31 |  | 22103.5 | 6501.18 | 0 | [7 empty] | Projeto On Hold | 29666.01 | 29055.99 | 0 | 0 | 29055.99 | 610.02 | 610.02
| 5 | LCP-210007-05 | 4930 |  | SIM | BUDGET | EBENEZER | Aprovado | 2021 | 2021-03-17 |  | -1485.336 | AME | B2 | VULCANIZAÇÃO | REINALDO CREN | HUELITON MAGNANI | CENTRALIZADOR DE PNEUS ESTEIRAS AÉREAS | EHS | ENCERRADO | 49756 |  | Serviço com a empresa LGS |  | 37869.48 | [8 empty] | 2107.54 | 5505.27 | 3884.98 | 26371.69 | 4726.0492 |  | -4.7308 | -4.7308 | 4730.78 |  | -1279.09 |  |  | 38834.73 | 33138.7 | 5024.17 | 0 | 38162.87 | 671.86 | -3760.7992
| 6 | LCP-210007-06 | 10607 |  | NÃO | CALC ROI | LAIS |  | 2021 | 2021-03-17 |  | -1485.336 | AME | STAFF | GERAL | MARCELO SIQUEIRA | HUELITON MAGNANI | ADEQUAÇÃO DE VESTIÁRIOS E BANHEIROS | EHS | ENCERRADO | 35000 |  |  | Utilidades/Facilidades | 27087.66 |  |  |  |  | 9409.9 | 13789.53 | 3888.23 | [5 empty] | 0 | [8 empty] | 27087.66 | 27087.66 | 0 | 0 | 27087.66 | 0 | 0
| 7 | LCP-210007-07 | 11017 |  | NÃO | APROV FINANÇAS | SARAH PREDOZA |  | 2021 | 2021-03-17 |  | -1485.336 | AME | A | CALANDRA | RICARDO SEVERNINI | DIEGO CASTANHARO | TRANSF EXTRUSORA Q6 - CAL4R2 E ESTEIRA NOVA | EHS | ENCERRADO | 49665 |  | CANCELAR Pedido em aberto |  | 19805.59 | [9 empty] | 4867.69 | 14627.82 | 310.08 | 0 |  |  |  |  | 90.27 |  |  | Sobra | 20115.99 | 19805.59 | 0 | 0 | 19805.59 | 310.4 | 310.4
| 8 | LCP-210007-08 | 10392 | 21/0030 | NÃO | CALC ROI | LAIS |  | 2021 | 2021-03-17 |  | -1485.336 | AME | A |  | GABRIEL ROMAGNOLO | DIEGO CASTANHARO | MELHORIAS CARRO DUMMY | Capability | ENCERRADO | 23000 |  |  |  | 17700.09 |  |  |  | 122.98 | 2555.41 | 71.21 | 2360.86 | 12589.63 |  |  |  |  | 0 | [8 empty] | 17700.09 | 17700.09 | 0 | 0 | 17700.09 | 0 | 0
| 9 | LCP-210007-09 | 10770 | 21/0029 | NÃO | CALC ROI | LAIS |  | 2021 | 2021-03-17 |  | -1485.336 | AME |  |  | JOAO DA SILVA | DIEGO CASTANHARO | SISTEMA DE TRAVAMENTO LOTOTO NR 12 | EHS | ENCERRADO | 49000 |  | CANCELAR Pedido em aberto |  | 27153.01 |  |  |  |  | 2277.35 | 1701.22 | 2014.12 | 1788.4 | 11860.68 | 5967.78 | 1427.38 | 116.08 | 0 | [8 empty] | 27188.34 | 27153.01 | 0 | 0 | 27153.01 | 35.33 | 35.33
| 10 | LCP-210007-10 | 9910 | 21/0031 | NÃO | CALC ROI | LAIS |  | 2021 | 2021-03-17 |  | -1485.336 | AME | A | CALANDRA | JUNIOR BUENO | DIEGO CASTANHARO | LINHA DE SEGURANÇA DA CALZ (CREEL ROOM) | Productivity | ENCERRADO | 30000 |  |  |  | 29826.64 |  |  |  |  | 9344.83 | 3472.32 | 151.07 |  | 2113.35 | 7205.1 | 6061.07 | 1478.9 | -0.3128 |  | -0.3128 | -0.3128 |  | 33.38 |  |  | Sobra 795 | 29828.3 | 29513.84 | 0 | 0 | 29513.84 | 314.46 | 1.9728
| 11 | LCP-210007-11 | 713 | 21/0032 | NÃO | APROV FINANÇAS | SARAH PREDOZA |  | 2021 | 2021-03-17 |  | -1485.336 | AME | B1 | PREPARAÇÃO | WILIAN CANTELLI | HUELITON MAGNANI | UPGRADE PLC5 FISCHER 01 | Facilities Sustaining | ENCERRADO | 32000 |  |  |  | 17314.16 |  |  |  | 3449.86 | 2964.73 | 3700.23 |  | 5398.46 | 2100.57 | -299.69 |  |  | 0 | [8 empty] | 17314.16 | 17314.16 | 0 | 0 | 17314.16 | 0 | 0
| 12 | LCP-210007-12 | 2228 |  | NÃO | AG. INFO SOLICITANTE | DANILO LEONE | Inicialmente o projeto foi recusado pelo Alexandre, porém foi aceito. Necessário aceitar no Hopper. | 2021 | 2021-04-02 |  | -1470.336 | AME | B2 | CONSTRUÇÃO | DANILO LEONE | HUELITON MAGNANI | GUIA LINEAR PARA APLICAÇÃO DE APEX NGTTS | Productivity | ENCERRADO | 10000 |  | Janeiro: Cilindros FESTO - Chega em 13/01 |  | 37762.34 | [6 empty] | 3199.58 |  | 5369.49 | 2861.12 | 6658.49 | 19673.66 | 299.4759 | 1018.41 | -0.52411 | -0.52411 | 300 |  |  |  | SC de Materiais faltantes será aberta até 15/10 | 39230.93 | 37238.23 | 391.05 | 0 | 37629.28 | 1601.65 | 1169.1141
| 13 | LCP-210007-13 | 1377 |  | NÃO | RECUSADO | - | CANCELADO | 2021 | 2021-04-02 |  | -1470.336 | AME | STAFF | GERAL | MARCELO SOARES | HUELITON MAGNANI | INTERFACE GESTÃO MÁQUINA EPI | EHS | CANCELADO | 8000 |  |  |  | 0 | [12 empty] | 0 | [14 empty] | 0
| 14 | LCP-210007-14 | 9813 |  | NÃO | CALC ROI | LAIS |  | 2021 | 2021-04-02 |  | -1470.336 | AME | B1 | PREPARAÇÃO | WILLIAN CANTELLI | HUELITON MAGNANI | DETECÇÃO FIO SOLTO AMORT. FSC#01 E AB#02 | Quality | ENCERRADO | 44500 |  |  |  | 49052.87 | [6 empty] | 1485.78 | 1358.42 | 14413.53 | 12756.92 | 3356.21 | 15682.01 | -0.30038 |  | -0.30038 | -0.30038 |  |  |  |  | SC será aberta até 15/10 | 48054.15 | 48752.49 | 0 | 0 | 48752.49 | -698.34 | -998.4196
| 15 | LCP-210007-15 | 5050 | 21/0034 | NÃO | APROV FINANÇAS | SARAH PREDOZA |  | 2021 | 2021-04-02 |  | -1470.336 | AME | A | CALANDRA | JUNIOR BUENO | DIEGO CASTANHARO | CAL. Z - UPG DRIVE PF700S POR PF755 | Facilities Sustaining | ENCERRADO | 50000 |  |  |  | 47598.3 |  |  |  | 254.99 |  | 31514.63 | 884.92 | 2095.86 | 12128.91 | 718.99 |  |  | 0 | [8 empty] | 47598.3 | 47598.3 | 0 | 0 | 47598.3 | 0 | 0
| 16 | LCP-210007-16 | 11067 |  | NÃO | CALC ROI | LAIS |  | 2021 | 2021-04-02 |  | -1470.336 | AME | B1 | PREPARAÇÃO | MAGRI | HUELITON MAGNANI | B1- PASSADEIRA DE FORRO / MAQ. REFUGO | Productivity | ENCERRADO | 49500 |  |  |  | 48913.78 | [8 empty] | 18441.09 | 5048.88 | 6051.14 | 19372.67 | -0.67444 |  | -0.67444 | -0.67444 |  | 592.01 |  |  | SC de M.O será aberta até 15/10 | 49784.74 | 48239.34 | 0 | 0 | 48239.34 | 1545.4 | 871.6344
| 17 | LCP-210007-17 | 3268 | 21/0035 | NÃO | APROV FINANÇAS | SARAH PREDOZA |  | 2021 | 2021-04-02 |  | -1470.336 | AME | A | BANBURY | PEDROSA | DIEGO CASTANHARO | MIXER#7 - UPG DRIVE PF700S POR PF755 | Facilities Sustaining | ENCERRADO | 42000 |  | CANCELAR Pedido em aberto |  | 45072.38 | [5 empty] | 266.18 | 378.48 | 66.35 |  | 23886.33 | 17640.8 | 2834.24 | -0.36984 |  | -0.36984 | -0.36984 | [5 empty] | 45350.31 | 44702.54 | 0 | 0 | 44702.54 | 647.77 | 278.2998
| 18 | LCP-210007-18 | 2957 | 21/0036 | NÃO | CALC ROI | LAIS |  | 2021 | 2021-04-02 |  | -1470.336 | AME | B2 | PREPARAÇÃO | RODRIGO BARBOZA | HUELITON MAGNANI | PLY CUTTER - REDUÇÃO DE BAD GOODS E FRICÇÃO | Productivity | ENCERRADO | 10000 |  |  |  | 15580.83 | [6 empty] | 10917.17 |  | 2607.04 | 41.54 |  | 2015.08 | 0 | [8 empty] | 15797.46 | 15580.83 | 0 | 0 | 15580.83 | 216.63 | 216.63
| 19 | LCP-210007-19 | 3236 | 21/0037 | NÃO | APROV FINANÇAS | SARAH PREDOZA |  | 2021 | 2021-04-02 |  | -1470.336 | AME | A | BANBURY | PEDROSA | DIEGO CASTANHARO | MIXER#4 - UPG DRIVE DO MOINHO 100" | Facilities Sustaining | ENCERRADO | 24000 |  |  |  | 48937.29 | [8 empty] | 37069.7 | 2472.79 | 5304.55 | 4090.25 | -0.40268 |  | -0.40268 | -0.40268 |  | 50.73 |  |  | Sobra | 48917.74 | 48534.61 | 0 | 0 | 48534.61 | 383.13 | -19.1473
| 20 | LCP-210007-20 | 11895 |  | NÃO | CALC ROI | LAIS |  | 2021 | 2021-04-02 |  | -1470.336 | AME | FACIL | MANUTENÇÃO | CLAUDIO ROQUE JUNIOR | HUELITON MAGNANI | RETROFIT SIST. HIDRAULICO EMPILHADEIRA FILOMENA | Productivity | ENCERRADO | 7500 |  |  | Utilidades/Facilidades | 5452.44 |  |  |  | 5452.44 | [8 empty] | 0 | [8 empty] | 5452.44 | 5452.44 | 0 | 0 | 5452.44 | 0 | 0
| 21 | LCP-210007-21 | 4057 | 21/0040 | NÃO | CALC ROI | LAIS |  | 2021 | 2021-04-02 |  | -1470.336 | AME | A | ENTUBADORA | ROBERTO DANEZI JUNIOR | DIEGO CASTANHARO | ENTUBADORA - AUTOMAÇÃO DE SETUP DE MÁQ. | Productivity | ENCERRADO | 21000 |  |  |  | 5898.6 | [8 empty] | 5898.6 |  |  |  | 0 | [8 empty] | 5898.6 | 5898.6 | 0 | 0 | 5898.6 | 0 | 0
| 22 | LCP-210007-22 | 7885 | 21/0039 | NÃO | CALC ROI | LAIS | Sarah solicitou revisão ao Engenheiro Responsavel | 2021 | 2021-04-02 |  | -1470.336 | AME | A | PREPARAÇÃO | GABRIEL ROMAGNOLO | DIEGO CASTANHARO | ISOLADORAS - CHECKLIST POKA YOKE | Quality | ENCERRADO | 15000 |  | CANCELAR Pedido em aberto |  | 42455.95 | [5 empty] | 3808.57 | 8753.58 | 4981.21 | 11994.22 | 275.76 | 10223.83 | 2418.78 | 0 |  |  |  |  | 50.54 |  |  |  | 43278.97 | 42455.95 | 0 | 0 | 42455.95 | 823.02 | 823.02
| 23 | LCP-210007-23 | 2730 |  | NÃO | AG. INFO SOLICITANTE | GUILHERME TUPY | Alexandre solicitou revisão ao Solicitante | 2021 | 2021-07-27 |  | -1353.336 | AME | B2 | CONSTRUÇÃO | PAULO FIGEURIA | HUELITON MAGNANI | SISTEMA DE TRANSMISSÃO LET-OFF DE DG | Productivity | ENCERRADO | 49840 |  | Janeiro: 1,4K Módulo de Segurança - INTERENG - Chega até 31/01 |  | 37228.1 | [6 empty] | 1233.87 | 4869.26 | 5789.45 | 2511.55 | 7733.59 | 15090.38 | 1200 | 1278.72 |  |  | 1200 |  |  |  | SC será aberta até 15/10 | 40117.76 | 37228.1 | 1278.72 | 0 | 38506.82 | 1610.94 | 1689.66
| 24 | LCP-210007-24 | 14309 |  | SIM | BUDGET | EBENEZER | Aprovado | 2021 | 2021-06-30 |  | -1380.336 | AME | UTIL | GERAL | ALEXANDRE STOCO | HUELITON MAGNANI | LIMPADORA DE TROCADORES DE CALOR SHELL & TUBE | Energy Conservation | ENCERRADO | 5100 |  |  | Utilidades/Facilidades | 5225.45 | [7 empty] | 3526.69 |  | 866.05 |  | 832.71 | 0 |  |  |  |  | -5225.45 |  |  |  | 5211.4 | 5225.45 | 0 | 0 | 5225.45 | -14.05 | -14.05
| 25 | LCP-210007-25 | 10611 |  | SIM | APROV FINANÇAS | SARAH PREDOZA | Aprovado | 2021 | 2021-07-05 |  | -1375.336 | AME | UTIL |  | MARIANA BRASIL | DIEGO CASTANHARO | ADEQUAÇÃO DIQUES CONTENÇÃO - TANQUES EXT | EHS | ENCERRADO | 30000 |  |  |  | 24034.81 | [10 empty] | 24034.81 |  | 0 | [8 empty] | 24034.81 | 24034.81 | 0 | 0 | 24034.81 | 0 | 0
| 26 | LCP-210007-26 | 3278 |  | SIM | APROV FINANÇAS | SARAH PREDOZA | Aprovado | 2021 | 2021-07-05 |  | -1375.336 | AME | B2 | VULCANIZAÇÃO | EDUARDO ALVEZ | HUELITON MAGNANI | GATEWAY DH+ PARA PRENSAS COM SLC500 5/04 | Quality | ENCERRADO | 21830 |  | Janeiro: 4,8K Valvulas Importadas - SMC PNEUMATICOS - Chega em 18/01 |  | 15337.99 | [9 empty] | 2392.68 |  | 12945.31 | 4.292 | 4817.38 | 4.292 | 4.292 |  |  |  |  | Verificar com Felipe 18-10 | 19903.44 | 19629.95 | 0 | 0 | 19629.95 | 273.49 | 4561.158
| 27 | LCP-210007-27 | 14440 |  | SIM | APROV FINANÇAS | SARAH PREDOZA | Aprovado | 2021 | 2021-07-05 |  | -1375.336 | AME | A |  | ROBERTO DANEZI | DIEGO CASTANHARO | CARRO LAGARTA TM | EHS | ENCERRADO | 15200 |  |  |  | 14568.22 | [8 empty] | 12462.56 |  |  | 2105.66 | 0 | [8 empty] | 14730.87 | 14568.22 | 0 | 0 | 14568.22 | 162.65 | 162.65
| 28 | LCP-210007-28 | 18460 |  | NÃO | CALC ROI | LAIS |  | 2021 | 2021-10-04 |  | -1284.336 | AME | B2 | CONSTRUÇÃO | GUILHERME TUPY | HUELITON MAGNANI | ZIPPER ELETRICO PARA AS NGTTS | Productivity | ENCERRADO |  |  | Zipper Previsão de chegada até 31/12 Janeiro: Disjuntor e Fonte - Intereng - Chega em 31/01 |  | 25099.81 | [11 empty] | 25099.81 | 406.0557 | 8147 | 6.0557 | 6.0557 | 400 |  |  |  | U$ 7K de imposto + 7K de M.O de instação - SC será aberta até dia 15/10 | 29198.58 | 31461.61 | 160.19 | 0 | 31621.8 | -2423.22 | 3692.7143
| 29 | LCP-210007-29 |  |  | NÃO | INSERIR NO HOPPER | CESAR PENTEADO |  | 2021 | 2021-08-05 |  | -1344.336 | AME | A | CALANDRA |  | HUELITON MAGNANI | VULCAWELD - PRENSA PARA CREEL ROOM | Capability | EM EXECUÇÃO |  |  | Material: 14,7K + 40% imposto = 20,6K ICP: 210037 |  | 18797.44 | [11 empty] | 18797.44 | 20515.1853 | 20580 | -5.3847 | -5.3847 | 20520.57 | -537.41 | 488.48 |  | U$ 5,8K de impostos + SC de 2k de M.O será aberta até 15/10 (18/10) | 39400.55 | 13412.74 | 20110.5 | 0 | 33523.24 | 5877.31 | 87.9247
| 30 | LCP-210007-30 | 16080 |  | SIM | PROX RODADA TEN | ALEXANDRE MARTINS |  | 2021 | 2021-10-21 |  | -1267.336 | AME | A | CALANDRA | GABRIEL ROMAGNOLO | DIEGO CASTANHARO | UPGRADE SISTEMA MEDIÇÃO TEMPERATURA CAL41 | Productivity | CANCELADO |  |  |  |  | -11.73 | [10 empty] | 2237.47 | -2249.2 | 0.01173 |  | 0.01173 | 0.01173 | [5 empty] | 2237.47 | 0 | 0 | 0 | 0 | 2237.47 | 2249.1883
| 31 | LCP-210007-31 | 25855 |  | NÃO | INSERIR NO HOPPER | DIEGO RAGONHA |  | 2021 | 2021-10-21 |  | -1267.336 | AME | A | CALANDRA | GABRIEL ROMAGNOLO | DIEGO CASTANHARO | RETROFIT SIST.INFLACAO FVMs ASTEC | Productivity | ENCERRADO |  |  |  |  | 26688.18 | [10 empty] | 11327.31 | 15360.87 | 0 | [8 empty] | 30204.57 | 26688.18 | 0 | 0 | 26688.18 | 3516.39 | 3516.39
| 32 | LCP-210007-32 | 705 |  | NÃO | CALC ROI | LAIS |  | 2021 | 2021-12-09 |  | -1220.336 | AME | B1 | CONST. TBM | ALEXANDRE SANTOS | EBENÉZER DAINEZ | UPGRADE CENTRALIZADOR A LASER - TBM | Productivity | ENCERRADO |  |  |  |  | 19614.1 | [11 empty] | 19614.1 | -0.41821 |  | -0.41821 | -0.41821 |  | 1319.11 |  |  |  | 22522.39 | 18885.69 | 0 | 0 | 18885.69 | 3636.7 | 2908.7082
Formulas:
Data Encerramento (politica 12 meses) = IF([DATA CONCLUSÃO]<>"",[DATA CONCLUSÃO]-[DATA DE LIBERAÇÃO],EDATE([DATA DE LIBERAÇÃO],3)-NOW())

## Capex
WBS | PROJECT NAME | PROJECT TYPE | PREVIOUS STATUS SAP | STATUS COMPARISON | SAP STATUS (MACRO)
LCP-230060 | AMERICANA QUADRUPLEX EXTRUDER #7 | Capability | REL | #REF! | NO BUDGET
ICP-240041 | AME - CONSUMER EXPANSION PHASE 2 | Growth | REL | #REF! | NO BUDGET
LCP-220207 | AME PIGMENT WEIGHT SYSTEM | EHS | REL | #REF! | NO BUDGET
LCP-240193 | MC - CARBON PROJECT 17" - GRAVATAI | SAG | REL | #REF! | NO BUDGET
LCP-250006 | AME - 2025 MISCELLANEOUS ANNUAL BUDGET | Facilities Maintaining | REL | #REF! | NO BUDGET
ICP-200043 | (VMI) AMERICANA CONSUMER HMC TIRE BUILDING | Capability | REL | #REF! | NO BUDGET
LCP-200130 | AME - UPGRADE PLC PRESSES MRT (12 PRESSES) | Facilities Maintaining | REL | #REF! | NO BUDGET
LCP-250027 | LAPG - SAFER BARRIER | SAG | CRTD | #REF! | NO BUDGET
LCP-250014 | FSB - RACKS PHASE 1 | Facilities Maintaining | CRTD | #REF! | NO BUDGET
LCP-250026 | LAPG - OPTICAL FIBER SYSTEM UPDATE | SAG | CRTD | #REF! | NO BUDGET
LCP-210221 | AME - CREEL ROOM E FANCOIL #11 UNISTEEL | Facilities Maintaining | REL | #REF! | NO BUDGET
LCP-250025 | LAPG - GPS RADIO TRACK MONITORING SYSTEM | SAG | REL | #REF! | NO BUDGET
LCP-210146 | AME - NR12 - WIRE CALENDER - BRZ MANDATORY | EHS | REL | #REF! | NO BUDGET
ICP-210004 | AME - CONTOUR CORRECTION MACHINE | Quality | REL | #REF! | NO BUDGET
LCP-230255 | AME - NEW BALANCE AKRODYNE MP04 | Facilities Maintaining | REL | #REF! | NO BUDGET
LCP-210131 | AME - WOMEN'S RESTROOM | EHS | REL | #REF! | NO BUDGET
ICP-240027 | AME - METAL DETECTOR HOTFORMER | Quality | REL | #REF! | NO BUDGET
Waiting4 | AME - PROTECTO WIRE SYS | Facilities Maintaining | NO BUDGET | #REF! | NO BUDGET
ICP-240033 | AME - (03) TRANSFER ORING WYKO – NGTTS | Facilities Maintaining | REL | #REF! | NO BUDGET
ICP-230071 | AME - NEW BALANCE AKRODYNE MP04 | Facilities Maintaining | REL | #REF! | NO BUDGET
LCP-240194 | MC - NEW AIR COMPRESSOR - EPIACABA | SAG | REL | #REF! | NO BUDGET
LCP-210180 | AME -UPGRADE PLC MRT PRESSES (11 PRESSES) | Facilities Maintaining | REL | #REF! | NO BUDGET
LCP-250043 | MC - CLIMATIZER MBB MANUFACTURING CELL | SAG | CRTD | #REF! | NO BUDGET
LCP-230096 | AME - METAL DETECTOR HOTFORMER | Quality | REL | #REF! | NO BUDGET
ICP-150042 | LAPG GERAL - MISCELANIUS QUARTELY | Facilities Maintaining | CLSD | #REF! | NO BUDGET
ICP-160008 | UPGRADE OF MRT YXLON | Facilities Maintaining | CLSD | #REF! | NO BUDGET
ICP-160011 | WIRE CAL AUTOMATIC WIND UP & CUTE IN ANGLE | Facilities Maintaining | CLSD | #REF! | NO BUDGET
ICP-160022 | AMERICANA REPLACEMENT OF WIRE CORD DETEC | Facilities Maintaining | CLSD | #REF! | NO BUDGET
ICP-180007 | AMERICANA AVCB NEW WAREHOUSE-BLDG COMM | SAG | CLSD | #REF! | NO BUDGET
ICP-180009 | AMERICANA (3) 52" HYDRAULIC CONS PRESSES | Capability | CLSD | #REF! | NO BUDGET
ICP-180013 | AMERICANA 2ND MRT MESNAC | Capability | CLSD | #REF! | NO BUDGET
ICP-180015 | REPLACE PLC/CCM OF BATCH OFF MIXER#3 | Facilities Maintaining | CLSD | #REF! | NO BUDGET
ICP-180020 | BRAZIL GE MOUNTING PROJECT | SAG | CLSD | #REF! | NO BUDGET
ICP-180031 | AMERICANA FVM GRINDER AUTOMATION | Energy Conservation | CLSD | #REF! | NO BUDGET
ICP-180041 | BRS GEM PROJECT | SAG | CLSD | #REF! | NO BUDGET
ICP-180044 | AMERICANA MIXER #2 BODY REPLACEMENT | Facilities Maintaining | CLSD | #REF! | NO BUDGET
ICP-180053 | AMERICANA REPLACE PLC/CCM BO MIXER#3 | Facilities Maintaining | CLSD | #REF! | NO BUDGET
ICP-190027 | AMERICANA UPGRADE MRT XYLON X-RAY | Facilities Maintaining | CLSD | #REF! | NO BUDGET
ICP-190041 | AER - CORSAIR | SAG | CLSD | #REF! | NO BUDGET
ICP-190047 | AMERICANA TRANSFER O-RING, MONO CUTTER | Quality | CLSD | #REF! | NO BUDGET
ICP-190053 | AMERICANA AKROMARKER FOR FVM-AAA | Quality | CLSD | #REF! | NO BUDGET
ICP-200001 | AMERICANA INFLATION TESTING MACHINE ICP-200001 | Quality | CLSD | #REF! | NO BUDGET
ICP-200008 | AMERICANA UPGRADE KOKUSAI #1 | Facilities Maintaining | CLSD | #REF! | NO BUDGET
ICP-200023 | AME - BT DRUM WYKO | Facilities Maintaining | CLSD | #REF! | NO BUDGET
ICP-200024 | AME REWIND STAT COM TBM | Facilities Maintaining | CLSD | #REF! | NO BUDGET
ICP-200033 | AMERICANA MIXER #6 BODY REPLACEMENT | Facilities Maintaining | CLSD | #REF! | NO BUDGET
ICP-200037 | AME PCI (6) ROGERS 47" PRESSES | Capability | REL | #REF! | NO BUDGET
ICP-210002 | AMERICANA MIXER BB#07 | Facilities Maintaining | CLSD | #REF! | NO BUDGET
ICP-210011 | AME - UPGRADE DRIVE + MOTOR AC MILL MIXER#3 | Facilities Maintaining | REL | #REF! | NO BUDGET
ICP-210016 | AME FVM TGIS UPGRADE (CAMERAS PRETAS) | Facilities Maintaining | CLSD | #REF! | NO BUDGET
ICP-210031 | AME - CREEL ROOM TRANSFER GADSDEN | Facilities Maintaining | REL | #REF! | NO BUDGET
ICP-210032 | AME PNC PNEUMATIC CORE CONSTRUCTION | Capability | REL | #REF! | NO BUDGET
ICP-210037 | AME - VULCAWELD CREEL ROOM PRESS | Facilities Maintaining | CLSD | #REF! | NO BUDGET
ICP-210051 | AME UPGRADE WINDUP EXTR 8X8 SW | Capability | REL | #REF! | NO BUDGET
ICP-210053 | ICP - AME - (8) PCI CAVITIES | Quality | REL | #REF! | NO BUDGET
ICP-210069 | AME MICROPOISE AIT BALANCE | Facilities Maintaining | CLSD | #REF! | NO BUDGET
ICP-210070 | AME 2500HP MAIN MOTOR SPARE | Facilities Maintaining | REL | #REF! | NO BUDGET
ICP-220010 | AME OTR PRESS TRANSFER (AKRON) | Facilities Maintaining | REL | #REF! | NO BUDGET
ICP-220025 | AME COGEN OVERHAUL | Facilities Maintaining | REL | #REF! | NO BUDGET
ICP-220037 | FSB - NEW MAIN FRAME FLAT PRESS | Facilities Maintaining | CLSD | #REF! | NO BUDGET
ICP-220048 | FF B1 - UPGRADE PCHP-ETMS FVM MACHINES (AAA) | Facilities Maintaining | CLSD | #REF! | NO BUDGET
ICP-220049 | AME - MIXER #3 BODY REPLACEMENT | Facilities Maintaining | REL | #REF! | NO BUDGET
ICP-230001 | MICROPOISE FVM/DBM EQUIPMENT AND TGIS UPGRADES (FVM#03 E FVM#10) | Facilities Maintaining | REL | #REF! | NO BUDGET
ICP-230035 | AMERICANA 15" TOOLING FOR VMI MACHINES | Capability | REL | #REF! | NO BUDGET
ICP-230054 | AME - 2023 MISCELLANEOUS ANNUAL BUDGET | Facilities Maintaining | REL | #REF! | NO BUDGET
ICP-240029 | AME - (1) BEAD WINDER#8 | Facilities Maintaining | REL | #REF! | NO BUDGET
ICP-240038 | AMA - MIXER#1 LOADING CONVEYOR UPGRADE | Facilities Maintaining | REL | #REF! | NO BUDGET
LCP-160092 | STEAM COGEN | Energy Conservation | CLSD | #REF! | NO BUDGET
LCP-160138 | PCI IN (8) ROGERS MECHANICAL PRESSES | Capability | CLSD | #REF! | NO BUDGET
LCP-160208 | FLEXCORD SENSOR DETECTOR UPGRADE | Productivity | CLSD | #REF! | NO BUDGET
LCP-170013 | AME - NR12 - ADEQUATION OF NR12 COMPLIANCE PHASE III | EHS | CLSD | #REF! | NO BUDGET
LCP-170039 | GREEN TIRE DEBOOKER FOR MRT PRESSES | EHS | CLSD | #REF! | NO BUDGET
LCP-170065 | AME - ARTICULATED DRUM TIRE 20,5" GREADERLRF AND OTRLAMINATOR | Productivity | CLSD | #REF! | NO BUDGET
LCP-170069 | REPLACE AND UPGRADE OF ROLLS IN WIRE CALANDER | Facilities Maintaining | CLSD | #REF! | NO BUDGET
LCP-170077 | AMERICANA WIND UPLET OFF PHASE III | EHS | CLSD | #REF! | NO BUDGET
LCP-170099 | FAM PRODUCTIVITY PROJECTS | Productivity | CLSD | #REF! | NO BUDGET
LCP-170107 | WIRE CAL AUTOMATIC WIND UP & CUTE IN ANGLE | Quality | CLSD | #REF! | NO BUDGET
LCP-170118 | RET - THERMAL OIL BOILER | Facilities Maintaining | CLSD | #REF! | NO BUDGET
LCP-170154 | BRZ - AVCB NEW WAREHOUSE-BUILDING COMMERCIAL | SAG | CLSD | #REF! | NO BUDGET
LCP-170159 | AME - SEPARATED INNERLINER NEST#18 & #20 | Productivity | CLSD | #REF! | NO BUDGET
LCP-170161 | AME WAREHOUSE MANAGEMENT SYSTEM UPGRADE | SAG | CLSD | #REF! | NO BUDGET
LCP-170170 | AME - R1 MACHINE STITCHER UPGRADE | Productivity | CLSD | #REF! | NO BUDGET
LCP-170194 | UPG MOUNTINGLINE FOR MQB - ANCHIETA | SAG | CLSD | #REF! | NO BUDGET
LCP-170210 | AER - CURING EXHAUST SYSTEM - FSP | EHS | CLSD | #REF! | NO BUDGET
LCP-180002 | FAM AVCB PHASE II EMERGENCYLIGHTINING AND ALARMS | EHS | CLSD | #REF! | NO BUDGET
LCP-180003 | GEM PROJECT EMC GRAVATAÍ | SAG | CLSD | #REF! | NO BUDGET
LCP-180005 | QUICK CHANGE OVER NGTTS#3 | Productivity | CLSD | #REF! | NO BUDGET
LCP-180009 | VOC REDUCTION IN APEX APLIER | EHS | CLSD | #REF! | NO BUDGET
LCP-180010 | (3) NEW 52 HYDRAULIC CONSUMER PRESSES | Capability | CLSD | #REF! | NO BUDGET
LCP-180013 | MIXER#2 BODY REPLACEMENT | Facilities Maintaining | CLSD | #REF! | NO BUDGET
LCP-180014 | SEMI AUTOMATIC BEAD STAPLER | Productivity | CLSD | #REF! | NO BUDGET
LCP-180015 | UPGRADE OF DRIVES NRM#2 - CAL4R#2 | Facilities Maintaining | CLSD | #REF! | NO BUDGET
LCP-180018 | AUTOMATIC BARCODE READER - FF CONSUMER | Productivity | CLSD | #REF! | NO BUDGET
LCP-180019 | AME - ANNUAL MISCELANEOUS <50K ALL PLANTS | Facilities Maintaining | CLSD | #REF! | NO BUDGET
LCP-180043 | AME - REPLACEMENT OF HOTFORMER CHILLER | Energy Conservation | CLSD | #REF! | NO BUDGET
LCP-180049 | AME - UPG PLC OF BB#3 | Facilities Maintaining | CLSD | #REF! | NO BUDGET
LCP-180051 | BRZ - FAM WHLOADING DOCKS ADEQUACY - 5 REMAINING EQUIPMENTS | SAG | CLSD | #REF! | NO BUDGET
LCP-180056 | AME- CEMENT HOUSE COINTAIMENT AREA | EHS | CLSD | #REF! | NO BUDGET
LCP-180078 | BRZ - FAM WH SECURITY CONTROL (CONTROL SYSTEM & CAMERAS) | SAG | CLSD | #REF! | NO BUDGET
LCP-180080 | COMMERCIAL TIRE BUILDING MACHINE | Capability | CLSD | #REF! | NO BUDGET
LCP-180081 | GEM PROJECT SÃO CAETANO DO SUL | SAG | CLSD | #REF! | NO BUDGET
LCP-180082 | NEW RUBBER PROCESS ANALYZER (RPA) | Quality | CLSD | #REF! | NO BUDGET
LCP-180090 | RET - UPGRADE DRIVE GV3000 TO POWERFLEX EXTRUDER | Facilities Maintaining | CLSD | #REF! | NO BUDGET
LCP-180095 | AME - METAL DETECTOR IN CALANDERS (FORD PROJECT) | Quality | CLSD | #REF! | NO BUDGET
LCP-180097 | UPGRADE FACKTORLINK/ GML D#4 | Facilities Maintaining | CLSD | #REF! | NO BUDGET
LCP-180101 | RET - ANNUAL MISCELLANEOUS <50K ALL PLANTS | Facilities Maintaining | CLSD | #REF! | NO BUDGET
LCP-180104 | AME - FVM GRINDERS AUTOMATION | Energy Conservation | CLSD | #REF! | NO BUDGET
LCP-180108 | RET - ADEQ. OF NR17 & NR12 | EHS | CLSD | #REF! | NO BUDGET
LCP-180111 | REG -LAPG VDA FIRE PROTECTIONLINE | SAG | CLSD | #REF! | NO BUDGET
LCP-180113 | GENERATION CONTROL SYSTEM - POWER HOUSE ADEQUACY | Facilities Maintaining | CLSD | #REF! | NO BUDGET
LCP-180114 | LAMINATOR PROFILE AUTOMATION | Facilities Maintaining | CLSD | #REF! | NO BUDGET
LCP-180115 | AME - CLOSED WATER SYSTEM - MIXERS SUBSTATIONS | Energy Conservation | CLSD | #REF! | NO BUDGET
LCP-180116 | HVAC – CENTRAL OFFICE | Energy Conservation | CLSD | #REF! | NO BUDGET
LCP-180117 | AER - NEW ORBITREAD MACHINE | SAG | CLSD | #REF! | NO BUDGET
LCP-180137 | (10) VDF PANEL INSTALLATION | Energy Conservation | CLSD | #REF! | NO BUDGET
LCP-180139 | POWER HOUSE STEAM TURBINE | Energy Conservation | CLSD | #REF! | NO BUDGET
LCP-180142 | AME - NR12 - ADEQUACY OF NR12 COMPLIANCE - PHASE IV | EHS | CLSD | #REF! | NO BUDGET
LCP-180149 | EXHAUST SYSTEM -LINES A/B & G/H CONSUMER PRESSES | EHS | CLSD | #REF! | NO BUDGET
LCP-180150 | AER - SHEROGRAPHY UPGRADE (OBSEOLESCENCE AND SOFTWARE) | SAG | CLSD | #REF! | NO BUDGET
LCP-180155 | AER - NR12 - PROJECT | EHS | CLSD | #REF! | NO BUDGET
LCP-180157 | FIRE FIGHTING SYSTEM BUILDING 75 | EHS | CLSD | #REF! | NO BUDGET
LCP-180163 | 2018 MISCELLANEOUS PROJECT TO MC PLANTS | SAG | CLSD | #REF! | NO BUDGET
LCP-180174 | METAL DETECTOR IN EXTRUDERS | Quality | CLSD | #REF! | NO BUDGET
LCP-180177 | NEW DUCTS TO COMMERCIAL CURING AREA | EHS | CLSD | #REF! | NO BUDGET
LCP-180178 | WIND UPLET OFF NGTTS#5 & #8 | EHS | CLSD | #REF! | NO BUDGET
LCP-180179 | UPG DRIVES & CONTROLS – CAL3R | Facilities Maintaining | CLSD | #REF! | NO BUDGET
LCP-180180 | ANCHOR SYSTEM & SAFETYLINE - PHASE II | EHS | CLSD | #REF! | NO BUDGET
LCP-180205 | SORTER B2 - MRT TIRES ADEQUACY | SAG | CLSD | #REF! | NO BUDGET
LCP-190004 | DRIVE OVER READER BERTOLINI | SAG | CLSD | #REF! | NO BUDGET
LCP-190011 | QCO - MOTHER ROLL CALEMARD | Quality | CLSD | #REF! | NO BUDGET
LCP-190019 | AME - ANNUAL MISCELANEOUS <50K ALL PLANTS | Facilities Maintaining | CLSD | #REF! | NO BUDGET
LCP-190020 | AME - ROBOT FOR BEAD WINDER | Productivity | REL | #REF! | NO BUDGET
LCP-190025 | BRZ - WAREHOUSE SAFETY IMPROVEMENTS - AM PLANT | SAG | CLSD | #REF! | NO BUDGET
LCP-190047 | RET - ANNUAL MISCELLANEOUS <50K ALL PLANTS | Facilities Maintaining | CLSD | #REF! | NO BUDGET
LCP-190057 | AME - UP GRADE EXTRUSORA Q5 ( AUTOMAX ) PHASE 2 | Facilities Maintaining | CLSD | #REF! | NO BUDGET
LCP-190061 | SECURITY IMPROVEMENT IN (8) APEX APPLIER - NGTTS | EHS | CLSD | #REF! | NO BUDGET
LCP-190066 | REPLACEMENT OF BARREL AND SCREW - Q#5 | Facilities Maintaining | CLSD | #REF! | NO BUDGET
LCP-190068 | MC GERAL - MISCELANIUS QUARTELY | SAG | CLSD | #REF! | NO BUDGET
LCP-190078 | REPLACEMENT OF ROLLS CAL3R | Facilities Maintaining | CLSD | #REF! | NO BUDGET
LCP-190085 | BRZ - BLUE RACKS FOR CONSUMER TIRES | SAG | CLSD | #REF! | NO BUDGET
LCP-190089 | AME - X-RAY B UPGRADE | Facilities Maintaining | CLSD | #REF! | NO BUDGET
LCP-190092 | SHIPMENT SAFETY IMPROVEMENT | EHS | CLSD | #REF! | NO BUDGET
LCP-190117 | CAP-X-RAY GREEN POINT MARKER | Quality | CLSD | #REF! | NO BUDGET
LCP-190120 | CAP-PROT.SYST.RETROFITTING-MAIN SUBSTATI | Facilities Maintaining | CLSD | #REF! | NO BUDGET
LCP-190129 | FIRE FIGHTING SYSTEM BUILDING 76 | EHS | CLSD | #REF! | NO BUDGET
LCP-190132 | VEHICLE DYNAMICS AREA (VDA) REPAVING | SAG | CLSD | #REF! | NO BUDGET
LCP-190138 | WHEEL PULSE TRANSDUCERS - CWPTA | SAG | CLSD | #REF! | NO BUDGET
LCP-190140 | UPGRADE RING 18" CUV IN MC ANCHIETA | SAG | CLSD | #REF! | NO BUDGET
LCP-190142 | NEW OILLINE SYDININI | Quality | CLSD | #REF! | NO BUDGET
LCP-190143 | MOLD CLEAN S.B.O | Facilities Maintaining | CLSD | #REF! | NO BUDGET
LCP-190144 | WIRE CALENDER EDGE TRIMMING DEVICE | Quality | CLSD | #REF! | NO BUDGET
LCP-190149 | B1 - UPGRADE HMI HF PLT2 | Facilities Maintaining | CLSD | #REF! | NO BUDGET
LCP-190150 | B1 - UPGRADE PC-ETMS BALANCE AND FVM MACHINE | Facilities Maintaining | CLSD | #REF! | NO BUDGET
LCP-190151 | METAL DETECTOR IN APEXER (NAKATA) | Quality | CLSD | #REF! | NO BUDGET
LCP-190159 | (02) TRANSFER ORING NGTTS & MONO CUTTER IN ANGLE | Quality | CLSD | #REF! | NO BUDGET
LCP-190173 | DOR PROJECT IC TRANSPORTS | SAG | CLSD | #REF! | NO BUDGET
LCP-190178 | REPLACE AND UPGRADE OF ROLLS IN WIRE CALENDER | Facilities Maintaining | CLSD | #REF! | NO BUDGET
LCP-190184 | WIRE CALENDER WIGWAG FEED CONVEYOR | Quality | CLSD | #REF! | NO BUDGET
LCP-190186 | AER - CORSAIR PROJECT | SAG | CLSD | #REF! | NO BUDGET
LCP-190188 | AER - ANNUAL MISCELLANEOUS<50K ALL PLANTS | SAG | CLSD | #REF! | NO BUDGET
LCP-190199 | MOBILE DOCKLEVELER FOR NEW WAREHOUSE | SAG | CLSD | #REF! | NO BUDGET
LCP-190202 | MIXER#6 BODY REPLACEMENT | Facilities Maintaining | CLSD | #REF! | NO BUDGET
LCP-190203 | SAFETY SYSTEMRIVER PUMP AREA | EHS | CLSD | #REF! | NO BUDGET
LCP-190204 | INFLATION TESTING MACHINE | Quality | CLSD | #REF! | NO BUDGET
LCP-190208 | AME- (1) BALANCE MACHINE MARKER (DOWN SIDE) | Quality | CLSD | #REF! | NO BUDGET
LCP-190213 | ALPHA SHEARLETOFF TREATMENT | Productivity | CLSD | #REF! | NO BUDGET
LCP-190229 | UPGRADE TYLOR SYSTEM IN MRT CURING PRESSES | Facilities Maintaining | CLSD | #REF! | NO BUDGET
LCP-190231 | HOTFORMER UPGRADELINNER AND SCREW | Facilities Maintaining | CLSD | #REF! | NO BUDGET
LCP-200001 | AME-REPL & UPG OF ROLLS IN CAL3R | Facilities Maintaining | CLSD | #REF! | NO BUDGET
LCP-200008 | AME-REPL & UPG OF ROLLS IN CAL4R1 | Facilities Maintaining | CLSD | #REF! | NO BUDGET
LCP-200009 | AME-REPL & UPG OF ROLLS IN CAL4R2 | Facilities Maintaining | REL | #REF! | NO BUDGET
LCP-200011 | PCI IN (6) ROGERS MECHANICAL PRESSES | Capability | REL | #REF! | NO BUDGET
LCP-200023 | UPGRADE KOKUSAI #01 | Facilities Maintaining | CLSD | #REF! | NO BUDGET
LCP-200026 | AME-MISCELANEOUS QUARTELY 2020 | Facilities Maintaining | CLSD | #REF! | NO BUDGET
LCP-200028 | REPLACEMENT OF RING IN KOKUSAI | Facilities Maintaining | CLSD | #REF! | NO BUDGET
LCP-200030 | REPL OF ACCELERATOR TUBE - EBP SYSTEM FOR CAL3R | Facilities Maintaining | CLSD | #REF! | NO BUDGET
LCP-200037 | REPLACE OF ROLLS IN HOTFORMER | Facilities Maintaining | CLSD | #REF! | NO BUDGET
LCP-200053 | MIXER#7 BODY REPLACEMENT | Facilities Maintaining | CLSD | #REF! | NO BUDGET
LCP-200076 | HOTFORMER UPGLINNER AND SCREW STATIONS #04 | Facilities Maintaining | CLSD | #REF! | NO BUDGET
LCP-200077 | AME - BIJINIC TANK | Quality | CLSD | #REF! | NO BUDGET
LCP-200092 | AME-METAL DETECTOR IN CAL 4R2 | Quality | CLSD | #REF! | NO BUDGET
LCP-200115 | AME - BT DRUM WYKO UPGRADE | Facilities Maintaining | CLSD | #REF! | NO BUDGET
LCP-200116 | SBO - UPGRADE PLC AUTOMAX EXTRUDER | Facilities Maintaining | CLSD | #REF! | NO BUDGET
LCP-200117 | REWIND STATIONS MRTBUILD MACHINES | Facilities Maintaining | CLSD | #REF! | NO BUDGET
LCP-200119 | REPL MAIN GEARBOX 6” & 10” MRT EXTRUDER | Facilities Maintaining | CLSD | #REF! | NO BUDGET
LCP-200120 | UPGRADE TPMS SYSTEM MC GRAVATAI | SAG | CLSD | #REF! | NO BUDGET
LCP-200121 | AME - PRODUCTIVITY MRT | Productivity | CLSD | #REF! | NO BUDGET
LCP-200124 | AME - BAMBURIES BATCH-OFF CRANES | EHS | CLSD | #REF! | NO BUDGET
LCP-200125 | UPGRADE MICROPOISE BALANCE MACHINE ANCHIETA | SAG | CLSD | #REF! | NO BUDGET
LCP-200126 | UPGRADE DRIVE VTW MICRIPOISE BALANCE MACHINE - GRAVATAI | SAG | CLSD | #REF! | NO BUDGET
LCP-200129 | AME - SAFETY UPGRADE BEADWINDER #03 | EHS | CLSD | #REF! | NO BUDGET
LCP-200131 | AME - UPGRADE GENERAL PANEL CURING PRESSES MRT | Productivity | CLSD | #REF! | NO BUDGET
LCP-200137 | UPGRADE XLE#7 AIR COMPRESSOR | Facilities Maintaining | CLSD | #REF! | NO BUDGET
LCP-200142 | BARCODE SYSTEM IN SEQUENCING AREA ANCHIETA | SAG | CLSD | #REF! | NO BUDGET
LCP-200145 | AUTOMATICLOADING WIND UP – GUM CALENDER #2 | Productivity | CLSD | #REF! | NO BUDGET
LCP-200149 | MASTER PLAN SECURITY AMERICANA PLANT | EHS | CLSD | #REF! | NO BUDGET
LCP-200159 | COMFORTLANES REPAVING | SAG | CLSD | #REF! | NO BUDGET
LCP-200169 | ENGINEERING CONTRACTOR’S SHOP STANDARDIZATION | EHS | CLSD | #REF! | NO BUDGET
LCP-200170 | AME - UPGRADE DRIVE + MOTOR AC MILL MIXER#3 | Facilities Maintaining | REL | #REF! | NO BUDGET
LCP-200175 | RETROFIT–BLUE RACKS FOR CONSUMER TIRES | SAG | CLSD | #REF! | NO BUDGET
LCP-200177 | NEW POWER GENERATOR | SAG | CLSD | #REF! | NO BUDGET
LCP-210007 | AME - 2021 MISCELLANEOUS ANNUAL BUDGET | Facilities Maintaining | CLSD | #REF! | NO BUDGET
LCP-210010 | REPLACEMENT OF THE PRIMARY GEARBOX MIXER#06 | Facilities Maintaining | CLSD | #REF! | NO BUDGET
LCP-210011 | WASTEWATER TANK IMPROVEMENT | EHS | CLSD | #REF! | NO BUDGET
LCP-210014 | UPGRADE OF DRIVES BEADWINDER#03 | Facilities Maintaining | CLSD | #REF! | NO BUDGET
LCP-210016 | IMPROVEMENT CLIMATIZATION IN THE TBM'S | Quality | CLSD | #REF! | NO BUDGET
LCP-210018 | REPLACEMENT OF BOTTOM COOLING TANK D#4 | Facilities Maintaining | REL | #REF! | NO BUDGET
LCP-210022 | PROJECT RUNNER | SAG | CLSD | #REF! | NO BUDGET
LCP-210025 | UPG AKROSCAN SYSTEM FORLINES FVM | Facilities Maintaining | CLSD | #REF! | NO BUDGET
LCP-210038 | UPPER CONVEYORS UPGRADE – CURING B1 | EHS | REL | #REF! | NO BUDGET
LCP-210040 | FSB - 2021 MISCELLANEOUS ANNUAL BUDGET | Facilities Maintaining | CLSD | #REF! | NO BUDGET
LCP-210045 | AME - CREEL ROOM TRANSFER GADSDEN | Productivity | REL | #REF! | NO BUDGET
LCP-210052 | FIRE PROTECTION SYSTEM MAIN SUBSTATION | EHS | CLSD | #REF! | NO BUDGET
LCP-210055 | AME – WULO CONSUMMER BUILDING - STEP 1 - NT20 | EHS | REL | #REF! | NO BUDGET
LCP-210077 | AERO - VENTILATION AND EXHAUSTING SYSTEM | EHS | CLSD | #REF! | NO BUDGET
LCP-210078 | PNC - PNEUMATIC CORE CONSTRUCTION | Quality | REL | #REF! | NO BUDGET
LCP-210083 | RET - FLAT PRECURED EXPANSION | Growth | CLSD | #REF! | NO BUDGET
LCP-210084 | AME - UPG BARREL AND SCREWS | Facilities Maintaining | CLSD | #REF! | NO BUDGET
LCP-210085 | CAL4R2 - UPG OF THE BELT STEEL SYSTEM | Facilities Maintaining | CLSD | #REF! | NO BUDGET
LCP-210086 | AME - NEW MRT KOKUSAI MACHINE | Quality | REL | #REF! | NO BUDGET
LCP-210092 | RET - UPG PLC AND PRESS TEMP CONTROL | Facilities Maintaining | CLSD | #REF! | NO BUDGET
LCP-210098 | AME - UPG WIND-UP EXTRUDER 8X8 SW | Capability | REL | #REF! | NO BUDGET
LCP-210100 | FSB - FM GLOBAL ADEQUANCY | EHS | CLSD | #REF! | NO BUDGET
LCP-210101 | RET - NR24 - BATHROOM ADEQUANCY | EHS | CLSD | #REF! | NO BUDGET
LCP-210102 | AERO - NR12 - ADEQUANCY AERO RETREAD MACHINES | EHS | CLSD | #REF! | NO BUDGET
LCP-210103 | AME - RESTAURANT’S KITCHEN ADEQUACY | EHS | CLSD | #REF! | NO BUDGET
LCP-210106 | AME - CENTAC#17 100 PSI AIR COMPRESSOR | Facilities Maintaining | CLSD | #REF! | NO BUDGET
LCP-210107 | UPGRADE COOLING SYSTEM BB#4 | Facilities Maintaining | REL | #REF! | NO BUDGET
LCP-210110 | MC - 2021 ANNUAL MISCELLANEOUS <50K ALL PLANTS | SAG | CLSD | #REF! | NO BUDGET
LCP-210114 | AME -COMPLEXITY AND CONCURRENCY INCREASE | Capability | CLSD | #REF! | NO BUDGET
LCP-210118 | COOLING SYSTEM UPGRADE MIXER#02–PHASE I | Facilities Maintaining | CLSD | #REF! | NO BUDGET
LCP-210120 | AME - COOLING SYSTEM UPGRADE MIXER#03 | Facilities Maintaining | CLSD | #REF! | NO BUDGET
LCP-210121 | AME – WULO – CONSUMMER BUILDING - STEP 2 - NT22 | EHS | REL | #REF! | NO BUDGET
LCP-210123 | AME - REPLACEMENT X-RAY SET TUBE (A & C) | Facilities Maintaining | CLSD | #REF! | NO BUDGET
LCP-210132 | AME - STEEL TRANSFERS BAND NGTTS | Productivity | CLSD | #REF! | NO BUDGET
LCP-210133 | AME - MILLS ADEQUACY PROJECT FAM | EHS | CLSD | #REF! | NO BUDGET
LCP-210134 | AME – INTERNALLIGHTING ADEQUACY | EHS | CLSD | #REF! | NO BUDGET
LCP-210135 | MC - FALSE TRUCK TIRES SYSTEM RETROFIT | SAG | CLSD | #REF! | NO BUDGET
LCP-210137 | AME -SIDEWALK BUILDING IN FRONT OF PLANT | EHS | CLSD | #REF! | NO BUDGET
LCP-210138 | AME - NEW RAINWATER CONTAINMENT SYSTEM | EHS | CLSD | #REF! | NO BUDGET
LCP-210140 | AME - CAL 3R COOLING IMPROVEMENT | Productivity | CLSD | #REF! | NO BUDGET
LCP-210147 | AME - SAFETY NT CONSUMMER BUILDING ENHANCEMENT | EHS | REL | #REF! | NO BUDGET
LCP-210148 | AME - SAFETY TEXTIL CALENDER 3R | EHS | REL | #REF! | NO BUDGET
LCP-210149 | AME - CURING VACUUM SYSTEM UPGRADE | Productivity | REL | #REF! | NO BUDGET
LCP-210177 | AME - UPG EXTRUDER HEAD 8X3 EXTRUDER | Facilities Maintaining | CLSD | #REF! | NO BUDGET
LCP-210189 | CTVM - VBOX EQUIPMENT | SAG | CLSD | #REF! | NO BUDGET
LCP-210196 | AME - 4 PCI (8) CAVITIES | Quality | REL | #REF! | NO BUDGET
LCP-210200 | AME - MIXER #3 BODY REPLACEMENT | Facilities Maintaining | REL | #REF! | NO BUDGET
LCP-210204 | AME - NEW MIXER SLURRY - PLITVIC | Quality | CLSD | #REF! | NO BUDGET
LCP-210208 | AME - 2500 HP MAIN MOTOR - SPARE FOR MIXERS | Facilities Maintaining | REL | #REF! | NO BUDGET
LCP-210209 | AME - MIXER#07 REPLACEMENT 2ND GEARBOX | Facilities Maintaining | CLSD | #REF! | NO BUDGET
LCP-210212 | AME - MICROPOISE AIT BALANCE MACHINES (OBSOLESENCE) | Facilities Maintaining | CLSD | #REF! | NO BUDGET
LCP-210215 | AME - FIRE PROTECTION ADEQUACY | EHS | CLSD | #REF! | NO BUDGET
LCP-210217 | LAPG - PROVING GROUNDS REPAVE PHASE 1 | SAG | CLSD | #REF! | NO BUDGET
LCP-210218 | LAPG - NEW ELECTRICAL WIRE BOX SEPARATE WATER AND CABLES | SAG | CLSD | #REF! | NO BUDGET
LCP-210219 | AME - RETROFIT SYSTEM OF THE CREEL ROOM | Facilities Maintaining | CLSD | #REF! | NO BUDGET
LCP-210220 | AME - OVERHAUL CHILLER AND FANCOIL - MIXER BB03 | Facilities Maintaining | REL | #REF! | NO BUDGET
LCP-220008 | AME - MRT CURING PRESS PO1314 UPG | Facilities Maintaining | CLSD | #REF! | NO BUDGET
LCP-220010 | RET- REPLACEMENT OF EXTRUDER TCU | Facilities Maintaining | CLSD | #REF! | NO BUDGET
LCP-220012 | AME - NEW ROLLS FOR HOTFORMER | Quality | CLSD | #REF! | NO BUDGET
LCP-220013 | AME - 2022 MISCELLANEOUS ANNUAL BUDGET | Facilities Maintaining | CLSD | #REF! | NO BUDGET
LCP-220014 | AME - NR12 - SAFETY REGULARIZATION - PG0102 | EHS | REL | #REF! | NO BUDGET
LCP-220018 | BLUE RACK ADAPTATION TO NEW FIRE DEPARTMENT STANDARD (50% MINIMUM WATER FLOW IN THE FLOOR) - PHASE_2 | SAG | CLSD | #REF! | NO BUDGET
LCP-220020 | AME - DC MOTOR 1500HP FROM NORTH AMERICA | Facilities Maintaining | CLSD | #REF! | NO BUDGET
LCP-220027 | RET - EXTRUDER NEW SOAP APLICATION | Facilities Maintaining | CLSD | #REF! | NO BUDGET
LCP-220028 | AME - UPGRADE DRIVES GV3000 POR PF755 | Facilities Maintaining | CLSD | #REF! | NO BUDGET
LCP-220029 | AER - 2022 MISCELLANEOUS ANNUAL BUDGET | Facilities Maintaining | CLSD | #REF! | NO BUDGET
LCP-220031 | RET - 2022 MISCELLANEOUS ANNUAL BUDGET | Facilities Maintaining | CLSD | #REF! | NO BUDGET
LCP-220033 | FSB - CAMERA MONITORING SYSTEM | EHS | CLSD | #REF! | NO BUDGET
LCP-220045 | AME - WINDUP/LETOFF UPGRADE PROJECTS | EHS | CLSD | #REF! | NO BUDGET
LCP-220048 | AME - OTR PRESS TRANSFER (P85) | Facilities Maintaining | REL | #REF! | NO BUDGET
LCP-220060 | MC - 2022 ANNUAL MISCELLANEOUS <50K ALL PLANTS | SAG | CLSD | #REF! | NO BUDGET
LCP-220065 | MIXER 3 EXTRUDER GEARBOX REPLACEMENT | Facilities Maintaining | CLSD | #REF! | NO BUDGET
LCP-220082 | LAPG - WORKSHOP CLIMATIZER | SAG | REL | #REF! | NO BUDGET
LCP-220088 | POLO PROJECT VW TAUBATÉ | SAG | CLSD | #REF! | NO BUDGET
LCP-220089 | MICROPOISE FVM/DBM EQUIPMENT AND TGIS UPGRADES (FVM#03 E FVM#10) | Facilities Maintaining | REL | #REF! | NO BUDGET
LCP-220093 | RET - NR12 ADEQUANCY | EHS | CLSD | #REF! | NO BUDGET
LCP-220094 | LAPG 2022 - GERAL MISCELLANEOUS QUARTELY | SAG | CLSD | #REF! | NO BUDGET
LCP-220095 | LAPG - TEST AND QUALITY EQUIPMENTS | SAG | CLSD | #REF! | NO BUDGET
LCP-220107 | REBOUND TESTING EQUIPMENT | Facilities Maintaining | CLSD | #REF! | NO BUDGET
LCP-220117 | AME – EXTERN TOTEM GOODYEAR AMERICANA | EHS | CLSD | #REF! | NO BUDGET
LCP-220132 | 100 PSI AIR COMPRESSOR OVERHAUL CENTAC18 | Facilities Maintaining | CLSD | #REF! | NO BUDGET
LCP-220133 | AME - FACTORY PUMP WATER | Facilities Maintaining | CLSD | #REF! | NO BUDGET
LCP-220134 | FF B1 - UPGRADE PCHP-ETMS FVM MACHINES (AAA) | Facilities Maintaining | CLSD | #REF! | NO BUDGET
LCP-220139 | RET - NEW MAIN FRAME FLAT PRESS | Facilities Maintaining | CLSD | #REF! | NO BUDGET
LCP-220162 | CTVM - CENTER MAX OFFICE RETROFIT | SAG | CLSD | #REF! | NO BUDGET
LCP-220171 | AME - 2 RHEOMETER PREMIER MDR FORLABORATORY | Facilities Maintaining | CLSD | #REF! | NO BUDGET
LCP-220172 | AME - 01 NEW RUBBER PROCESS ANALYZER RPA | Facilities Maintaining | CLSD | #REF! | NO BUDGET
LCP-220173 | AME - IMPROVEMENT APPLIED APR FOR NGTTS | Quality | CLSD | #REF! | NO BUDGET
LCP-220176 | LAPG - NOISE - KIT VBOX EQUIPMENT | SAG | CLSD | #REF! | NO BUDGET
LCP-220184 | AME - BEAD COMPRESSION WKM-B4 | Capability | REL | #REF! | NO BUDGET
LCP-220201 | AME - UPG BARCODE READERS FINAL FINISH B2 | Facilities Maintaining | CLSD | #REF! | NO BUDGET
LCP-220202 | AME - 1 NUMETRIX 1ST TIRE CHECK VISION SYSTEM | Quality | CLSD | #REF! | NO BUDGET
LCP-220215 | RET - FM GLOBAL ADEQUANCY | EHS | CLSD | #REF! | NO BUDGET
LCP-220267 | AME - FLOOR AVAILABILITY TBM (LINER/PLY RACKS PURCHASE) | Facilities Maintaining | REL | #REF! | NO BUDGET
LCP-230021 | REPLACEMENT CAR EXCHANGE MOLDS AND BLADDERS FOR CURING B1 | Facilities Maintaining | REL | #REF! | NO BUDGET
LCP-230031 | AME - Q5 EXTRUDER 8” GEAR BOX (EPT-200) | Facilities Maintaining | REL | #REF! | NO BUDGET
LCP-230033 | AME - UPGRADE NO SISTEMA DE ROLL BENDING E COLETA DE DADOS PARA A CALANDRA 3 ROLOS | Quality | REL | #REF! | NO BUDGET
LCP-230034 | AME - UPG CALENDER EXTRUDER REPLACEMENT BB#2 | Facilities Maintaining | REL | #REF! | NO BUDGET
LCP-230053 | UPGRADE E+LCALENDER 3 ROLLS | Quality | REL | #REF! | NO BUDGET
LCP-230055 | AME - RETROFIT – BLUE RACKS FOR CONSUMER TIRES PHASE 3 | SAG | CLSD | #REF! | NO BUDGET
LCP-230098 | AME - TROCA DE ROSCAS DE EXTRUSORAS DIV. A (BB, HOT, EXT, CAL) | Facilities Maintaining | REL | #REF! | NO BUDGET
LCP-230110 | LAPG - 2023 MISCELLANEOUS ANNUAL BUDGET | SAG | CLSD | #REF! | NO BUDGET
LCP-230111 | AER - NEW SOAP APLICATION | Facilities Maintaining | CLSD | #REF! | NO BUDGET
LCP-230112 | LAPG - WHEELS RACKS | SAG | REL | #REF! | NO BUDGET
LCP-230115 | FSB - 2023 MISCELLANEOUS ANNUAL BUDGET | Facilities Maintaining | CLSD | #REF! | NO BUDGET
LCP-230116 | EQUIPMENT FOR VMI MACHINES TO BUILD 15”TIRES | Quality | CLSD | #REF! | NO BUDGET
LCP-230120 | MC - POLO PROJECT PHASE 02 | SAG | CLSD | #REF! | NO BUDGET
LCP-230121 | AER - NEW BUILDING MACHINE (AZ/SOL) - VMI MACHINE | Quality | REL | #REF! | NO BUDGET
LCP-230122 | BRA -CONVEYOR'S REPLACEMENT IN WH TOLOAD TIRES (3 UNITS) | SAG | CLSD | #REF! | NO BUDGET
LCP-230123 | MC - 2023 MISCELLANEOUS ANNUAL BUDGET | SAG | CLSD | #REF! | NO BUDGET
LCP-230124 | MC -LUBRIFICADOR DE CUBO DE RODA AUTOMATICO | SAG | CLSD | #REF! | NO BUDGET
LCP-230125 | MC - NR12 - ADEQUACY - ANCHIETA | SAG | REL | #REF! | NO BUDGET
LCP-230144 | AME - OVERHAULLASER 4JET MACHINE | Facilities Maintaining | CLSD | #REF! | NO BUDGET
LCP-230145 | AME - MIXER#6 TSR- 450C/20 ROLLER REPLACEMENT | Facilities Maintaining | CLSD | #REF! | NO BUDGET
LCP-230152 | AME - 2023 MISCELLANEOUS ANNUAL - PHASE2 | Facilities Maintaining | CLSD | #REF! | NO BUDGET
LCP-230154 | LAPG - RETROFIT OF THE CONTROL SPRAY PIPE | SAG | CLSD | #REF! | NO BUDGET
LCP-230167 | AME - NR12 - SAFETY REGULARIZATION BW#02 | EHS | REL | #REF! | NO BUDGET
LCP-230178 | AME - CAL4R#2 WIND-UP UPGRADE | Quality | REL | #REF! | NO BUDGET
LCP-230179 | AME - CAL4R#1 WIND-UP UPGRADE | Quality | REL | #REF! | NO BUDGET
LCP-230180 | AME-MIXER#7 TSRD ROLLER REPLACEMENT | Facilities Maintaining | CLSD | #REF! | NO BUDGET
LCP-230181 | AME - CAL_EXTR_GEARBOX MIXER#1 | Facilities Maintaining | CLSD | #REF! | NO BUDGET
LCP-230185 | AME - EBP SYSTEM MAJOR OVERHAUL | Facilities Maintaining | CLSD | #REF! | NO BUDGET
LCP-230186 | LAPG - REPAVING PROVING GROUND AND CFTV | SAG | REL | #REF! | NO BUDGET
LCP-230191 | AME - HIGH PRESSURE PUMP REPLACEMENT OTR | Facilities Maintaining | TECO | #REF! | NO BUDGET
LCP-230208 | AME - SAFETY REGULARIZATION ON WIND-UP (ACIDENTE 4R1) | EHS | CLSD | #REF! | NO BUDGET
LCP-230225 | AME - INSTALLATION OF DIV.A RACKS | Facilities Maintaining | REL | #REF! | NO BUDGET
LCP-230253 | MC - ECRS PROJECT BY GM EPIACABA SEQUENCING | SAG | REL | #REF! | NO BUDGET
LCP-240001 | LAPG - RETROFIT BUILDING PROVING GROUND | SAG | CLSD | #REF! | NO BUDGET
LCP-240087 | AME - UPGRADE GENERAL PANEL B2 CURING | Facilities Maintaining | REL | #REF! | NO BUDGET
LCP-240093 | AME - NEW TRUCK GATE | EHS | REL | #REF! | NO BUDGET
LCP-240096 | AME - UPG X-RAY COMPUTERS YXLON-MTIS | Quality | REL | #REF! | NO BUDGET
LCP-240097 | RET- NEW TRIMMER | Facilities Maintaining | REL | #REF! | NO BUDGET
LCP-240098 | FSB - 2024 MISCELLANEOUS ANNUAL BUDGET | Facilities Maintaining | REL | #REF! | NO BUDGET
LCP-240100 | NEW CHILLER | Facilities Maintaining | REL | #REF! | NO BUDGET
LCP-240101 | BRZ - RETROFIT FOR CONSUMER RACKS PHASE 4 | SAG | REL | #REF! | NO BUDGET
LCP-240102 | NEW AIR COMPRESSOR - 100 PSI - CENTAC 20 | Facilities Maintaining | REL | #REF! | NO BUDGET
LCP-240107 | LAPG - 2024 MISCELLANEOUS ANNUAL BUDGET | SAG | CLSD | #REF! | NO BUDGET
LCP-240110 | MC - GRAVATAI - NEW MICROPOISE BALANCER | SAG | CLSD | #REF! | NO BUDGET
LCP-240112 | AME - WINDOWS 10 FOR TGIS FVM AAA | Facilities Maintaining | CLSD | #REF! | NO BUDGET
LCP-240113 | AME - NG08 - SERVO DRIVE AND CONTROL REPLACEMENT | Facilities Maintaining | REL | #REF! | NO BUDGET
LCP-240114 | AME - TBM01 - SERVO DRIVE AND CONTROL REPLACEMENT | Facilities Maintaining | REL | #REF! | NO BUDGET
LCP-240115 | AME - EQUIPMENT FOR VMI MACHINES TO BUILD 15" TIRES | Capability | REL | #REF! | NO BUDGET
LCP-240124 | BRZ - VBOX KIT AND SENSORS | SAG | REL | #REF! | NO BUDGET
LCP-240128 | MC - MISCELLANEOUS ANNUAL BUDGET | SAG | CLSD | #REF! | NO BUDGET
LCP-240140 | AME - CONSUMER EXPANSION PHASE 2 | Growth | REL | #REF! | NO BUDGET
LCP-240149 | AME - HEXAPLEX RTS REPLACEMENT | Facilities Maintaining | REL | #REF! | NO BUDGET
LCP-240177 | FSB - INSPECTION CAMERA BUFFER E TRIMMER | Quality | CLSD | #REF! | NO BUDGET
LCP-240178 | FSB - PROFILE CONTROL ANDLENGTH EXTRUDER | Capability | CLSD | #REF! | NO BUDGET
LCP-240192 | AME - CALENDER ROLL GRINDING CAPABILITY | Quality | REL | #REF! | NO BUDGET
LCP-240196 | AME - NR12 - WULO PHASE 2 | EHS | REL | #REF! | NO BUDGET
LCP-240200 | MC – PROTECTIVE FENCE – WHEEL RACKS AREA | SAG | REL | #REF! | NO BUDGET
LCP-250008 | AME - MIXER#5 BODY REPLACEMENT | Facilities Maintaining | REL | #REF! | NO BUDGET
LCP-250028 | MC – MANUAL BALANCER MACHINES - ANCHIETA | SAG | REL | #REF! | NO BUDGET
LCP-250029 | RET - LIGHTING SYSTEM ADEQUATION | Facilities Maintaining | CRTD | #REF! | NO BUDGET
LCP-250030 | AME - REPLACEMENT OF BOTTOM COOLING TANK D#4 - PHASE 2 | Facilities Maintaining | REL | #REF! | NO BUDGET
LCP-250031 | AME - UPGRADE OF THE BELT STEEL SYSTEM GUN CALENDER - CAL4R1 | Facilities Maintaining | CRTD | #REF! | NO BUDGET
LCP-250033 | AME - REPLACEMENT OF THE METAL CONVEYOR HOTFORMER | Facilities Maintaining | CRTD | #REF! | NO BUDGET
LCP-250036 | AME - MILL ROLLERS 100 MIXER #4 | Facilities Maintaining | CRTD | #REF! | NO BUDGET
LCP-250040 | FSB - 2025 MISCELLANEOUS ANNUAL BUDGET | Facilities Maintaining | CRTD | #REF! | NO BUDGET
LCP-250041 | RET - UPGRADE DUST COLLECTOR BUFFER | Facilities Maintaining | REL | #REF! | NO BUDGET
LCP-250056 | FSB - FACTORY ACCESS CONTROL | EHS | CRTD | #REF! | NO BUDGET
Waiting1 | AME - NEW CREEL TO REPLACE CREEL TRANSFERED FROM GADSDEN | Productivity | NO BUDGET | #REF! | NO BUDGET
Waiting2 | AER - BARCODE TRACEABILITY PROJECT + RTS UPGRADE | Capability | NO BUDGET | #REF! | NO BUDGET
x1 | AME - REGIONAL ADJUSTMENT | Regional Adjustment | NO BUDGET | #REF! | NO BUDGET
x2 | AME - ADJUSMENT TO TARGET | Regional Adjustment | NO BUDGET | #REF! | NO BUDGET
x3 | AME - EQUIPMENT IN TRANSIT | Equipment in Transit | NO BUDGET | #REF! | NO BUDGET
x4 | RET - ADJUSTMENT TO TARGET | Facilities Maintaining | NO BUDGET | #REF! | NO BUDGET
ICP-210036 | AME - NEW MRT KOKUSAI MACHINE | Quality | REL | #REF! | NO BUDGET
ICP-230007 | AMERICANA WU/LO SAFETY UPGRADE | EHS | REL | #REF! | NO BUDGET
ICP-240001 | AME - NR12 - SAFETY ADEQUACY AND OBSOLESCENCE PROJECT FOR FVM’S MACHINE | EHS | REL | #REF! | NO BUDGET
Waiting3 | MC - 2025 MISCELLANEOUS ANNUAL BUDGET | SAG | NO BUDGET | #REF! | NO BUDGET
LCP-250021 | LAPG - 2025 MISCELLANEOUS ANNUAL BUDGET | SAG | CRTD | #REF! | NO BUDGET
LCP-240186 | AME - PREMIER MDR AUTOMATIC EQUIPMENT | Quality | REL | #REF! | NO BUDGET
LCP-240185 | AME - PREMIER RPA AUTOMATIC EQUIPMENT | Quality | REL | #REF! | NO BUDGET
LCP-230221 | AME - NR12 - SAFETY ADEQUACY AND OBSOLESCENCE PROJECT FOR FVM’S MACHINE | EHS | REL | #REF! | NO BUDGET
LCP-240059 | AME - 2024 MISCELLANEOUS ANNUAL BUDGET | Facilities Maintaining | REL | #REF! | NO BUDGET
LCP-230168 | AME - NR12 - SAFETY REGULARIZATION BW#05 | EHS | REL | #REF! | NO BUDGET
LCP-240152 | AME - (03) TRANSFER ORING WYKO – NGTTS | Facilities Maintaining | REL | #REF! | NO BUDGET
LCP-220266 | AME - (1) BEAD WINDER#8 | Facilities Maintaining | REL | #REF! | NO BUDGET
LCP-210213 | LAPG - CHARGER FOR ELETRIC VEHICLE | SAG | REL | #REF! | NO BUDGET
LCP-210190 | AME - (2) NEW AIR DRYER POWER HOUSE | Facilities Maintaining | REL | #REF! | NO BUDGET
LCP-220044 | AME - (1) NEW BOILER FEED WATER PUMP (POWER HOUSE) | Facilities Maintaining | REL | #REF! | NO BUDGET
LCP-230151 | AME - UPG BARCODE READERS PHASE 2 FF B2 | Facilities Maintaining | REL | #REF! | NO BUDGET
LCP-230007 | AME - 2023 MISCELLANEOUS ANNUAL BUDGET | Facilities Maintaining | REL | #REF! | NO BUDGET
ICP-220054 | AME PIGMENT WEIGHT SYSTEM | EHS | REL | #REF! | NO BUDGET
LCP-210020 | AME - NEW AIR COMPRESSOR - 100 PSI - CENTAC 19 | Facilities Maintaining | REL | #REF! | NO BUDGET
LCP-230205 | 100 PSI AIR COMPRESSOR OVERHAUL CENTAC14 | Facilities Maintaining | REL | #REF! | NO BUDGET
LCP-230159 | AME - NR12 - SAFETY REGULARIZATION NT 19 MG R3 | EHS | REL | #REF! | NO BUDGET
LCP-200185 | (VMI) AMERICANA CONSUMER HMC TIRE BUILDING | Capability | REL | #REF! | NO BUDGET
ICP-230034 | AMERICANA QUADRUPLEX EXTRUDER #7 | Capability | REL | #REF! | NO BUDGET
LCP-230196 | AME - NR12 - SAFETY REGULARIZATION NT 18 MG R3 | EHS | REL | #REF! | NO BUDGET
LCP-240179 | MC - SPARE TIRE DATA MATRIXLABEL IMPLEMENTATION | SAG | REL | #REF! | NO BUDGET
LCP-230206 | AME - NEW AWS DRUMS RSX1 | Quality | TECO | #REF! | NO BUDGET
LCP-190215 | AME - CONTOUR CORRECTION MACHINE | Quality | REL | #REF! | NO BUDGET
LCP-230166 | AME - NR12 - SAFETY REGULARIZATION BW#01 | EHS | REL | #REF! | NO BUDGET
LCP-230213 | AME - MAZAK INTEGREX J300 MACHINING CENTER | Facilities Maintaining | REL | #REF! | NO BUDGET
LCP-230158 | AME - NR12 - SAFETY ADEQUACY IN WULO (WULO PHASE 1) | EHS | REL | #REF! | NO BUDGET
LCP-240103 | AME - EQUIPMENT FOR VMI MACHINES TO BUILD 19" TIRES | Capability | REL | #REF! | NO BUDGET
LCP-220002 | AME - COGEN OVERHAUL | Facilities Maintaining | REL | #REF! | NO BUDGET
LCP-240191 | FSB - UPGRADE AERO RETREAD SHEAROGRAPHY | Facilities Maintaining | REL | #REF! | NO BUDGET
ICP-240032 | AME - HEXAPLEX RTS REPLACEMENT | Facilities Maintaining | REL | #REF! | NO BUDGET
ICP-240025 | EQUIPMENT FOR VMI MACHINES TO BUILD 15" TIRES | Capability | REL | #REF! | NO BUDGET
ICP-240020 | AME - UPG X-RAY COMPUTERS YXLON-MTIS | Quality | REL | #REF! | NO BUDGET
ICP-240024 | EQUIPMENT FOR VMI MACHINES TO BUILD 19" TIRES | Capability | REL | #REF! | NO BUDGET

## AME - Quarterly
[7 empty] | 483.3834 | 709.8518 | #REF! | 0 | 0 | 0 | 0 | 0 | 1893.7151 | 517.8161
AMERICANA QUARTELYS PROJECTS MANAGEMENT ($000)
WBS | PROJECT NAME | PROJECT TYPE | PREVIOUS STATUS SAP | STATUS COMPARISON | SAP STATUS (MACRO) | REASON FOR POSTPONATION | TOTAL 2023 | TOTAL 2024 | TOTAL 2025 | TOTAL 2026 | TOTAL 2027 | TOTAL 2028 | TOTAL 2029 | TOTAL 2030 | BUDGET APPROVED ON HOPPER | AOP CURRENT YEAR
LCP-230007-02 | ADEQUAÇÃO ÁREA ARMAZENAMENTO DE INFLAMÁVEIS DEPTO 85 | EHS | CLSD | #REF! | NO BUDGET |  | 0 | 88.1861 | #REF! | [5 empty] | 89.3
LCP-230007-03 | Retrofit (01) TORRE DE RESFRIAMENTO - MIXER | Facilities Maintaining | CLSD | #REF! | NO BUDGET |  | 0 | 43.2447 | #REF! | [5 empty] | 75
LCP-230007-04 | UPGRADE MIXER#1 - INSTALAÇÃO DE CÉLULA DE CARGA NA ESTEIRA DE CARREGAMENTO | Quality | REL | #REF! | NO BUDGET |  | 7.1559 | 77.3878 | #REF! | [5 empty] | 50
LCP-230007-13 | Upgrade 02 Relés de Proteção - Subestação Primária | Facilities Maintaining | CLSD | #REF! | NO BUDGET |  | 35.4489 | 11.9553 | #REF! | [5 empty] | 32
LCP-230007-15 | Speed up Gate way (comunicação PLC prensas com supervisório nivel1) | Quality | CLSD | #REF! | NO BUDGET |  | 27.7201 | 1.6427 | #REF! | [5 empty] | 25
LCP-230007-18 | GTU - Green tire Uniformity B1 (portable) | Quality | CLSD | #REF! | NO BUDGET |  | 47.6948 | 0.54834 | #REF! | [5 empty] | 67
LCP-230007-19 | Calandra Z - Regen | Facilities Maintaining | CLSD | #REF! | NO BUDGET |  | 1.5659 | 27.6816 | #REF! | [5 empty] | 71.5
LCP-230007-20 | SISTEMA DE MONITORAMENTO UNIDADE HIDRÁULICA DOS BANBURYS | Facilities Maintaining | CLSD | #REF! | NO BUDGET |  | 0 | 7.2595 | #REF! | [5 empty] | 12
LCP-230007-23 | CECOM DIV.B2 | EHS | CLSD | #REF! | NO BUDGET |  | 0 | 72.5237 | #REF! | [5 empty] | 60
LCP-230007-24 | RESFRIAMENTO DA CABINE DOLASER RAIO X 2A | Facilities Maintaining | CLSD | #REF! | NO BUDGET |  | 46.9459 | 0 | #REF! | [5 empty] | 49
LCP-230007-26 | TROCA DA ROSCA DE 6'' INFERIOR HEXAPLEX | Facilities Maintaining | CLSD | #REF! | NO BUDGET |  | 35.3947 | 0 | #REF! | [5 empty] | 17
LCP-230007-27 | Aplicador de rodagem NGTTS | Quality | CLSD | #REF! | NO BUDGET |  | 81.4222 | 13.969 | #REF! | [5 empty] | 46
LCP-230152-02 | CARRO DE CORTE NRM | Facilities Maintaining | CLSD | #REF! | NO BUDGET |  | 20.4305 | 3.8039 | #REF! | [5 empty] | 32
LCP-230152-03 | ADEQUAÇÃO DE SEGURANÇA CALANDRA Z | EHS | CLSD | #REF! | NO BUDGET |  | 1.2249 | 52.1957 | #REF! | [5 empty] | 93.0791
LCP-230152-04 | NOVO SISTEMA COMUNICAÇÃO BBYs 1,2,3,4 | Facilities Maintaining | CLSD | #REF! | NO BUDGET |  | 58.3716 | 15.217 | #REF! | [5 empty] | 93.5503
LCP-230152-05 | CAMERA PARA MONITORAMENTO DOS BBYs | Quality | CLSD | #REF! | NO BUDGET |  | 0 | 39.5274 | #REF! | [5 empty] | 20.017
LCP-230152-06 | CAÇAMBAS PARA COLETA SELETIVA FAM | EHS | CLSD | #REF! | NO BUDGET |  | 48.9314 | 33.5894 | #REF! | [5 empty] | 97.8602
LCP-230152-08 | UPG. SISTEMA ACIONAMENTO PRENSA MC NIEL | Facilities Maintaining | CLSD | #REF! | NO BUDGET |  | 35.7493 | 1.5952 | #REF! | [5 empty] | 50.0425
LCP-230152-09 | RETROFIT DISJ. GERAIS SUBESTAÇÕES 03 1CF | Facilities Maintaining | CLSD | #REF! | NO BUDGET |  | 0 | 16.8802 | #REF! | [5 empty] | 20.017
LCP-230152-10 | ANEL 4 AROS AKRODYNE | Produtivity | CLSD | #REF! | NO BUDGET |  | 35.3271 | 10.6911 | #REF! | [5 empty] | 48
LCP-240059-03 | SUBSTITUIÇÃO DA BOMBA #2 DA TORRE RESFRIAMENTO CASA DE FORÇA | Facilities Maintaining | TECO | #REF! | NO BUDGET |  |  | 40.5989 | #REF! | [5 empty] | 83 | 17
LCP-240059-04 | MAQ. MONTAGEM PNEUS P/ RESILIOMETRO | Facilities Maintaining | CLSD | #REF! | NO BUDGET |  |  | 5.8725 | #REF! | [5 empty] | 5.9 | 0
LCP-240059-05 | ADEQUAÇÃO SIST. DE ALIMENTAÇÃO ESTRUSORA | EHS | CLSD | #REF! | NO BUDGET |  |  | 11.0682 | #REF! | [5 empty] | 40.034 | 27.9
LCP-240059-06 | PRO-MIC EQUIPMENT TO MEASURE CALENDER CROWN | Quality | CLSD | #REF! | NO BUDGET |  |  | 0 | #REF! | [5 empty] | 99.98 | 62
LCP-240059-07 | MANIPULADOR DAS BANDAS DE CAMELBACK NA DUPLEX#1 | EHS | CLSD | #REF! | NO BUDGET |  |  | 14.1051 | #REF! | [5 empty] | 59.9486 | 10.5
LCP-240059-09 | APLICADORA DE ENVOLTÓRIO EM TALÃO | Produtivity | CLSD | #REF! | NO BUDGET |  |  | 15.7211 | #REF! | [5 empty] | 36 | 0
LCP-240059-10 | CONTROLE DE ACESSO PORTARIA | Facilities Maintaining | CLSD | #REF! | NO BUDGET |  |  | 11.2381 | #REF! | [5 empty] | 25.0454 | 7
LCP-240059-11 | UPGRADE PRENSAS MRT SLC500/CONTROLLOGIX5000 UPGRADE | Facilities Maintaining | CLSD | #REF! | NO BUDGET |  |  | 93.3494 | #REF! | [5 empty] | 100 | 0
LCP-240059-12 | CILINDRO DA PLACA DO GRIPPER | Productivity | TECO | #REF! | NO BUDGET |  |  | 0 | #REF! | [5 empty] | 50 | 90
LCP-240059-13 | POKA YOKE ISOLADORAS FASE 2 BEADWINDER DATA MANAGEMENT (NSNL) | Quality | TECO | #REF! | NO BUDGET |  |  | 0 | #REF! | [5 empty] | 50 | 65
LCP-250006-02 | FEEDBOX EXTRUSORA 6 INFERIOR Q5 | Facilities Maintaining | REL | #REF! | NO BUDGET | [9 empty] | 42 | 42
LCP-250006-03 | ADEQUACAO DE PAINEL MOTOBOMBA EDF.75 | Facilities Maintaining | REL | #REF! | NO BUDGET | [9 empty] | 50 | 46
LCP-250006-04 | JATEADORA DE GELO SECO | EHS | TECO | #REF! | NO BUDGET | [10 empty] | 54
LCP-250006-05 | BALANÇA PARA PONTE ROLANTE | Quality | REL | #REF! | NO BUDGET | [9 empty] | 8.393
LCP-250006-06 | MELHORIA UNIDADE HIDRÁULICA NGTTS | Facilities Maintaining | REL | #REF! | NO BUDGET | [9 empty] | 45 | 45
LCP-250006-07 | AUTOCOMPOUND Q5 SLOW MOVING | Quality | REL | #REF! | NO BUDGET
LCP-250006-08 | NOVO DISPERGRADER PARA MEDIÇÃO DA DISPERSÃO EM COMPOSTOS | Quality | REL | #REF! | NO BUDGET | [9 empty] | 51.4161 | 51.4161
LCP-250006-09 | MIXER 05 - TROCA TCU CALANDRA E EXTRUSORA | Facilities Maintaining | REL | #REF! | NO BUDGET
LCP-250006-10 | VALIDAÇÃO DE NR12 - TBMs | EHS | REL | #REF! | NO BUDGET | [9 empty] | 58.346
LCP-250006-11 | VALIDAÇÃO DE NR12 - NGs | EHS | REL | #REF! | NO BUDGET | [9 empty] | 40.286

## CAPEX RISK (hidden)
DASHBOARD - CAPEX RISKS
VALOR RISK
#REF!
IMPORTAÇÃO
| #REF! | #REF!
COMPRAS
| #REF! | #REF! | #REF!
FORNECEDOR
| #REF! | #REF!
ENGENHARIA
| #REF! | #REF!
PPP
| #REF! | #REF!

## COMPARATIVO CENARIOS 8+4 (hidden)
DASHBOARD - COMPARATIVO CENÁRIOS (OTIMISTA vs PESSIMISTA)
PESSIMISTA (riscos não mitigados)
BRZ |  | RISK |  | NEW FORECAST |  | CONTINGENCY PLAN |  | NEW TOTAL
12738.3911 | - | #REF! | = | #REF! | + | 969 | = | #REF!
AME |  | RISK |  | NEW FORECAST |  | CONTINGENCY PLAN |  | NEW TOTAL
8945.8878 | - | 999.745 | = | 7946.1428 | + | 591 | = | 8537.1428
OTIMISTA (riscos mitigados)
BRZ |  | RISK |  | NEW FORECAST |  | CONTINGENCY PLAN |  | NEW TOTAL
12738.3911 | - | 0 | = | 12738.3911 | + | 969 | = | 13707.3911
AME |  | RISK |  | NEW FORECAST |  | CONTINGENCY PLAN |  | NEW TOTAL
8945.8878 | - | 0 | = | 8945.8878 | + | 591 | = | 9536.8878

## Capex 4+8 (hidden)
CAPEX PROJECTS 2020 ($000)
|  |  |  | 3453.283 | 7907.1116 | 11360.3946 | 5469.212 | 2720.8855
NUM. PROJETO | NOME PROJETO | CATEGORY | Budget Total | Gasto 2020 (Jan-Abr) | Previsão Gasto (Maio-Dez) | TOTAL 2020 | Impossivel Parar | Plano Corte 2020 | WITH P.O | COMMENTS | IMPACT
LCP-180080 | COMMERCIAL TIRE BUILDING MACHINE | Capability | 10188.98 | 475.8269 | 319 | 794.8269 | 319 |  |  | Final costs to be transfer (Akron), Mechanical Drum should arrive Oct/20 | Finance
LCP-180010 | (3) NEW 52 HYDRAULIC CONSUMER PRESSES | Capability | 2961.5 | 150.7557 | 10 | 160.7557 | 10 |  |  | Necessary finalize the start-up | Start-up
LCP-180002 | FAM AVCB PHASE II EMERGENCY LIGHTINING AND ALARMS | EHS | 3492 | 0.90294 | 179 | 179.9029 |  | 179 |  | All works in primary substation will be executed in 2021 | Exception sheet (+18 Month)
LCP-180178 | WIND UP LET OFF NGTTS#5 & #8 | EHS | 242.75 | 3.9959 | 125.2139 | 129.2097 |  | 125.2139 |  | CTI Requirement | Compliance
LCP-180149 | EXHAUST SYSTEM - LINES A/B & G/H CONSUMER PRESSES | EHS | 438.68 | 66.6911 | 45.5 | 112.1911 |  | 45.5 |  | Liability | Liability
LCP-180180 | ANCHOR SYSTEM & SAFETY LINE - PHASE II | EHS | 560.6 | 9.717 | 73.9 | 83.617 | 73.9 |  |  | Brazilian law (NR35) | Compliance
LCP-190129 | FIRE FIGHTING SYSTEM BUILDING 76 | EHS | 96.3 | 0.59536 | 10 | 10.5954 | 10 |  |  | Fire Protection | Fire Protection
LCP-190092 | SHIPMENT SAFETY IMPROVEMENT | EHS | 11.5 | 9.2873 | 1.3 | 10.5873 | 1 |  |  | Start-up | Start-up
LCP-180157 | FIRE FIGHTING SYSTEM BUILDING 75 | EHS | 109 | 1.065 | 0 | 1.065 |  |  |  | Fire Protection | Fire Protection
LCP-180139 | POWER HOUSE STEAM TURBINE | Energy Conservation | 1326.87 | 12.0332 | 69.6609 | 81.6942 | 69.6609 |  | X | Equipment should arrive on Jul/20 | Energy Saving
LCP-180115 | AME - CLOSED WATER SYSTEM - MIXERS SUBSTATIONS | Energy Conservation | 320.65 | 2.8366 | 3.0648 | 5.9014 |  | 3.0648 |  | Energy Saving | Energy Saving
LCP-180116 | HVAC – CENTRAL OFFICE | Energy Conservation | 332.2 | 2.0255 | 0 | 2.0255 |  |  |  | Energy Saving | Energy Saving
LCP-180137 | (10) VDF PANEL INSTALLATION | Energy Conservation | 213 | 1.8244 | 0 | 1.8244 |  |  |  | Energy Saving | Energy Saving
LCP-200026 | AME-MISCELANEOUS QUARTELY 2020 | Facilities Sustaining | 1000 | 34.7037 | 828.2068 | 862.9105 |  | 828.2068 |  | EHS/PRODUCTIVITY/REALIBILITY | EHS/PRODUCTIVITY/REALIBILITY
LCP-190140 | UPGRADE RING 18" CUV IN MC ANCHIETA | Facilities Sustaining | 427.82 | 29.7319 | 399.8692 | 429.6012 | 399.8692 |  | Y | Strategic project to business | VW
LCP-190078 | REPLACEMENT OF ROLLS CAL3R | Facilities Sustaining | 1675.63 | 23.2375 | 360.144 | 383.3815 | 642.2 |  | X | Equipment should arrive in Aug/20 | Supplier Agreement
LCP-180117 | SAO - NEW ORBITREAD MACHINE | Facilities Sustaining | 387.67 | 0.02214 | 378.7 | 378.7221 | 378.7 |  | X | Equipment should arrive in Nov/20, to be Installed in 2021 | Supplier Agreement
LCP-200030 | REPL OF ACCELERATOR TUBE - EBP SYSTEM FOR CAL3R | Facilities Sustaining | 312.819 | 267.5342 | 81.9 | 349.4342 | 81.9 |  |  | Necessary finalize the start-up | Waste results
LCP-190089 | AME - X-ray B upgrade | Facilities Sustaining | 385.7 | 219.4108 | 115.7 | 335.1108 | 115.7 |  |  | Equipment Obsolete, high risk of failure | Lack of MRT Capacity
LCP-200023 | UPGRADE KOKUSAI #01 | Facilities Sustaining | 505.31 | 0 | 313.0025 | 313.0025 | 200 | 113 | X | Equipment should arrive on Nov/20, to be Installed in 2021 | Lack of MRT Capacity
LCP-190202 | MIXER#6 BODY REPLACEMENT | Facilities Sustaining | 1431.34 | 0 | 300 | 300 | 300 |  | X | Condition is high critical (detachment of chamber) in the next week will be check again. If necessary the body delivery in this year, the total cost = $1.1MM (>$800) | Lack of Mixers Capacity
LCP-200028 | REPLACEMENT OF RING IN KOKUSAI | Facilities Sustaining | 299.667 | 0 | 299.6676 | 299.6676 | 240 | 60 | X | Equipment should arrive in Oct/20, to be Installed in 2021 | Lack of MRT Capacity
LCP-180114 | LAMINATOR PROFILE AUTOMATION | Facilities Sustaining | 267.8 | 29.9817 | 129 | 158.9817 |  | 129 |  | Cost Reduction from over weight tire | Cost Reduction from over weight tire
LCP-180003 | GEM PROJECT EMC GRAVATAÍ | Facilities Sustaining | 3767.5 | 66.6412 | 38.2818 | 104.923 | 38.2818 |  | X | Finalize manipulator to attend production cycle and AVCB Requirement | Production and permits
LCP-200037 | REPLACE OF ROLLS IN HOTFORMER | Facilities Sustaining | 341.866 | 36.0672 | 55 | 91.0672 | 55 |  | X | Equipment should arrive on May/20 | Supplier Agreement
LCP-190204 | INFLATION TESTING MACHINE | Facilities Sustaining | 131.6 | 0 | 85.5 | 85.5 | 85.5 |  | X | Equipment should arrive on Jul/20, to be Installed in 2021 | Supplier Agreement
LCP-180179 | UPG DRIVES & CONTROLS – CAL3R | Facilities Sustaining | 783.3 | 75.5862 | 0 | 75.5862 |  |  |  | Without expenses in 2020
LCP-190231 | HOTFORMER UPGRADE LINNER AND SCREW | Facilities Sustaining | 225 | 3.2646 | 71.5 | 74.7646 | 71.5 |  |  | Out off spec - Comply with global standard GMS | Quality
LCP-190229 | UPGRADE TYLOR SYSTEM IN MRT CURING PRESSES | Facilities Sustaining | 120 | 0 | 60 | 60 | 60 |  | X | Equipment should arrive on Oct/20, to be Installed in 2021 | Supplier Agreement
LCP-190057 | AME - UP GRADE EXTRUSORA Q5 ( AUTOMAX ) PHASE 2 | Facilities Sustaining | 375.72 | 14.5183 | 40 | 54.5183 | 20 | 20 | X | Equipment should arrive on Jun/20, to be Installed in 2021 | Supplier Agreement
LCP-190203 | SAFETY SYSTEM RIVER PUMP AREA | Facilities Sustaining | 72.1 | 19.1046 | 23.3 | 42.4046 |  | 23.3 |  | Property Security | Property Security
LCP-180150 | SAO - SHEROGRAPHY UPGRADE (OBSEOLESCENCE AND SOFTWARE) | Facilities Sustaining | 77.8 | 26.215 | 10.7 | 36.915 | 10.7 |  |  | Equipment Obsolete, high risk of failure | Lack of aviation capacity
LCP-190019 | AME - ANNUAL MISCELANEOUS <50K ALL PLANTS | Facilities Sustaining | 1236 | 36.1973 | 0 | 36.1973 |  |  |  | Without expenses in 2020
LCP-190068 | MC Geral - Miscelanius Quartely | Facilities Sustaining | 75 | 28.5871 | 0 | 28.5871 |  |  |  | Without expenses in 2020
LCP-180097 | UPGRADE FACKTOR LINK/ GML D#4 | Facilities Sustaining | 275.96 | 19.7699 | 0 | 19.7699 |  |  |  | Without expenses in 2020
LCP-190199 | MOBILE DOCK LEVELER FOR NEW WAREHOUSE | Facilities Sustaining | 46 | 5.5895 | 14.1 | 19.6895 |  | 14.1 |  | lack of WH capacity | lack of WH capacity
LCP-180015 | UPGRADE OF DRIVES NRM#2 - CAL4R#2 | Facilities Sustaining | 454 | 5.7302 | 5.2 | 10.9302 | 5 |  |  | Safety deliveries | Exception sheet (+18 Month)
LCP-190120 | CAP-PROT.SYST.RETROFITTING-MAIN SUBSTATI | Facilities Sustaining | 85 | 10.6448 | 0 | 10.6448 |  |  |  | Without expenses in 2020
LCP-190188 | SAO - ANNUAL MISCELLANEOUS <50K ALL PLANTS | Facilities Sustaining | 10.5 | 9.4718 | 0 | 9.4718 |  |  |  | Without expenses in 2020
LCP-180013 | MIXER#2 BODY REPLACEMENT | Facilities Sustaining | 1426.22 | 7.0989 | 0 | 7.0989 |  |  |  | Without expenses in 2020
LCP-170118 | RET - THERMAL OIL BOILER | Facilities Sustaining | 248 | 1.1069 | 0 | 1.1069 |  |  |  | Without expenses in 2020
LCP-180090 | RET - UPGRADE DRIVE GV3000 TO POWERFLEX EXTRUDER | Facilities Sustaining | 211.9 | 0.00149 | 0 | 0.00149 |  |  |  | Without expenses in 2020
LCP-190178 | REPLACE AND UPGRADE OF ROLLS IN WIRE CALENDER | Facilities Sustaining | 445.88 | -25.0477 |  | -25.0477
LCP-190150 | B1 - UPGRADE PC-ETMS BALANCE AND FVM MACHINE | IT | 304 | 3.118 | 62 | 65.118 | 32 | 30 |  | Fiat Requirement (Tdip Shoulder) | lack of consumer capacity
LCP-190149 | B1 - UPGRADE HMI HF PLT2 | IT | 157.2 | 11.2323 | 37.6 | 48.8323 | 28 | 10 | X | Equipment should arrive on May/20, to be Installed in 2021 | Supplier Agreement
LCP-190020 | AME - ROBOT FOR BEAD WINDER | Productivity | 250 | 5.5183 | 195.4 | 200.9183 |  | 195.4 |  | Compensation Saving | Compensation Saving
LCP-190213 | ALPHA SHEAR LETOFF TREATMENT | Productivity | 126.48 | 9.3488 | 17.2 | 26.5488 |  | 17.2 |  | Compensation Saving | Compensation Saving
LCP-180014 | SEMI AUTOMATIC BEAD STAPLER | Productivity | 271 | 0 | 10 | 10 |  | 10 |  | Compensation Saving | Compensation Saving
LCP-XXXXXX | AME-METAL DETECTOR IN CAL 4R2 | Quality | 150 | 0 | 150 | 150 |  | 150 |  | Ford Requirement to attendance until end of 2020 | Ford Healthy Chart
LCP-190011 | QCO - MOTHER ROLL CALEMARD | Quality - Cost Savings | 57 | 13.726 | 4.9 | 18.6259 | 5 |  |  | Compensation Saving | Compensation Saving
LCP-190208 | AME- (1) BALANCE MACHINE MARKER (DOWN SIDE) | Quality - Improvement | 560.5 | 0 | 500.5 | 500.5 | 330 | 170.5 | X | Equipment should arrive on Oct/20, to be Installed in 2021 | Supplier Agreement
LCP-180174 | METAL DETECTOR IN EXTRUDERS | Quality - Improvement | 390.22 | 4.5163 | 317.4 | 321.9163 | 141 | 176.4 | X | Equipment should arrive on Jul/20, to be Installed in 2021 | Supplier Agreement
LCP-190159 | (02) TRANSFER ORING NGTTS & MONO CUTTER IN ANGLE | Quality - Improvement | 298.96 | 148.2864 | 158 | 306.2864 |  | 158 |  | Equipment delivered, to be installed in 2021 | Qualiy saving
LCP-190142 | NEW OIL LINE SYDININI | Quality - Improvement | 616.41 | 50.4687 | 176.2 | 226.6687 | 100 | 76 | X | Imported Equipment should arrive on May/20, to be Installed in 2021 | Supplier Agreement
LCP-200077 | AME - Bijinic Tank | Quality - Improvement | 213.85 | 0 | 170 | 170 |  | 170 |  | VW requirement to attendance until end of 2020 | VW requirement
LCP-200008 | AME-REPL & UPG OF ROLLS IN CAL4R1 | Quality - Improvement | 955.782 | 33.2128 | 1.7 | 34.9128 |  | 2 |  | Quality | Quality
LCP-180095 | AME - METAL DETECTOR IN CALANDERS (FORD PROJECT) | Quality - Improvement | 247 | 2.1102 | 15 | 17.1102 |  | 15 |  | Ford Requirement to attendance until end of 2020 | Ford Healthy Chart
LCP-190151 | METAL DETECTOR IN APEXER (NAKATA) | Quality - Improvement | 79 | 11.837 | 0 | 11.837 |  |  |  | Without expenses in 2020
LCP-200009 | AME-REPL & UPG OF ROLLS IN CAL4R2 | Quality - Improvement | 864.938 | 9.1975 | 0 | 9.1975 |  |  |  | Without expenses in 2020
LCP-200001 | AME-REPL & UPG OF ROLLS IN CAL3R | Quality - Improvement | 1208.957 | 5.9227 | 0 | 5.9227 |  |  |  | Without expenses in 2020
LCP-190117 | CAP-X-RAY GREEN POINT MARKER | Quality - Improvement | 67.5 | 5.6005 | 0 | 5.6005 |  |  |  | Without expenses in 2020
LCP-190186 | CORSAIR Project | SAG | 1490 | 76.0825 | 1316.5519 | 1392.6344 | 1316.5519 |  | Y | Project Strategy Business | Project Strategy Business
LCP-190132 | VEHICLE DYNAMICS AREA (VDA) REPAVING | SAG | 844.223 | 569.5375 | 151.6 | 721.1375 | 151.6 |  | Y | Project Strategy Business | Project Strategy Business
LCP-170154 | BRZ - AVCB NEW WAREHOUSE-BUILDING COMMERCIAL | SAG | 2866.6 | 123.4104 | 37.1481 | 160.5585 | 37.1481 |  |  | Necessary finalize to Cetesb Requirement | Cetesb Requirement
LCP-180081 | GEM PROJECT SÃO CAETANO DO SUL | SAG | 5863 | -23.4696 | 100 | 76.5304 | 100 |  | X | Manipulator / Paletization / False Truck / Whell grease application | GM
LCP-190173 | DOR PROJECT IC TRANSPORTS | SAG | 180.02 | 13.678 | 0 | 13.678 |  |  |  | Without expenses in 2020
LCP-190085 | BRZ - BLUE RACKS FOR CONSUMER TIRES | SAG | 140 | 6.1554 | 0 | 6.1554 |  |  |  | Without expenses in 2020
LCP-190004 | DRIVE OVER READER BERTOLINI | SAG | 190.97 | 3.1921 | 0 | 3.1921 |  |  |  | Without expenses in 2020
LCP-190025 | BRZ - WAREHOUSE SAFETY IMPROVEMENTS - AM PLANT | SAG | 26.2 | 0.00583 | 0 | 0.00583 |  |  |  | Without expenses in 2020
| AME - REGIONAL ADJUSTMENT | REGION |  | 652.869 |  | 652.869 |  |  |  | Region Adjustment | Region Adjustment
| AME - CAPITALIZED INTEREST | REGION |  | 35 | 39.5 | 74.5 | 40 |  |  | Capitalized Interest | Capitalized Interest
69.17%
[7 empty] | 2788 | P.O
[7 empty] | 1868 | Corsair/VDA/ARO 18
[7 empty] | 752 | SOBRA
5408